## Sheet1
Subcontractor: | J R Enterprises
State: | Uttar Pradesh
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold Amount For Quantity excess against DPR | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | SD (5%) | Advance paid | Total_Amount | UTR
[9 empty] | 1% | 5% | 5% & 10% | 10% | [6 empty] | 1% | 5%
52656
52656 | Ulhani BinaMazra Village Pipeline laying work | 2022-09-30 | 1 | 200061.5 | 0 | 200062 | 36011 | 236073 | 2001 | 10003 | 10003 | 20006 | 36011 | 20057 | 137992 |  | RIUP22/886 | 100000 | 1000 | 0 | 0 | 99000 | 03-10-2022 NEFT/AXISP00324920998/RIUP22/886/JAKIR S/O ISLAM 99000.00
52656 | GST Release Note | 2022-11-07 | 1 | 36011 | 0 | 36011 | 0 | 36011 | 0 | 0 | 0 | 0 | 0 | 0 | 36011 |  | RIUP22/940 | 100000 | 1000 | 0 | 0 | 99000 | 11-10-2022 NEFT/AXISP00327542818/RIUP22/940/JAKIRS/O ISLAM 99000.00
52656 | Ulhani BinaMazra Village Pipeline laying work | 2022-12-01 | 2 | 376174.25 | 0 | 376174.25 | 67711 | 443885.25 | 3762 | 18809 | 37617 | 37617 | 67711 | 66579 | 211790 |  | RIUP22/1470 | 187794 | 0 | 0 | 0 | 187794 | 12-12-2022 NEFT/AXISP00345679736/RIUP22/1470/JAKIRS/O ISLAM 187794.00
52656 | GST Release Note |  | 2 | 67711 | 0 |  |  |  |  | 0 |  |  | 0 |  | 67711 |  | RIUP22/1940 | 59400 | 0 |  | 0 | 59400 | 23-01-2023 NEFT/AXISP00356620202/RIUP22/1940/JAKIR S/O ISLAM ₹ 59,400.00
52656
52656
[12 empty] | Total Payable Amount Rs. - |  |  | 453504 |  |  |  |  | Total Paid Amount Rs. - |  | 445194
|  |  |  | 679957.75 | 0 | 612247.25 | 103722 | 715969.25 | 5763 | 28812 | 47620 | 57623 | 103722 | 86636 | [5 empty] | Balance Payable Amount Rs. - |  | 8310
203480
J R Enterprises
Updated On 19-08-2024 ( Vikash )
[9 empty] | Total Hold ( SD+OC+HT ) |  | 134055
[9 empty] | Advance / Surplus |  | 0
[9 empty] | DPR Excess |  | 86636
[9 empty] | GST Remaining |  | 0