## Sheet1
Subcontractor: | MK Traders
State: | Uttar Pradesh
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold Amount for excess Qty. against DPR | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | SD (5%) | Advance paid | Total_Amount | UTR
[9 empty] | 1% | 5% | 10% | 10% | [6 empty] | 1% | 5%
53526
53526 | Dhatera Village Balance Pipeline laying work | 2022-11-28 | 28 | 257436 | 0 | 257436 | 46338 | 303774 | 2574 | 12872 | 25744 | 25744 | 46338 | 41406 | 149096 |  | RIUP22/1476 | 149096 | 0 | 0 | 0 | 149096 | 12-12-2022 NEFT/AXISP00345679734/RIUP22/1476/M K TRADERS 149096.00
53526 | Dhatera Village Balance Pipeline laying work | 2023-01-30 | 60 | 247515 | 0 | 247515 | 44553 | 292068 | 2475 | 12376 | 24752 | 24752 | 44553 | 36259 | 146901 |  | RIUP22/2041 | 40000 | 400 | 0 | 0 | 39600 | 30-01-2023 NEFT/AXISP00358099602/RIUP22/2041/M K TRADERS 39600/-
53526 | GST Release note | 2023-03-05 | 28 | 46338 | 0 | 46338 | 0 | 46338 | 0 | [5 empty] | 46338 |  | RIUP22/2105 | 107301 | 0 | 0 | 0 | 107301 | 07-02-2023 NEFT/AXISP00361376406/RIUP22/2105/M K TRADERS ₹ 1,07,301.00
53526 | GST Release note | 2023-05-13 | 60 | 44553 | 0 | 44553 | 0 | 44553 | 0 | 0 |  |  | 0 |  | 44553 |  | RIUP22/2211 | 50000 | 500 | 0 | 0 | 49500 | 17-02-2023 NEFT/AXISP00364121242/RIUP22/2211/M K TRADERS 49500.00
53526 | Dhatera Village Balance Pipeline laying work | 2023-05-22 | 12 | 682668.5 | 522829.75 | 159838.75 | 28771 | 188610 | 1598 | 7992 | 15984 | 15984 | 28771 | 11291 | 106990 |  | RIUP22/2483 | 50000 | 500 | 0 | 0 | 49500 | 06-03-2023 NEFT/AXISP00369164326/RIUP22/2483/M K TRADERS 49500.00
53526 | GST Release note | 2023-08-16 | 60 | 44553 | 0 | 28771 | 0 | 28771 | 0 | 0 |  |  | 0 |  | 28771 |  | RIUP22/2670 | 46338 | 0 | 0 | 0 | 46338 | 27-03-2023 NEFT/AXISP00374579148/RIUP22/2670/M K TRADERS 46338.00
53526 | Dhatera Village Balance Pipeline laying work | 2023-07-22 | 21 | 273437 |  | 273437 | 49219 | 322656 | 2734 | 13672 | 27344 | 27344 | 49219 | 95677 | 106666 |  | SPUP23/0274 | 50000 | 500 | 0 | 0 | 49500 | 26-04-2023 26-04-2023 NEFT/AXISP00384433562/SPUP23/0274/M K TRADERS 49500.00
53526 | [16 empty] | RIUP23/268 | 44553 | 0 | 0 | 0 | 44553 | 18-05-2023 NEFT/AXISP00391091646/RIUP23/268/M K TRADERS 44553.00
53526 | [16 empty] | RIUP23/853 | 50000 | 500 |  |  | 49500 | 26-06-2023 NEFT/AXISP00400726015/RIUP23/853/M K TRADERS 49500.00
53526 | [16 empty] | RIUP23/1518 | 150000 | 1500 |  |  | 148500 | 14-08-2023 NEFT/AXISP00415763054/RIUP23/1518/M K TRADERS ₹ 1,48,500.00
53526 | [16 empty] | RIUP23/1583 | 28771 |  |  |  | 28771 | 18-08-2023 NEFT/AXISP00416613498/RIUP23/1583/M K TRADERS 28771.00
53526
53526
53526
53526
53526
[10 empty] | 75744 |  | 66480
[12 empty] | Total Payable Amount Rs.- |  |  | 629315 |  |  |  |  | Total Paid Amount Rs.- |  | 762159
[20 empty] | Balance Payable Amount Rs.- |  | -132844
|  |  | ITEM | DPR | CUM | EXCESS | RATE | AMOUNT
|  |  | BOE | 108.73 | 410.01 | 301.28 | 50 | 15064
|  |  | R BOE | 108.73 | 530.97 | 422.24 | 175 | 73892
[7 empty] | Hol amount | 88956
[7 empty] | Already hold | 77665
[7 empty] | To be hold | 11291