## Sheet1
Subcontractor: | Khatu Ji construction
State: | Uttar Pradesh
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | GST_SD_Amount | Hold against extra work | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% | [6 empty] | 1%
56246
56246 | Harsana, Kamalpur,Bhogi mazra village DG platform work | 2023-04-09 | 1 | 120000 | 0 | 120000 | 21600 | 141600 | 1200 | 6000 | 21600 |  | 112800 |  | SPUP23/0155 | 112800 |  | 112800 | 19-04-2023 19-04-2023 NEFT/AXISP00382939924/SPUP23/0155/SHIVANI WO SAND 112800.00
56246 | Yarpur,Mahavatpur,Dhakhori jamalpur,Khanpur village DG platform work | 2023-04-25 | 2 | 160000 | 0 | 160000 | 28800 | 188800 | 1600 | 8000 | 28800 |  | 150400 |  | RIUP23/262 | 75200 | 0 | 75200 | 17-05-2023 NEFT/AXISP00390799663/RIUP23/262/SHIVANI WO SANDE ₹ 75,200.00
56246 | Khera Gadai, Manatmanti village DG platform work | 2023-05-11 | 3 | 80000 | 0 | 80000 | 14400 | 94400 | 800 | 4000 | 14400 |  | 75200 |  | SPUP23/0359 | 150400 |  | 150400 | 03-05-2023 NEFT/AXISP00386899987/SPUP23/0359/SHIVANI WO SAND 150400.00
56246 | Jafarpur,Titoly, Jangheri, Hassanpur village DG platform work | 2023-06-04 | 4 | 160000 | 0 | 160000 | 28800 | 188800 | 1600 | 8000 | 28800 |  | 150400 |  | RIUP23/574 | 150400 |  | 150400 | 13-06-2023 NEFT/AXISP00398036679/RIUP23/574/SHIVANI WO SANDE 150400.00
56246 | Rangana village DG platform work | 2023-06-20 | 5 | 40000 | 0 | 40000 | 7200 | 47200 | 400 | 2000 | 7200 |  | 37600 |  | RIUP23/575 | 37600 |  | 37600 | 28-06-2023 NEFT/AXISP00401442264/RIUP23/856/SHIVANI WO SANDE 37600.00
56246 | Gandharva and Bibipur Hathiya village DG platform work | 2023-08-16 | kjc23/24/006 | 80000 |  | 80000 | 14400 | 94400 | 800 | 4000 | 14400 |  | 75200 |  | RIUP23/576 | 75200 |  | 75200 | 28-08-2023 NEFT/AXISP00418772999/RIUP23/1732/SHIVANI WO SANDEEP/IDIB000T081 75200.00
56246 | Panjokhera village DG platform work | 2023-09-05 | 7 | 40000 |  | 40000 | 7200 | 47200 | 400 | 2000 | 7200 |  | 37600 |  | RIUP23/577 | 37600 |  | 37600 | 07-09-2023 NEFT/AXISP00422860737/RIUP23/1889/SHIVANI WO SANDEEP/IDIB000T081 37600.00
56246 | Bharsi village DG platform work | 2023-10-05 | 7 | 40000 |  | 40000 | 7200 | 47200 | 400 | 2000 | 7200 |  | 37600 |  | RIUP23/2608 | 37600 |  | 37600 | 10-10-2023 NEFT/AXISP00432944786/RIUP23/2608/SHIVANI WO SANDEEP/IDIB000T081 37600.00
56246
56246
56246
56246
[9 empty] | Total Payable Amount Rs. - |  |  |  | 676800 |  | Total Paid Amount Rs. - |  |  | 676800
[15 empty] | Balance Payable Amount Rs. - |  |  | 0