## Sheet1
Subcontractor: | VIDESHI LAL VERMA
State: | Uttar Pradesh | [5 empty] | Pipeline Laying work
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold Amount For Quantity excess against DPR | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | SD (5%) | Advance paid | Total_Amount | UTR
[9 empty] | 1% | 5% | 10% | 10% | [6 empty] | 1% | 5%
57795 | ISSOPUR TEEL Village Pipeline laying work | 2023-07-10 | 1 | 263745.15 | 18014.15 | 245731 |  | 245731 | 2457 | 12287 | 24573 | 24573 | 0 | 0 | 181841 |  | RIUP23/646 | 50000 | 500 | 0 | 0 | 49500 | 13-06-2023 NEFT/AXISP00398119349/RIUP23/646/VIDESHI LAL VERM 49500.00
57795 | ISSOPUR TEEL Village Pipeline laying work | 2023-07-24 | 2 | 151129.72 | 22517.5 | 128612.22 |  | 128612.22 | 1286 | 6431 | 12861 | 12861 | 0 | 0 | 95173 |  | RIUP23/960 | 50000 | 500 |  |  | 49500 | 30-06-2023 NEFT/AXISP00402141209/RIUP23/960/VIDESHI LAL VERM 49500.00
57795 | [16 empty] | RIUP23/1104 |  |  |  |  | 82841 | 17-07-2023 NEFT/AXISP00407488698/RIUP23/1104/VIDESHI LAL VER 82841.0
57795 | [15 empty] | 0 | RIUP23/12519 | 50000 | 500 |  |  | 49500 | 14-08-2023 NEFT/AXISP00415763053/RIUP23/1519/VIDESHI LAL VER ₹ 49,500.00
57795 | [16 empty] | RIUP23/1294 |  |  |  |  | 79174 | 31-07-2023 NEFT/AXISP00859645626/RIUP23/1294/VIDESHI LAL VER 79174.00
57795 | [16 empty] | RIUP23/2858 |  |  |  |  | 49500 | 25-10-2023 NEFT/AXISP00436731130/RIUP23/2858/VIDESHI LAL VERMA/CBIN0284109 49500.00
57795
[12 empty] | Total Payable Amount Rs. - |  |  | 277014 |  |  |  |  | Total Paid Amount Rs. - |  | 310515
|  |  |  | 414874.87 | 40531.65 | 374343.22 | 0 | 374343.22 | 3743 | 18718 | 37434 | 37434 | 0 | 0 | [5 empty] | Balance Payable Amount Rs. - |  | -33501
|  | Dia of PIPE | DPR | Ambay tools | Videshi Lal Verma | Cum
| Quantity as per revised Drawing | 63 | 5358 | 751.3 | 0 | 751.3
|  | 75 | 563 | 77 | 93 | 170
|  | 90 | 1250 | 275.4 | 321.4 | 596.8
|  | 110 | 262 | 138.5 | 42 | 180.5
|  | 160 | 252 | 242.2 | 0 | 242.2
|  | 200 | 14 | 0 | 0 | 0
| Quantity as per DPR | FHTC | 921 | 43 | 39 | 82
|  | Dism. BOE | 23.21 | 448.19 |  | 448.19
|  | Dism. BT | 669.51 | 0 | 163.35 | 163.35
|  | Dism. IL | 671.91 | 0 | 0 | 0
|  | Dism. C C | 2313.9 | 270.54 | 337.43 | 607.97
|  | RR. BOE | 23.21 | 0 | 0 | 0
|  | RR. BT | 669.51 | 0 | 0 | 0
|  | RR. IL | 671.91 | 0 | 0 | 0
|  | RR. C C | 2313.9 | 0 | 0 | 0