## Sheet1
Subcontractor: | Ashwini Kumar Pandey
State: | Uttar Pradesh | [5 empty] | Pipeline laying work
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold Amunt for Quantity excess anainst DPR | Final_Amount | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | SD (5%) | Advance paid | Total_Amount | UTR | remark
[9 empty] | 1% | 5% | 10% | 10% | [5 empty] | 1% | 5%
51820 | Jafarpur Village Pipeline laying work | 2022-12-01 | AKP/01 | 1106460 | 0 | 1106460 | 199163 | 1305623 | 11065 | 55323 | 110646 | 110646 | 199163 | 138542 | 680238 | RIUP22/429 | 300000 | 3000 | 0 | 0 | 297000 | 30-07-2022 NEFT/AXISP00307447419/RIUP22/429/ASHWINI KUMAR PA 297000.00
51820 | GST |  | 1 | 199163 | [10 empty] | 199163 | RIUP22/488 | 200000 | 2000 | 0 | 0 | 198000 | 09-08-2022 NEFT/AXISP00310655299/RIUP22/488/ASHWINI KUMAR PA 198000.00
51820 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | RIUP22/587 | 100000 | 1000 |  |  | 99000 | 23-08-2022 NEFT/AXISP00313590074/RIUP22/587/ASHWINI KUMAR PA 99000.00
51820 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | RIUP22/768 | 100000 | 1000 |  | 0 | 99000 | 16-09-2022 NEFT/AXISP00320727447/RIUP22/768/ASHWINI KUMAR PA 99000.00
51820 | [15 empty] | RIUP22/1842 | 200000 | 2000 |  |  | 148500 | 11-01-2023 NEFT/AXISP00354136365/RIUP22/1842/ASHWINI KUMAR P 148500.00
51820 | [17 empty] | 0 |  |  |  |  | 37901
52349 | Jaffarpur Village Pump House work | 2022-12-03 | 4 | 185000 | 9537.5 | 175463 | 31583 | 207046 | 1754.63 | 8773.15 |  | 31583 | 31583 |  | 133352 | RIUP22/683 | 100000 | 1000 |  |  | 99000 | 03-09-2022 NEFT/AXISP00317096343/RIUP22/683/ASHWINI KUMAR PA 99000.00
52349 | GST |  | 4 | 31583 | [10 empty] | 31583 | RIUP22/767 | 100000 | 1000 |  |  | 99000 | 16-09-2022 NEFT/AXISP00320727448/RIUP22/767/ASHWINI KUMAR PA 99000.00
52349 | [15 empty] | RIUP22/842 | 100000 | 1000 | 0 |  | 99000 | 29-09-2022 NEFT/AXISP00323307453/RIUP22/842/ASHWINI KUMAR PA 99000.00
52349 | [22 empty] | -132065
52351 | Jafarpur Village OHT Construction work | 2023-02-25 | 3 | 826658.7 | 636868 | 189790.7 | 34162.326 | 223953.026 | 0 | 9489.535 |  | 0 | 34162.326 |  | 180301.165 | RIUP22/682 | 100000 | 1000 | 0 | 0 | 99000 | 03-09-2022 NEFT/AXISP00317096342/RIUP22/682/ASHWINI KUMAR PA 99000.00
52351 | GST |  | 3 | 34162.326 | [10 empty] | 34162.326 | RIUP22/709 | 200000 | 2000 | 0 | 0 | 198000 | 09-09-2022 NEFT/AXISP00318849701/RIUP22/709/ASHWINI KUMAR PA 198000.00
52351 | [15 empty] | RIUP22/1045 | 250000 | 2500 |  |  | 247500 | 20-10-2022 NEFT/AXISP00330028510/RIUP22/1045/ASHWINI KUMAR P 247500.00
52351 | [15 empty] | RIUP22/2414 | 200000 | 2000 |  | 0 | 198000 | 2-03-2023 NEFT/AXISP00367916641/RIUP22/2414/ASHWINI KUMAR P 198000.00
52351 | [22 empty] | -528036.509
52494 | Kheragadai Village OHT Construction work 175 Kl 16 mtr work | 2023-02-25 | 2 | 509900.8 | 283116 | 226785 | 40821.3 | 267606.3 | 2268 | 11339 | 22679 | 0 | 40821.3 |  | 190499 | RIUP22/827 | 250000 | 2500 | 0 | 0 | 247500 | 26-09-2022 NEFT/AXISP00322525750/RIUP22/827/ASHWINI KUMAR PANDEY ₹ 2,47,500.00
52494 | GST |  | 2 | 40821.3 | [10 empty] | 40821.3 | RIUP22/1106 | 100000 | 1000 | 0 | 0 | 99000 | 21-10-2022 NEFT/AXISP00331059030/RIUP22/1106/ASHWINI KUMAR P 99000.00
52494 | [15 empty] | RIUP22/1125 | 50000 | 500 | 0 | 0 | 49500 | 29-10-2022 NEFT/AXISP00332271913/RIUP22/1125/ASHWINI KUMAR P 49500.00
52494 | [15 empty] | RIUP/22/1862 | 200000 | 2000 | 0 | 0 | 198000 | 13-01-2023/NEFTAXISP00327681888 /RIUP/22/1862/ASHWINI KUMAR P 198000.00
52494 | [15 empty] | RIUP22/2315 | 200000 | 2000 | 0 | 0 | 198000 | 27-02-2023 NEFT/AXISP00365798946/RIUP22/2315/ASHWINI KUMAR P 198000.00
52494 | [22 empty] | -560679.7
52497 | Yarpur village OHTwork | [14 empty] | RIUP22/873 | 50000 | 500 | 0 | 0 | 49500 | 01-10-2022 NEFT/AXISP00324596974/RIUP22/873/ASHWINI KUMAR PA 49000.00
52497 | [15 empty] | RIUP22/1391 | 400000 | 4000 | 0 | 0 | 396000 | 01-12-2022 NEFT/AXISP00342521078/RIUP22/1391/ASHWINI KUMAR P 396000.00
-445500
[9 empty] | 15087.63 | 84924.685 | 133325 | 142229 | 305729.626 | 138542 | 1490119.791 |  | 3200000 |  | Total Paid Amount Rs. - |  | 3118500
-1628380.209
[19 empty] | Balance Payable Amount Rs. - |  | -1628380.209
A K pandey
22.7.24 - Girija Joshi
[8 empty] | Total Hold |  | 360478.685
[8 empty] | DPR Excess Debit |  | 138542
[8 empty] | Advance/ Surplus |  | -1628380.209
[8 empty] | GST Remaining |  | 0