## Sheet1
Subcontractor: | Abhinisha infra MZN
State: | Uttar Pradesh
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | Hydro_Testing | GST_SD_Amount | Final_Amount | PAYMENT NOTE No. | Amount | TDS Amount @ 1% on BASIC AMOUNT | SD (5%) | Advance paid | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% | 10% | 18% |  |  |  | 1% | 5%
54347 | Mohiddinpur Village All Work | [12 empty] | RIUP22/1812 |  | 0 | 0 | 0 | 99000 | 09-01-2023 NEFT/AXISP00353457265/RIUP22/1812/ABHINISHA INFRA 99000.00
54347 | Mohiddinpur Village All Work |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RIUP22/2061/ |  | 0 | 0 | 0 | 99000 | 01-02-2023 NEFT/AXISP00359583342/RIUP22/2061/ABHINISHA INFRA ₹ 99,000.00
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
54350 | Mujahidpur Village All Work | [11 empty] | 0 | RIUP22/1813 |  | 0 | 0 | 0 | 99000 | 09-01-2023 NEFT/AXISP00353457267/RIUP22/1813/ABHINISHA INFRA 99000.00
54350 | Mujahidpur Village All Work |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RIUP22/2062 |  | 0 | 0 | 0 | 99000 | 01-02-2023 NEFT/AXISP00359583341/RIUP22/2062/ABHINISHA INFRA ₹ 99,000.00
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54354 | Mubarikpur Village Boundary wall Work | 2023-03-06 | 3 | 244860 | 22800 | 222060 | 39971 | 262031 | 2221 | 0 | 22206 | 39971 | 197633 | RIUP22/1902 | 100000 | 1000 | 0 | 0 | 99000 | 18-01-2023 NEFT/AXISP00355710815/RIUP22/1902/ABHINISHA INFRA ₹ 99,000.00
54354 | Mubarikpur Village OHT Work | 2023-04-13 | 2 | 170888 | 134250 | 36638 | 6595 | 43233 | 366 | 1831.9 | 3663.8 | 6595 | 30776 | RIUP22/2063 | 100000 | 1000 | 0 | 0 | 99000 | 01-02-2023 NEFT/AXISP00359583343/RIUP22/2063/ABHINISHA INFRA ₹ 99,000.00
54354 | Mubarikpur Village Boundary wall Work | 2023-04-13 | 1 | 81620 | 0 | 81620 | 14692 | 96312 | 816 | 0 | 8162 | 14692 | 72642 | RIUP22/2634 | 30409 | 0 | 0 | 0 | 30409 | 30-03-2023 NEFT/AXISP00376411983/RIUP22/2634/ABHIN ISHA INFRA 30409.00
54354 | GST Release Note |  | 3 | 39971 |  |  | 39971 | [5 empty] | 39971 | RIUP23/2635 | 72642 | 0 | 0 | 0 | 72642 | 20-04-2023 20-04-2023 NEFT/AXISP00383281375/SPUP23/0140/ABHINISHA INFRA 72642.00
54354 | GST Release Note |  | 2 | 6595 |  |  | 6595 | [5 empty] | 6595 | RIUP23/077 | 46566 |  |  |  | 46566 | 10-05-2023 NEFT/AXISP00388990948/RIUP23/077/ABHINISHA INFRA 46566.00
54354 | GST Release Note |  | 1 | 14692 |  |  | 14692 | [5 empty] | 14692 | RIUP23/2766 | 14692 |  |  |  | 14692 | 08-11-2023 NEFT/AXISP00442118542/RIUP23/2766/ABHINISHA INFRA/YESB0001014 14692.00
54354 | Mubarikpur Village OHT Work | 2023-06-12 | 17 | 683554.2 | 223132 | 460422 | 82876 | 543298 | 4604 | 23021.1 | 46042.2 | 82876 | 386755
54667 | Silajuddi Village OHT Construction 150 kl 12m Work | 2023-03-06 | 1 | 110211.8 | 68178 | 42034 | 7566 | 49600 | 420 | 2101.7 | 4203 | 7566 | 35309 | RIUP22/2558 | 35309 | 0 | 0 | 0 | 35309 | 17-03-2023 NEFT/AXISP00372194503/RIUP22/2558/ABHINISHA INFRA 35309.00
54667 | Silajuddi Village OHT Construction 150 kl 12m Work | 2023-05-08 | 7 | 220423 | 76000 | 144423 | 25996 | 170419 | 1444 | 7221.15 | 14442 | 25996 | 121316 | RIUP23/076 | 7566 | 0 | 0 | 0 | 7566 | 10-05-2023 NEFT/AXISP00388990949/RIUP23/076/ABHINISHA INFRA 7566.00
54667 | GST Release Note |  | 1 | 7566 | [8 empty] | 7566 | RIUP23/219 | 121317 | 0 | 0 | 0 | 121317 | 25-05-2023 NEFT/AXISP00392595794/RIUP23/219/ABHINISHA INFRA 121317.00
54667 | Silajuddi Village OHT Construction 150 kl 12m Work | 2023-05-31 | 14 | 220423 | 27991 | 192432 | 34638 | 227070 | 1924 | 9621.6 | 19243 | 34638 | 161643 | RIUP23/559 | 161643 |  |  |  | 161643 | 09-06-2023 NEFT/AXISP00397387005/RIUP23/559/ABHINISHA INFRA 161643.00
54667 | [13 empty] | RIUP23/677 | 200000 | 2000 |  |  | 198000 | 15-06-2023 NEFT/AXISP00398797337/RIUP23/677/ABHINISHA INFRA 198000.00
54668 | Bibipur Village OHT Construction 150 kl 12m Work | 2023-03-06 | 8 | 110211.8 | 0 | 110212 | 19838 | 130050 | 1102 | 5510.6 | 11021 | 19838 | 92578 | RIUP23/222 | 116050 | 0 | 0 | 0 | 116050 | 12-05-2023 NEFT/AXISP00389894137/RIUP23/222/ABHINISHA INFRA 116050.00
54668 | Bibipur Village OHT Construction 150 kl 12m Work | 2023-05-08 | 5 | 220423.6 | 82268 | 138156 | 24868 | 163024 | 1382 | 6907.8 | 13816 | 24868 | 116050 | RIUP22/2623 | 92578 | 0 | 0 | 0 | 92578 | 17-03-2023 NEFT/AXISP00372194520/RIUP22/2623/ABHINISHA INFRA 92578.00
54668 | GST Release Note |  | 8 | 19838 | [8 empty] | 19838 | RIUP23/081 | 19838 | 0 | 0 | 0 | 19838 | 04-05-2023 NEFT/AXISP00387404081/RIUP23/081/ABHINISHA INFRA 19838.00
54668 | Bibipur Village OHT Construction 150 kl 12m Work | 2023-05-31 | 15 | 220423.6 | 24191 | 196233 | 35322 | 231555 | 1962 | 9811.65 | 19623 | 35322 | 164836 | RIUP23/560 | 164835 | 0 |  |  | 164835 | 09-06-2023 NEFT/AXISP00397387006/RIUP23/560/ABHINISHA INFRA 164835.00
54668 | Bibipur Village OHT Construction 150 kl 12m Work | 2023-07-20 | 30 | 67691 |  | 67691 | 12184 | 79875 | 677 | 3385 | 6769 | 12184 | 56860 | RIUP23/678 | 200000 | 2000 |  |  | 198000 | 15-06-2023 NEFT/AXISP00398797336/RIUP23/678/ABHINISHA INFRA 198000.00
54668 | GST Release Note
54668 | GST Release Note
55306 | Khanpur Village Boundary wall Work | 2023-03-06 | 6 | 251055 | 127058 | 123997 | 22319 | 146316 | 1240 | 12399.7 | 0 | 22319 | 110357 | RIUP22/2584 | 110357 | 0 | 0 | 0 | 110357 | 27-03-2023 NEFT/AXISP00374448946/RIUP22/2584/ABHINISHA INFRA 110357.00
55306 | Khanpur Village Boundary wall Work | 2023-04-13 | 2 | 83685 | 0 | 83685 | 15063 | 98748 | 837 | 8368.5 | 0 | 15063 | 74480 | SPUP23/0141 | 74479 | 0 | 0 | 0 | 74479 | 20-04-2023 20-04-2023 NEFT/AXISP00383281374/SPUP23/0141/ABHINISHA INFRA 74479.00
55306 | GST Release Note |  | 6 | 22319 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22319 | RIUP23/079 | 22319 | 0 | 0 | 0 | 22319 | 04-05-2023 NEFT/AXISP00387404082/RIUP23/079/ABHINISHA INFRA 22319.00
55306 | GST Release Note |  | 2 | 15063 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15063 | RIUP23/2767 | 15063 |  |  |  | 15063 | 26-10-2023 NEFT/AXISP00437006016/RIUP23/2767/ABHINISHA INFRA/YESB0001014 15063.00
55596 | bahpur Khatauli Village OHT Construction 150 kl 12m work | 2023-03-06 | 7 | 110211.8 | 0 | 110212 | 19838 | 130050 | 1102 | 5510.6 | 11021 | 19838 | 92578 | RIUP22/2635 | 92578 | 0 | 0 | 0 | 92578 | 20-03-2023 NEFT/AXISP00372620114/RIUP22/2635/ABHINISHA INFRA 92578.00
55596 | GST Release Note |  | 7 | 19838 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 19838 | RIUP23/080 | 19838 | 0 | 0 | 0 | 19838 | 09-05-2023 NEFT/AXISP00388778891/RIUP23/080/ABHINISHA INFRA 19838.00
55596 | bahpur Khatauli Village OHT Construction 150 kl 12m work | 2023-07-20 | 7 | 13538 | 0 | 13538 | 2437 | 15975 | 135 | 676.9 | 1354 | 2437 | 11372 | RIUP23/1314 | 11372 |  |  |  | 11372 | 01-08-2023 NEFT/AXISP00411668991/RIUPP23/1314/ABHINISHA INFR 11372.00
55598 | Khanpur Village OHT Construction 75 kl 12m Work | 2023-03-06 | 4 | 78750 | 30892 | 47858 | 8614 | 56472 | 479 | 2392.9 | 4786 | 8614 | 40200 | RIUP22/2621 | 40200 | 0 | 0 | 0 | 40200 | 16-03-2023 NEFT/AXISP00371978438/RIUP22/2621/ABHINISHA INFRA ₹ 40,200.00
55598 | GST Release Note |  | 4 | 8614 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 8614 | RIUP23/082 | 8614 | 0 | 0 | 0 | 8614 | 04-05-2023 NEFT/AXISP00387404080/RIUP23/082/ABHINISHA INFRA 8614.00
55598 | Khanpur Village OHT Construction 75 kl 12m Work | 2023-07-20 | 34 | 6562.5 |  | 6563 | 1181 | 7744 | 66 | 328 | 656 | 1181 | 5513
55599 | Jandheri jatan Village Boundary wall Work | 2023-03-06 | 5 | 255570 | 70124 | 185446 | 33380 | 218826 | 1854 | 18544.6 | 0 | 33380 | 165047 | RIUP22/2622 | 165047 | 0 | 0 | 0 | 165047 | 16-03-2023 NEFT/AXISP00371978436/RIUP22/2622/ABHINISHA INFRA ₹ 1,65,047.00
55599 | Jandheri jatan Village Boundary wall Work | 2023-04-13 | 3 | 85190 | 0 | 85190 | 15334 | 100524 | 852 | 8519 | 0 | 15334 | 75819 | SPUP22/0142 | 75819 | 0 | 0 | 0 | 75819 | 19-04-2023 19-04-2023 NEFT/AXISP00382826208/SPUP23/0142/ABHINISHA INFRA 75819.00
55599 | GST Release Note |  | 5 | 33380 | [8 empty] | 33380 | RIUP22/078 | 33380 | 0 | 0 | 0 | 33380 | 09-05-2023 NEFT/AXISP00388778892/RIUP23/078/ABHINISHA INFRA 33380.00
55599 | GST Release Note | 2023-09-27 | 3 | 15334 | [8 empty] | 15334 | RIUP22/2768 | 15334 |  |  |  | 15334 | 26-10-2023 NEFT/AXISP00437006017/RIUP23/2768/ABHINISHA INFRA/YESB0001014 15334.00
56459 | Mubarikpur Village Pump House work | 2023-04-13 | 4 | 111000 | 0 | 111000 | 19980 | 130980 | 1110 | 11100 | 19980 |  | 98790 | SPUP23/0189 | 98790 |  |  |  | 98790 | 19-04-2023 19-04-2023 NEFT/AXISP00382826209/SPUP23/0189/ABHINISHA INFRA 98790.00
56459 | GST Release Note | 2023-09-27 | 4 | 19980 |  | 19980 |  | 19980 |  |  |  |  | 19980 | RIUP22/2769 | 19980 |  |  |  | 19980 | 26-10-2023 NEFT/AXISP00437006018/RIUP23/2769/ABHINISHA INFRA/YESB0001014 19980.00
57230 | garhi Durganpur Village OHT Construction 125 kl 12m Work | 2023-05-16 | 9 | 104209 | 27991 | 76218 | 13719 | 89937 | 762 | 3810.9 | 7622 | 13719 | 64023 | RIUP23/337 | 64023 | 0 | 0 | 0 | 64023 | 23-05-2023 NEFT/AXISP00392088477/RIUP23/337/ABHINISHA INFRA 64023.00
57230 | garhi Durganpur Village OHT Construction 125 kl 12m Work | 2023-07-20 | 33 | 8290 | 0 | 8290 | 1492 | 9782 | 83 | 414.5 | 829 | 1492 | 6964
57233 | Ladawa Village OHT Work | 2023-05-22 | 10 | 212591.15 | 16591 | 196000 | 35280 | 231280 | 1960 | 9800 | 19600 | 35280 | 164640 | RIUP23/393 | 148500 | 0 | 0 | 0 | 148500 | 25-05-2023 NEFT/AXISP00392601986/RIUP23/393/ABHINISHA INFRA 148500.00
57233 | Ladawa Village OHT Work | 2023-08-10 | 38 | 846158.85 | 62937 | 783222 | 140980 | 924202 | 7832 | 39161.1 | 78322 | 140980 | 657907 | RIUP23/487 | 16140 |  | 0 | 0 | 16140 | 03-06-2023 NEFT/AXISP00395454139/RIUP23/487/ABHINISHA INFRA ₹ 16,140.00
57233 | [13 empty] | RIUP23/616 | 148500 |  | 0 | 0 | 148500 | 12-06-2023 NEFT/AXISP00397819350/RIUP23/616/ABHINISHA INFRA 148500.00
57233 | [13 empty] | RIUP23/1548 | 400000 | 4000 |  |  | 396000 | 17-08-2023 NEFT/AXISP00416302873/RIUP23/1548/ABHINISHA INFRA 396000.00
57233 | [13 empty] | RIUP23/1637 | 113407 |  |  |  | 113407 | 22-08-2023 NEFT/AXISP00417367263/RIUP23/1637/ABHINISHA INFRA 113407.00
57234 | Jafarpur Village OHT Construction 75 kl 12m Work | 2023-06-22 | 23 | 78750 | 17982 | 60768 | 10938 | 71706 | 608 | 3038.4 | 6077 | 10938 | 51045 | RIUP23/394 | 50000 | 500 | 0 | 0 | 49500 | 25-05-2023 NEFT/AXISP00392601987/RIUP23/394/ABHINISHA INFRA 49500.00
57234 | Jafarpur Village OHT Construction 75 kl 12m Work | 2023-07-02 | 27 | 347812.5 | 124088 | 223725 | 40271 | 263996 | 2237 | 11186.25 | 22373 | 40271 | 187929 | RIUP23/922A | 1545 |  |  |  | 1545 | 28-06-2023 NEFT/AXISP00401442272/RIUP23/922A/ABHINISHA INFRA 1545.00
57234 | [13 empty] | RIUP23/1065 | 187929 |  |  |  | 187929 | 14-07-2023 NEFT/AXISP00406995899/RIUP23/1065/ABHINISHA INFRA 187929.00
57368 | Rampurr Village OHT Construction 75 kl 12m Work | 2023-05-13 | 8 | 78750 | 0 | 78750 | 14175 | 92925 | 788 | 3937.5 | 7875 | 14175 | 66150 | RIUP23/286 | 66149 | 0 | 0 | 0 | 66149 | 25-05-2023 NEFT/AXISP00392595796/RIUP23/286/ABHINISHA INFRA 66149.00
57368 | Rampurr Village OHT Construction 75 kl 12m Work | 2023-07-20 | 8 | 6562 | 0 | 6562 | 1181 | 7743 | 66 | 328.1 | 656 | 1181 | 5512 | RIUP23/1288 | 5513 | 0 | 0 | 0 | 5513 | 01-08-2023 NEFT/AXISP00411668986/RIUPP23/1288/ABHINISHA INFR 5513.00
57530 | karwara Village OHT Construction 150 kl 16 m Work | 2023-05-22 | 11 | 117716 | 27991 | 89725 | 16151 | 105876 | 897 | 4486.25 | 8973 | 16151 | 75369 | RIUP23/422 | 75369 | 0 | 0 | 0 | 75369 | 29-05-2023 NEFT/AXISP00393029900/RIUP23/422/ABHINISHA INFRA 75369.00
57603 | Dholari Village OHT Construction 150 kl 12 m Work | 2023-05-27 | 12 | 110211.8 | 20391 | 89821 | 16168 | 105989 | 898 | 4491.05 | 8982 | 16168 | 75450 | RIUP23/468 | 75450 | 0 | 0 | 0 | 75450 | 02-06-2023 NEFT/AXISP00395047094/RIUP23/468/ABHINISHA INFRA 75450.00
57691 | Amirnagar Village OHT Construction 325 kl 12m Work | 2023-05-31 | 13 | 179250 | 20391 | 158859 | 28595 | 187454 | 1589 | 7942.95 | 15886 | 28595 | 133441 | Cash | 100000 | 0 | 0 | 0 | 100000 | In cash at site
57691 | Amirnagar Village OHT Construction 325 kl 12m Work | 2023-07-02 | 29 | 816062 | 67433 | 748629 | 134753 | 883382 | 7486 | 37431.45 | 74863 | 134753 | 628849 | RIUP23/636 | 33441 | 0 | 0 | 0 | 33441 | 13-06-2023 NEFT/AXISP00398105740/RIUP23/636/ABHINISHA INFRA ₹ 33,441.00
57691 | [13 empty] | RIUP23/679 | 200000 | 2000 | 0 | 0 | 198000 | 15-06-2023 NEFT/AXISP00398797335/RIUP23/679/ABHINISHA INFRA 198000.00
57691 | [13 empty] | RIUP23/1064 | 430849 |  |  |  | 430849 | 14-07-2023 NEFT/AXISP00406995898/RIUP23/1064/ABHINISHA INFRA 430849.00
57737 | Atali Village OHT Work | 2023-06-05 | 16 | 121247.45 | 10789 | 110458.45 | 19883 | 130341.45 | 1104.58 | 5522.92 | 11045.845 | 19883 | 92785 | RIUP23/635 | 92784 | 0 | 0 | 0 | 92784 | 13-06-2023 NEFT/AXISP00398105739/RIUP23/635/ABHINISHA INFRA ₹ 92,784.00
58046 | Badh Village OHT Construction 150 KL 12m staging Work | 2023-06-22 | 20 | 110211.8 | 17982 | 92229.8 | 16601 | 108830.8 | 922.3 | 4611.49 | 9222.98 | 16601 | 77473 | RIUP23/894 | 77474 | 0 | 0 | 0 | 77474 | 28-06-2023 NEFT/AXISP00401332291/RIUP23/894/ABHINISHA INFRA 77474.00
58047 | Gyanmazra Village OHT Construction 150KL 16m staging Work | 2023-06-22 | 21 | 117716 | 13487 | 104229 | 18761 | 122990 | 1042.29 | 5211.45 | 10422.9 | 18761 | 87552 | RIUP23/895 | 87553 | 0 | 0 | 0 | 87553 | 28-06-2023 NEFT/AXISP00401332292/RIUP23/895/ABHINISHA INFRA 87553.00
58256 | Bihari Village OHT Construction Work | 2023-07-02 | 28 | 236000 | 13487 | 222513 | 40052 | 262565 | 2225.13 | 11125.65 | 22251.3 | 40052 | 186911 | RIUP23/1110 | 186911 | 0 | 0 | 0 | 186911 | 24-07-2023 NEFT/AXISP00408935242/RIUP23/1110/ABHINISHA INFRA 186911.00
[19 empty] | 148500 | 25-07-2023 NEFT/AXISP00409244026/RIUP23/1215/ABHINISHA INFRA 148500.00
58621 | Chimavu Village OHT Construction 150 kl 12m Work | 2023-07-24 | 37 | 123750 | 16184 | 107566 | 19362 | 126928 | 1076 | 5378.3 | 10757 | 19362 | 90355 | RIUP23/1356 | 90355 | 0 | 0 | 0 | 90355 | 18-08-2023 NEFT/AXISP00416613525/RIUP23/1356/ABHINISHA INFRA 90355.00
58621 | Chimavu Village OHT Construction 150 kl 12m Work | 2023-08-29 | 39 | 247500 | 164767 | 82733 | 14892 | 97625 | 827 | 4136.65 | 0 | 14892 | 77769 | RIUP23/1819 | 77769 | 0 | 0 | 0 | 77769 | 02-09-2023 NEFT/AXISP00421170810/RIUP23/1819/ABHINISHA INFRA/YESB0001014 ₹ 77,769.00
58560 | Buddakheda Village OHT Construction 150 kl 12m Work | 2023-07-24 | 36 | 123750 | 8991 | 114759 | 20657 | 135416 | 1148 | 5737.95 | 11476 | 20657 | 96397 | RIUP23/1337 | 96397 | 0 | 0 | 0 | 96397 | 02-08-2023 NEFT/AXISP00411992213/RIUP23/1337/ABHINISHA INFRA 96397.00
58560 | Buddakheda Village OHT Construction 150 kl 12m Work | 2023-10-10 | 40 | 247500 | 148663 | 98837 | 17791 | 116628 | 988 | 4941.85 | 0 | 17791 | 92907 |  |  | 0 | 0 | 0 | 92907 | 26-10-2023 NEFT/AXISP00437006011/RIUP23/2683/ABHINISHA INFRA/YESB0001014 92907.00

## Sheet2
M/s Abhinisha Infra
Total Hold Without GST | SD + Testing Deposit | 844169.435
Debit | Cement - 97750 + Deisel- 65634 + Steel- 733101 | 996485
Advance |  | 484408
GST Hold |  | 1044414
GST Paid to Contractor |  | 223190
Remaining GST |  | 821224