## Sheet1
Subcontractor: | Anivarti infraengg pvt ltd
State: | Uttar Pradesh |  | Anivarti infraengg pvt ltd
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | TD | Gate Fixing/ P& F etc | DPR Excess hold | GST_SD_Amount | Final_Amount |  | BOQ Amount | Balance Against BOQ | Payment_Amount | TDS_Payment_Amount | Total_Amount | UTR
[9 empty] | 2% | 5% | 10% | [8 empty] | 1%
60097 | [15 empty] | 60097
60097 | Jharkheri village - 225 - 14 work | 2023-11-07 | 2 | 1296000 | 299718 | 996282 | 179331 | 1175613 | 19925.64 | 49814.1 |  |  |  | 179331 | 926542 |  | 3240000 | 934749 | 400000 | 8000 | 392000 | 10-11-2023 NEFT/AXISP00443569636/RIUP23/3267/ANIVARATI INFRAENG/ICIC0000913 392000.00 | -100344
60097 | GST |  | 2 | 179331 | [9 empty] | 0 | 179331 |  |  |  | 534541 |  | 534541 | 29-11-2023 NEFT/AXISP00447355227/RIUP23/3443/ANIVARATI INFRAENG/ICIC0000913 534541.00
60097 | Jharkheri village OHT work | 2024-03-14 | 11 | 486000 | 136697 | 349303 | 62875 | 412178 | 6986.06 | 17465.15 |  |  |  | 62875 | 324852 |  |  |  | 179331 |  | 179331 | 02-02-2024 NEFT/AXISP00467690377/RIUP23/4309/ANIVARATI INFRAENG/ICIC0000913 179331.00
60097 | GST |  | 11 | 62875 | [10 empty] | 62875 |  |  |  | 324852 |  | 324852 | 19-03-2024 NEFT/AXISP00482138720/RIUP23/5179/ANIVARATI INFRAENG/ICIC0000913 324852.00
60097 | Jharkheri village OHT work | 2024-05-16 | 2 | 486000 | 0 | 486000 | 87480 | 573480 | 9720 | 24300 |  |  |  | 87480 | 451980 |  |  |  | 62875 |  | 62875 | 16-05-2024 NEFT/AXISP00500630401/RIUP24/0341/ANIVARATI INFRAENG/ICIC0000913 62875.00
60097 | Jharkheri village OHT work | 2024-06-15 | 3 | 162000 | 14080 | 147920 | 26626 | 174546 | 2958.4 | 7396 |  |  |  | 26626 | 137566 |  |  |  | 451980 |  | 451980 | 03-06-2024 NEFT/AXISP00505249176/RIUP24/0673/ANIVARATI INFRAENG/ICIC0000913 451980.00
60097 | GST | 2024-05-16 | 2 | 87480 | [10 empty] | 87480 |  |  |  | 137566 |  | 137567 | 14-08-2024 NEFT/AXISP00528230426/RIUP24/1017/ANIVARATI INFRAENG/ICIC0000913 137566.00
60097 | GST | 2024-06-15 | 3 | 26626 | [10 empty] | 26626 |  |  |  | 114106 |  | 114106 | 20-09-2024 NEFT/AXISP00542404136/RIUP24/1764/ANIVARATI INFRAENG/ICIC0000913 114106.00
60097 | Jharkheri village OHT work | 2024-12-13 | 10 | 259200 | 0 | 259200 | 46656 | 305856 | 5184 | 12960 |  |  |  | 46656 | 241056 |  |  |  | 100000 |  | 98000 | 30-10-2024 NEFT/AXISP00561389907/RIUP24/2363/ANIVARATI INFRAENG/ICIC0000913 98000.00
60097 | GST | 2024-06-15 | 10 | 46656 | [10 empty] | 46656 | [5 empty] | 143056 | 21-01-2025 NEFT/AXISP00601114145/RIUP24/2774/ANIVARATI INFRAENG/ICIC0000913 143056.00
60097 | [20 empty] | 147000 | 21-01-2025 NEFT/AXISP00601114151/RIUP24/2987/ANIVARATI INFRAENG/ICIC0000913 147000.00
60098 | [15 empty] | 60098
60098 | PANJETH village - 300 -12 work | 2023-11-07 | 3 | 551250 | 165769 | 385481 | 69387 | 454868 | 7709.62 | 19274.05 | 38548.1 |  |  | 69387 | 319949 |  | 3675000 | 3281665 | 200000 | 4000 | 196000 | 10-11-2023 NEFT/AXISP00443569635/RIUP23/3268/ANIVARATI INFRAENG/ICIC0000913 196000.00 | 1
60098 | GST |  | 3 | 69387 | [10 empty] | 69387 |  |  |  | 123948 |  | 123948 | 13-12-2023 NEFT/AXISP00452748655/RIUP23/3597/ANIVARATI INFRAENG/ICIC0000913 123948.00
60098 | [18 empty] | 69387 |  | 69387 | 29-01-2024 NEFT/AXISP00465419057/RIUP23/4310/ANIVARATI INFRAENG/ICIC0000913 69387.00
60100 | [15 empty] | 60100
60100 | Muhmaddpura village - 325 - 16 work | 2021-11-27 | 1 | 628875 | 212700 | 416175 | 74912 | 491087 | 8323.5 | 20808.75 |  |  |  | 74912 | 387043 |  | 4192500 | 3078810 | 200000 |  | 196000 | 10-11-2023 NEFT/AXISP00443569634/RIUP23/3261/ANIVARATI INFRAENG/ICIC0000913 196000.00 | -229347
60100 | GST |  | 1 | 74912 | [9 empty] | 0 | 74912 |  |  |  | 191042 |  | 191042 | 29-11-2023 NEFT/AXISP00447355226/RIUP23/3435/ANIVARATI INFRAENG/ICIC0000913 191042.00
60100 |  | 2024-02-12 | 10 | 1048125 | 679610 | 368515 | 66333 | 434848 | 7370.3 | 18425.75 |  |  |  | 66333 | 342719 |  |  |  | 100000 |  | 98000 | 22-12-2023 NEFT/AXISP00454984275/RIUP23/3921/ANIVARATI INFRAENG/ICIC0000913 98000.00
60100 |  | 2024-03-15 | 15 | 3005 |  | 3005 | 541 | 3546 | 60.1 | 150.25 |  |  |  | 541 | 2795 |  |  |  | 74912 |  | 74912 | 01-02-2024 NEFT/AXISP00467376686/RIUP23/4308/ANIVARATI INFRAENG/ICIC0000913 74912.00
60100 | GST |  | 10 | 66333 | [10 empty] | 66333 |  |  |  | 150000 |  | 147000 | 18-03-2024 NEFT/AXISP00481766501/RIUP23/5164/ANIVARATI INFRAENG/ICIC0000913 147000.00
60100 | GST |  | 15 | 541 | [10 empty] | 541 |  |  |  | 50000 |  | 49000 | 22-03-2024 NEFT/AXISP00483290494/RIUP23/5250/ANIVARATI INFRAENG/ICIC0000913 49000.00
60100 | [18 empty] | 97719 |  | 97719 | 29-04-2024 NEFT/AXISP00494414244/RIUP24/0337/ANIVARATI INFRAENG/ICIC0000913 97719.00
60100 | [18 empty] | 145951 |  | 145951 | 29-04-2024 NEFT/AXISP00494414245/RIUP24/0338/ANIVARATI INFRAENG/ICIC0000913 145951.00
60100 | [18 empty] | 104066 |  | 104066 | 29-04-2024 NEFT/AXISP00494414246/RIUP24/0339/ANIVARATI INFRAENG/ICIC0000913 104066.00
60100
60101 | [15 empty] | 60101
60101 | BHARSI Village BOUNDARY WALL work | 2021-11-27 | 7 | 455000 | 275458 | 179542 | 32318 | 211860 | 3590.84 | 8977.1 |  | 91000 |  | 32318 | 131066 | As per HO |  |  | 100000 |  | 98000 | 12-12-2023 NEFT/AXISP00451877866/RIUP23/3698/ANIVARATI INFRAENG/ICIC0000913 98000.00 | 0
60101 | GST |  | 7 | 32318 | [9 empty] | 0 | 32318 |  |  |  | 33066 |  | 33066 | 01-03-2024 NEFT/AXISP00476344540/RIUP23/4916/ANIVARATI INFRAENG/ICIC0000913 33066.00
60101 | [18 empty] | 32318 |  | 32318 | 01-03-2024 NEFT/AXISP00476344539/RIUP23/4917/ANIVARATI INFRAENG/ICIC0000913 32318.00
60101
60102 | [15 empty] | 60102
60102 | Bhasri village PH work | 2023-11-07 | 6 | 314500 | 0 | 314500 | 56610 | 371110 | 6290 | 15725 |  |  |  | 56610 | 292485 |  |  |  | 292485 | 0 | 292485 | 24-11-2023 NEFT/AXISP00446428093/RIUP23/3286/ANIVARATI INFRAENG/ICIC0000913 292485.00 | 0
60102 | GST |  | 6 | 56610 | [9 empty] | 0 | 56610 |  |  |  | 56610 | 0 | 56610 | 02-02-2024 NEFT/AXISP00467690378/RIUP23/4312/ANIVARATI INFRAENG/ICIC0000913 56610.00
60103 | [15 empty] | 60103
60103 | Issopur Teel Village BW work | 2024-03-22 | 17 | 497122 |  | 497122 | 89482 | 586604 | 9942 | 24856.1 |  | 49712.2 | 3209500.2 | 89482 | -2796889 |  |  |  | 100000 |  | 98000 | 18-12-2023 NEFT/AXISP00453885474/RIUP23/3835/ANIVARATI INFRAENG/ICIC0000913 98000.00 | -6233213
60103 | GST |  | 17 | 89482 | [10 empty] | 89482 |  |  |  | 127713 |  | 127713 | 04-04-2024 NEFT/AXISP00488005304/RIUP23/5328/ANIVARATI INFRAENG/ICIC0000913 127713.00
60103 | Issopur Teel Village BW work | 2025-03-07 | 13 | 87727 | 440 | 87287 | 15712 | 102999 | 1745.74 | 4364.35 |  | 0 | 3209500.2 | 15712 | -3128323 |  |  |  | 89482 |  | 89482 | 17-05-2024 NEFT/AXISP00500883070/RIUP24/0340/ANIVARATI INFRAENG/ICIC0000913 89482.00
60103 | GST |  | 13 | 15712 | [10 empty] | 15712 | [5 empty] | 98000 | 26-09-2024 NEFT/AXISP00544686589/RIUP24/1932/ANIVARATI INFRAENG/ICIC0000913 98000.00
60104 | [15 empty] | 60104
60104 | Issopur Teel Village PUMP HOUSE work | 2023-12-15 | 6 | 185000 | 0 | 185000 | 33300 | 218300 | 3700 | 9250 |  |  |  | 33300 | 172050 |  |  |  | 150000 | 0 | 147000 | 22-12-2023 NEFT/AXISP00454984276/RIUP23/3922/ANIVARATI INFRAENG/ICIC0000913 147000.00 | 19414
60104 | GST |  | 6 | 33300 | [9 empty] | 0 | 33300 |  |  |  | 25050 |  | 25050 | 09-01-2024 NEFT/AXISP00460826664/RIUP23/4059/ANIVARATI INFRAENG/ICIC0000913 25050.00
60104 | Issopur Teel Village PUMP HOUSE work | 2024-07-09 | 4 | 157900 | 50047 | 107853 | 19414 | 127267 | 2157.06 | 5392.65 |  |  |  | 19414 | 100303 |  |  |  | 33300 |  | 33300 | 01-03-2024 NEFT/AXISP00476344538/RIUP23/4918/ANIVARATI INFRAENG/ICIC0000913 33300.00
60104 | GST |  | 4 | 19414 | [10 empty] | 19414 |  |  |  | 100303 |  | 100303 | 17-09-2024 NEFT/AXISP00541245540/RIUP24/1122/ANIVARATI INFRAENG/ICIC0000913 100303.00
60104
60179 | [15 empty] | 60179
60179 | jarkheri village PH work | 2023-11-07 | 4 | 314500 | 0 | 314500 | 56610 | 371110 | 6290 | 15725 |  |  |  | 56610 | 292485 |  |  |  | 292485 |  | 292485 | 02-12-2023 NEFT/AXISP00449103424/RIUP23/3430/ANIVARATI INFRAENG/ICIC0000913 292485.00 | 0
60179 | GST |  | 4 | 56610 | [9 empty] | 0 | 56610 |  |  |  | 56610 |  | 56610 | 01-02-2024 NEFT/AXISP00467376687/RIUP23/4311/ANIVARATI INFRAENG/ICIC0000913 56610.00
61412 | [15 empty] | 61412
61412 | ALIPUR UMERPUR village - 250 -12 work | 2024-03-22 | 18 | 24564.8 | 341250 | -316685.2 | -57003 | -373688.2 | -6333.704 | -15834.26 |  |  |  | -57003 | -294517 |  | 3412500 | 2263138 | 150000 |  | 147000 | 12-01-2024 NEFT/AXISP00461943526/RIUP23/4242/ANIVARATI INFRAENG/ICIC0000913 147000.00 | -1487882
61412 | gst |  | 18 | -57003 | [10 empty] | -57003 |  |  |  | 500000 | 10000 | 490000 | 22-03-2024 NEFT/AXISP00483288611/RIUP23/5252/ANIVARATI INFRAENG/ICIC0000913 490000.00
61412 | [18 empty] | 315087 |  | 315087 | 10-05-2024 NEFT/AXISP00499057073/RIUP24/0343/ANIVARATI INFRAENG/ICIC0000913 315087.00
61412 | [18 empty] | 184275 |  | 184275 | 10-05-2024 NEFT/AXISP00499057074/RIUP24/0342/ANIVARATI INFRAENG/ICIC0000913 184275.00
61412
61412
62334 | [15 empty] | 62334
62334 | ALIPUR village - 375 -14 work | 2024-04-15 | 1 | 1134375 |  | 1134375 | 204188 | 1338563 | 22687.5 | 56718.75 |  |  |  | 204188 | 1054969 |  | 4537500 | 1054500 | 150000 |  | 147000 | 07-03-2024 NEFT/AXISP00478571757/RIUP23/5054/ANIVARATI INFRAENG/ICIC0000913 147000.00 | -37592
62334 | Gst |  | 1 | 204188 | [10 empty] | 204188 |  |  |  | 907468 |  | 907968 | 24-04-2024 NEFT/AXISP00493457029/RIUP24/0263/ANIVARATI INFRAENG/ICIC0000913 907968.00
62334 | ALIPUR village - 375 -14 work | 2024-08-06 | 5 | 226875 |  | 226875 | 40838 | 267713 | 4537.5 | 11343.75 |  |  |  | 40838 | 210994 |  |  |  | 204188 |  | 204188 | 27-05-2024 NEFT/AXISP00502944904/RIUP24/0612/ANIVARATI INFRAENG/ICIC0000913 204188.00
62334 | ALIPUR village - 375 -14 work | 2024-09-24 | 7 | 453750 |  | 453750 | 81675 | 535425 | 9075 | 22687.5 |  |  |  | 81675 | 421988 |  |  |  | 210993 |  | 210993 | 19-08-2024 NEFT/AXISP00529670924/RIUP24/1472/ANIVARATI INFRAENG/ICIC0000913 210993.00
62334 | ALIPUR village - 375 -14 work | 2024-10-16 | 8 | 680625 |  | 680625 | 122513 | 803138 | 13612.5 | 34031.25 |  |  |  | 122513 | 632981 |  |  |  | 100000 |  | 98000 | 18-09-2024 NEFT/AXISP00541733389/RIUP24/1833/ANIVARATI INFRAENG/ICIC0000913 98000.00
62334 | GST |  | 5, 7 | 122513 | [10 empty] | 122513 |  |  |  | 400000 |  | 392000 | 21-10-2024 NEFT/AXISP00556268920/RIUP24/2260/ANIVARATI INFRAENG/ICIC0000913 392000.00
62334 | GST |  | 8 | 122513 | [10 empty] | 122513 |  |  |  | 200000 |  | 196000 | 30-10-2024 NEFT/AXISP00561389906/RIUP24/2362/ANIVARATI INFRAENG/ICIC0000913 196000.00
62334 | ALIPUR village - 375 -14 work | 2024-11-29 | 9 | 226875 |  | 226875 | 40838 | 267713 | 4537.5 | 11343.75 |  |  |  | 40838 | 210994 |  |  |  | 122513 |  | 122513 | 20-12-2024 NEFT/AXISP00587058612/RIUP24/2598/ANIVARATI INFRAENG/ICIC0000913 122513.00
62334 | GST |  | 9 | 40838 | [10 empty] | 40838 |  |  |  | 200000 |  | 196000 | 20-12-2024 NEFT/AXISP00587058614/RIUP24/2757/ANIVARATI INFRAENG/ICIC0000913 196000.00
62334 | ALIPUR village - 375 -14 work | 2025-03-07 | 11 | 363000 |  | 363000 | 65340 | 428340 | 7260 | 18150 |  |  |  | 65340 | 337590 |  |  |  | 40838 |  | 40838 | 07-02-2025 NEFT/AXISP00612564981/RIUP24/2822/ANIVARATI INFRAENG/ICIC0000913 40838.00
62334 | GST |  | 11 | 65340 | [10 empty] | 65340 |  |  |  | 200000 |  | 200000 | 15-02-2025 NEFT/AXISP00616936486/RIUP24/3181/ANIVARATI INFRAENG/ICIC0000913 200000.00
62334 | [18 empty] | 150000 |  | 150000 | 13-03-2025 NEFT/AXISP00633031179/RIUP24/3417/ANIVARATI INFRAENG/ICIC0000913 150000.00
62334 | [18 empty] | 250000 |  | 250000 | 09-04-2025 NEFT/AXISP00648889496/RIUP25/0063/ANIVARATI INFRAENG/ICIC0000913 250000.00
62334 | [18 empty] | 200000 |  | 200000 | 19-04-2025 NEFT/AXISP00653358545/RIUP25/0135/ANIVARATI INFRAENG/ICIC0000913 200000.00
62334 | [18 empty] | 147000 |  | 147000 | 24-04-2025 NEFT/AXISP00655699069/RIUP25/0146/ANIVARATI INFRAENG/ICIC0000913 147000.00
62335 | [15 empty] | 62335
62335 | MANNAMAZRA village - 300 -16 work | 2024-03-18 | 16 | 990000 |  | 990000 | 178200 | 1168200 | 19800 | 49500 |  |  |  | 178200 | 920700 |  | 3960000 | 2650100 | 150000 |  | 147000 | 07-03-2024 NEFT/AXISP00478571758/RIUP23/5055/ANIVARATI INFRAENG/ICIC0000913 147000.00 | 23780
62335 | GST |  | 16 |  |  | 178200 | [8 empty] | 178200 |  |  |  | 400000 |  | 392000 | 22-03-2024 NEFT/AXISP00483288610/RIUP23/5253/ANIVARATI INFRAENG/ICIC0000913 392000.00
62335 | MANNAMAZRA village - 300 -16 work | 2025-03-07 | 12 | 198000 |  | 198000 | 35640 | 233640 | 3960 | 9900 |  |  |  | 35640 | 184140 |  |  |  | 381700 |  | 381700 | 06-04-2024 NEFT/AXISP00489186684/RIUP23/5310/ANIVARATI INFRAENG/ICIC0000913 381700.00
62335 | GST |  | 12 |  |  | 35640 | [8 empty] | 35640 |  |  |  | 178200 |  | 178200 | 16-05-2024 NEFT/AXISP00500630404/RIUP24/0445/ANIVARATI INFRAENG/ICIC0000913 178200.00
62335 | [18 empty] | 100000 |  | 98000 | 18-09-2024 NEFT/AXISP00541733390/RIUP24/1834/ANIVARATI INFRAENG/ICIC0000913 98000.00
62335 | [18 empty] | 100000 |  | 98000 | 30-10-2024 NEFT/AXISP00561390211/RIUP24/2354/ANIVARATI INFRAENG/ICIC0000913 98000.00
62336 | [15 empty] | 62336
62336 | Erti-Kairana village - 175 -12 work | [21 empty] | 0
62336 | Closed
62336
[9 empty] | 181089.576 | 452725.04 | 38548.2 | 140712.2 | 6419000.4 | 1629816 | 3507334 |  | Total Paid Amount Rs. - |  |  |  | 11552517
[17 empty] | Balance Payable Amount Rs. - |  |  |  | -8045183 |  | -8045183
Anivarati Infraengineers
2025-05-10
[9 empty] | Total Hold ( SD+OC+HT ) |  | 631985.44
[9 empty] | Advance / Surplus |  | -8045183
[9 empty] | DPR Excess Hold |  | 6419000.4
Debit
[9 empty] | GST Remaining |  | 100980
AMOUNT
[6 empty] | ITEM | EXCESS | RATE | 1010
[6 empty] | Dism BOE | 20.2 | 50 | 8875
[6 empty] | Dism C C | 35.5 | 250 | 9885
Hold Amt