## Sheet1
Subcontractor: | BT Contractor
State: | Uttar Pradesh
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | DPR excess hold | Final_Amount | Total_Amount | UTR | Villages Wise Advance
[7 empty] | 18% |  | 1% | 5% | 10% | 10% | 18%
66037 | PATNI PRATAPUR village RR work | 2024-10-22 | 5 | 484237.88 | 186935 | 297302.88 | 53514.5184 | 350817.3984 | 59460.576 | 14865.144 | 29730.288 | 29730.288 | 53514.5184 |  | 163516.584 | 99000 | 01-10-2024 NEFT/AXISP00547355132/RIUP24/2012/B T CONTRACTOR/IDIB000K650 99000.00 | 76297.9624
66037 | GST |  | 5 | 53514.5184 | [10 empty] | 53514.5184 | 74250 | 04-10-2024 NEFT/AXISP00548962989/RIUP24/2124/B T CONTRACTOR/IDIB000K650 74250.00
66037 | PATNI PRATAPUR village RR work | 2024-11-11 | 6 | 318882 | 0 | 318882 | 57398.76 | 376280.76 | 63776.4 | 15944.1 | 31888.2 | 31888.2 | 57398.76 |  | 175385.1 | 46753 | 04-12-2024 NEFT/AXISP00579764048/RIUP24/2587/B T CONTRACTOR/IDIB000K650 46753.00
66037 | GST |  | 6 | 57398.76 | [10 empty] | 57398.76 | 100000 | 04-12-2024 NEFT/AXISP00579764049/RIUP24/2588/B T CONTRACTOR/IDIB000K650 100000.00
66037 | [15 empty] | 53514 | 04-12-2024 NEFT/AXISP00579764050/RIUP24/2589/B T CONTRACTOR/IDIB000K650 53514.00
66037 | [15 empty] | 57399 | 13-03-2025 NEFT/AXISP00633039287/RIUP24/3378/B T CONTRACTOR/IDIB000K650 57399.00
66038 | SINGRA village RR work | [16 empty] | 0
66038
66038
[5 empty] | 186935 | 616184.88 | 110913.2784 | 727098.1584 | 123236.976 | 30809.244 | 61618.488 | 61618.488 | 110913.2784 | 0 | 449814.9624 | 430916 |  | 76297.9624
18898.9624
B.T. Contractor
2024-12-05
[11 empty] | Total Hold |  | 154046.22
[11 empty] | DPR Excess Hold |  | 0
[11 empty] | Total Debit |  | Nil
[11 empty] | Advance/ Surplus |  | 18898.9624
GST Remaining