## Sheet1
Subcontractor: | M/s DNA Enterprises
State: | Uttar Pradesh | [5 empty] | Pipeline laying work
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | Painting and Finishing | Hold Amount for excess Qty. against DPR/ Advance | GST_SD_Amount | Final_Amount | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | Total_Amount | UTR | Advance Village Wise
[9 empty] | 1% | 5% | 10% | 10% | 0.05/10% | [5 empty] | 1%
56258 | Khanpur village Boundary Wall work | 2023-05-09 | 2 | 189000 | 53414 | 135586 | 24405 | 159991 | 1356 | 6779 | 0 | 0 | 6779.3 | 0 | 24405 | 120671.7 | SPUP23/0215 | 100000 | 1000 | 99000 | 20-04-2023 20-04-2023 NEFT/AXISP00383281386/SPUP23/0215/MS DNA ENTERPRI 99000.00
56258 | GST Release Note | 2023-05-21 | 2 | 24405 | [11 empty] | 24405 | RIUP23/178 | 21672 |  | 21672 | 10-05-2023 NEFT/AXISP00388990936/RIUP23/178/MS DNA ENTERPRIS 21672.00
56258 | Khanpur village Boundary Wall work | 2023-06-20 | 5 | 232575 | 4578 | 227997 | 41039 | 269036 | 2280 | 11400 | 0 | 0 | 22799.7 | 23625 | 41039 | 167892.3 | RIUP23/362 | 24405 |  | 24405 | 24-05-2023 NEFT/AXISP00392230455/RIUP23/362/MS DNA ENTERPRIS 24405.00
56258 | GST Release Note |  | 5 | 41039 | [11 empty] | 41039 | RIUP23/510 | 50000 | 500 | 49500 | 05-06-2023 NEFT/AXISP00395669164/RIUP23/510/MS DNA ENTERPRIS 49500.00
56258 | [16 empty] | RIUP23/752 | 118392 |  | 118392 | 21-06-2023 NEFT/AXISP00399842965/RIUP23/752/MS DNA ENTERPRIS 118392.00
56258 | [16 empty] | RIUP23/4360 | 41039 |  | 41039 | 02-02-2024 NEFT/AXISP00467749359/RIUP23/4360/MS DNA ENTERPRISES/SBIN0000017 41039.00
0
55445 | Paotikalan Village Pipe laying work | 2023-03-16 | 6 | 313203 | 0 | 313203 | 56377 | 369580 | 3132.03 | 15660.15 | 31320.3 | 31320.3 |  |  | 56376.54 | 231770.68 | RIUP23/2687 | 150000 | 1500 | 148500 | 21-03-2023 NEFT/AXISP00373201704/RIUP22/2687/MS DNA ENTERPRI 148500.00
55445 | GST release note | 2023-05-05 | 6 | 56376.54 | [11 empty] | 56376.54 | RIUP23/2743 | 50000 | 500 | 49500 | 27-03-2023 NEFT/AXISP00374579146/RIUP22/2743/MS DNA ENTERPRI 49500.00
55445 | [16 empty] | RIUP23/116 | 33771 |  | 33771 | 06-05-2023 NEFT/AXISP00388047281/RIUP23/116/MS DNA ENTERPRIS 33771.00
55445 | [16 empty] | RIUP23/117 | 56377 |  | 56377 | 06-05-2023 NEFT/AXISP00388047282/RIUP23/117/MS DNA ENTERPRIS 56377.00
55445
-0.78
55444 | Unchgaon Village - Khairan Block Pipe laying work | 2023-03-16 | 5 | 613025 | 2 | 613023 | 110344 | 723367 | 6130.23 | 30651.15 | 61302.3 | 61302.3 | 29407.5 |  | 110344 | 424229.52 | RIUP22/2473 | 200000 | 2000 | 198000 | 06-03-2023 NEFT/AXISP00369001734/RIUP22/2473/MS DNA ENTERPRI 198000.00
55444 | Unchgaon Village - Khairan Block Pipe laying work | 2023-04-15 | 1 | 365351 | 18014 | 347337 | 62521 | 409858 | 3473.37 | 17366.85 | 34733.7 | 34733.7 | 0 |  | 62521 | 257029.38 | RIUP22/2686 | 100000 | 1000 | 99000 | 21-03-2023 NEFT/AXISP00373201703/RIUP22/2686/MS DNA ENTERPRI 99000.00
55444 | GST release note | 2023-04-03 | 5 | 110344.14 | [11 empty] | 110344.14 | RIUP22/2735 | 100000 | 1000 | 99000 | 27-03-2023 NEFT/AXISP00374603534/RIUP22/2735/MS DNA ENTERPRI 99000.00
55444 | GST release note | 2023-05-21 | 1 | 62520 | [11 empty] | 62520 | SPUP23/0070 | 50000 | 500 | 49500 | 11-04-2023 NEFT/AXISP00380905285/SPUP23/0070/DNA ENTERPRI 49500.00
55444 | Unchgaon Village - Khairan Block Pipe laying work | 2023-07-27 | 6 | 471276 | 0 | 471276 | 84830 | 556106 | 4712.76 | 23563.8 | 47127.6 | 47127.6 | 0 | 15798 | 84830 | 332946.24 | SPUP23/0241 | 200000 | 2000 | 198000 | 24-04-2023 24-04-2023 NEFT/AXISP00383950326/SPUP23/0241/MS DNA ENTERPRI 198000.00
55444 | GST release note | 2023-07-28 | 6 | 84830 | [11 empty] | 84830 | RIUP23/163 | 110344 | 0 | 110344 | 10-05-2023 NEFT/AXISP00388990942/RIUP23/163/MS DNA ENTERPRIS 110344.00
55444 | Unchgaon Village - Khairan Block Pipe laying work | 2023-11-06 | 10 | 368509 | 36028 | 332481 | 59847 | 392328 | 3324.81 | 16624.05 | 33248.1 | 33248.1 | 0 | 8098 | 59847 | 237937.94 | RIUP23/361 | 62521 | 0 | 62521 | 24-05-2023 NEFT/AXISP00392230454/RIUP23/361/MS DNA ENTERPRIS 62521.00
55444 | GST release note |  | 10 | 59847 | [11 empty] | 59847 | RIUP23/1122 | 100000 | 1000 | 99000 | 17-07-2023 NEFT/AXISP00407544695/RIUP23/1122/MS DNA ENTERPRI 99000.00
55444 | Unchgaon Village - Khairan Block Pipe laying work | 2024-07-18 | 3 | 739762 | 4403 | 735359 | 132365 | 867724 | 7353.59 | 36767.95 | 73535.9 | 73535.9 | 0 | 57580 | 132365 | 486585.66 | RIUP23/1354 | 138741 |  | 138741 | 02-08-2023 NEFT/AXISP00412149932/RIUP23/1354/MS DNA ENTERPRI 138741.00
55444 | [16 empty] | RIUP23/1523 | 100000 | 1000 | 99000 | 14-08-2023 NEFT/AXISP00415763060/RIUP23/1523/MS DNA ENTERPRI ₹ 99,000.00
55444 | [16 empty] | RIUP23/1962 | 100000 | 1000 | 99000 | 12-09-2023 NEFT/AXISP00423960528/RIUP23/1962/MS DNA ENTERPRISES/SBIN0000017 99000.00
55444 | [16 empty] | RIUP23/2038 | 84830 | 0 | 84830 | 15-09-2023 NEFT/AXISP00425251742/RIUP23/2038/MS DNA ENTERPRISES/SBIN0000017 ₹ 84,830.00
55444 | [16 empty] | RIUP23/2855 | 100000 | 1000 | 99000 | 25-10-2023 NEFT/AXISP00436731127/RIUP23/2855/MS DNA ENTERPRISES/SBIN0000017 99000.00
55444 | [16 empty] | RIUP23/3173 | 100000 | 1000 | 99000 | 09-11-2023 NEFT/AXISP00442541909/RIUP23/3173/MS DNA ENTERPRISES/SBIN0000017 99000.00
55444 | [16 empty] | RIUP23/4268 | 200000 | 2000 | 198000 | 15-01-2024 NEFT/AXISP00462583085/RIUP23/4268/MS DNA ENTERPRISES/SBIN0000017 198000.00
55444 | [16 empty] | RIUP23/5028 | 200000 | 2000 | 198000 | 06-03-2024 NEFT/AXISP00477822859/RIUP23/5028/MS DNA ENTERPRISES/SBIN0000017 ₹ 1,98,000.00
55444 | [19 empty] | 158400 | 17-05-2024 NEFT/AXISP00500883097/RIUP24/0551/MS DNA ENTERPRISES/SBIN0000017 158400.00
55444
55444
-33066.12
55157 | Jandheri Village - Boundary wall work | 2023-05-13 | 3 | 372645 | 57565 | 315080 | 56714 | 371794 | 3151 | 15754 |  |  |  | 20000 | 56714 | 276175 | RIUP23/0091 | 150000 | 1500 | 148500 | 11-04-2023 NEFT/AXISP00380947708/SPUP23/0091/MS DNA ENTERPRI 148500.00
55157 | GST Release Note | 2023-06-26 | 3 | 56714 | [11 empty] | 56714 | RIUP23/620 | 127675 | 0 | 127675 | 13-06-2023 NEFT/AXISP00398036688/RIUP23/620/MS DNA ENTERPRIS 127675.00
55157 | [16 empty] | RIUP23/909 | 56714 | 0 | 56714 | 28-06-2023 NEFT/AXISP00401332297/RIUP23/909/MS DNA ENTERPRIS 56714.00
55157
0
54365 | Manakpur-Yunishpur Village Pipeline laying work | 2023-01-03 | 3 | 835569 | 0 | 835569 | 150402 | 985971 | 8356 | 41778 | 83557 | 83557 |  | 201990 | 150402 | 416331 | RIUP23/1946 | 300000 | 3000 | 297000 | 23-01-2023 NEFT/AXISP00356620225/RIUP22/1946/MS DNA ENTERPRI ₹ 2,97,000.00
54365 | Manakpur-Yunishpur Village Pipeline laying work | 2023-05-18 | 4 | 550402 | 98924 | 451478 | 81266 | 532744 | 4515 | 22574 | 45148 | 45148 |  |  | 81266 | 334093 | RIUP23/2154 | 119331 |  | 119331 | 13-02-2023 NEFT/AXISP00362757395/RIUP22/2154/MS DNA ENTERPRI ₹ 1,19,331.00
54365 | GST Release Note | 2023-05-18 | 4 | 81266 | [11 empty] | 81266 | RIUP23/2210 | 80000 | 800 | 79200 | 17-02-2023 NEFT/AXISP00364121241/RIUP22/2210/MS DNA ENTERPRI 79200.00
54365 | [16 empty] | RIUP23/2309 | 150402 |  | 150402 | 27-02-2023 NEFT/AXISP00365798941/RIUP22/2309/MS DNA ENTERPRI 150402.00
54365 | GST Release Note | 2023-01-03 | 3 | 150402 | [11 empty] | 150402 | RIUP23/2496 | 50000 | 500 | 49500 | 08-03-2023 NEFT/AXISP00369766183/RIUP22/2496/MS DNA ENTERPRI 49500.00
54365 | [16 empty] | RIUP23/0074 | 30000 | 300 | 29700 | 11-04-2023 NEFT/AXISP00380905281/SPUP23/0074/DNA ENTERPRI 29700.00
54365 | Manakpur-Yunishpur Village Pipeline laying work | 2023-08-03 | 7 | 225406 | 0 | 225406 | 40573.08 | 265979.08 | 2254.06 | 11270.3 | 22540.6 | 22540.6 |  | 80083 | 40573.08 | 86717.44 | RIUP23/297 | 150000 | 1500 | 148500 | 17-05-2023 NEFT/AXISP00390799662/RIUP23/297/MS DNA ENTERPRIS ₹ 1,48,500.00
54365 | GST Release Note | 2023-08-03 | 7 | 40573.08 | [11 empty] | 40573.08 | RIUP23/319 | 27193 |  | 27193 | 25-05-2023 NEFT/AXISP00392595797/RIUP23/319/MS DNA ENTERPRIS 27193.00
54365 | Manakpur-Yunishpur Village Pipeline laying work | 2023-04-18 | 1 | 167371.7 |  | 167371.7 | 30126.906 | 197498.606 | 1673.717 | 8368.585 | 16737.17 | 16737.17 |  | 41117 | 30126.906 | 82738.058 | RIUP23/443 | 100000 | 1000 | 99000 | 30-05-2023 NEFT/AXISP00393348673/RIUP23/443/MS DNA ENTERPRIS 99000.00
54365 | [16 empty] | RIUP23/900 | 81266 |  | 81266 | 28-06-2023 NEFT/AXISP00401442268/RIUP23/900/MS DNA ENTERPRIS 81266.00
54365 | [16 empty] | RIUP23/1516 | 150000 | 1500 | 148500 | 14-08-2023 NEFT/AXISP00415763056/RIUP23/1516/MS DNA ENTERPRI ₹ 1,48,500.00
54365 | [16 empty] | RIUP23/2248 |  |  | 40573 | 30-09-2023 NEFT/AXISP00428978249/RIUP23/2248/MS DNA ENTERPRISES/SBIN0000017 40573.00
54365 | [16 empty] | RIUP23/4729 | 150000 | 1500 | 148500 | 16-02-2024 NEFT/AXISP00472105178/RIUP23/4729/MS DNA ENTERPRISES/SBIN0000017 148500.00
54365
54365
-226544.422
59028 | Jhanjeri Village Pipeline Road Restoration work | 2023-09-15 | 8 | 469458 | 38150 | 431308 | 77635.44 | 508943.44 | 4313.08 | 21565.4 | 0 | 0 |  |  | 77635.44 | 405429.52 | RIUP23/1771 | 200000 | 2000 | 198000 | 29-08-2023 NEFT/AXISP00418978120/RIUP23/1771/MS DNA ENTERPRISES/SBIN0000017 198000.00
59028 | GST Release Note |  | 8 | 77635.44 | [11 empty] | 77635.44 | RIUP23/2105 | 207427 |  | 207427 | 18-09-2023 NEFT/AXISP00425751852/RIUP23/2105/MS DNA ENTERPRISES/SBIN0000017 207427.00
59028 | Jhanjeri Village Pipeline Road Restoration work | 2024-01-12 | 12 | 68044 | 0 | 68044 | 12247.92 | 80291.92 | 680.44 | 3402.2 | 6804.4 | 6804.4 |  |  | 12247.92 | 50352.56 | RIUP23/3297 | 77635 |  | 77635 | 18-11-2023 NEFT/AXISP00445057523/RIUP23/3297/MS DNA ENTERPRISES/SBIN0000017 77635.00
59028 | Jhanjeri Village Pipeline Road Restoration work | 2024-04-18 | 2 | 63277 |  | 63277 | 11389.86 | 74666.86 | 632.77 | 3163.85 | 6327.7 | 6327.7 |  |  | 11389.86 | 46824.98 |  |  |  | 50354 | 06-03-2024 NEFT/AXISP00477669912/RIUP23/4342/MS DNA ENTERPRISES/SBIN0000017 50354.00
59028 |  |  | 12 | 12247.92 | [11 empty] | 12247.92
59028
59028
1.52
59463 | Kajipur Thirwa Village Pipeline Road Restoration work | 2023-10-30 | 9 | 181541 | 40057 | 141484 | 25467.12 | 166951.12 | 1414.84 | 7074.2 | 14148.4 | 14148.4 |  |  | 25467.12 | 104698.16 | RIUP23/2835 | 100000 | 1000 | 99000 | 23-10-2023 NEFT/AXISP00436552881/RIUP23/2835/MS DNA ENTERPRISES/SBIN0000017 99000.00
59463 | GST Release Note |  | 9 | 25467.12 | [11 empty] | 25467.12 | RIUP23/3174 | 99000 |  | 99000 | 09-11-2023 NEFT/AXISP00442541914/RIUP23/3174/MS DNA ENTERPRISES/SBIN0000017 99000.00
59463 | [16 empty] | RIUP23/3175 | 25467 |  | 25467 | 18-11-2023 NEFT/AXISP00445057524/RIUP23/3298/MS DNA ENTERPRISES/SBIN0000017 25467.00
59463
-93301.72
[10 empty] | 293763.485 | 476531.17 | 476531.17 | 58986.5 | 448291 | 1057549.866 | 4946090.378 | Total Paid Amount Rs.- |  |  | 5239929
[17 empty] | Balance Payable Amount Rs.- |  |  | -293838.622
M/s DNA Enterprises
2024-08-03
[8 empty] | Total Hold |  | 1305812.325
[8 empty] | DPR Excess |  | 448291
[8 empty] | Advance / Surplus |  | -293838.622
[8 empty] | Debit |  | Nil
[8 empty] | GST Remaining |  | 173882.626