## Sheet1
Subcontractor: | Jai Kumar
State: | Uttar Pradesh
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commissio | Hydro_Testing | GST_SD_Amount | Hold Amount | Final_Amount | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | SD (5%) | Advance paid | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% |  | 10% | 18% |  |  |  |  | 1% | 5%
52435 | Dholari Village Pump House work | 2022-11-03 | 2 | 381000 | 44151 | 336849 | 60633 | 397482 | 3368.49 | 16842.45 |  |  | 60633 |  | 316638 | RIUP22/745 | 100000 | 1000 |  |  | 99000 | 14-09-2022 NEFT/AXISP00320017795/RIUP22/745/JAI KUMAR 99000.00
52435 | GST release note | 2023-12-20 | 2 | 60633 |  | 60633 | 0 | 60633 | 0 | 0 |  |  | 0 |  | 60633 | RIUP22/1214 | 217639 | 0 | 0 | 0 | 217638 | 14-11-2022 NEFT/AXISP00337247384/RIUP22/1214/JAI KUMAR 217639.00
52435 | [5 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | RIUP22/1571 | 60633 | 0 | 0 |  | 60633 | 20-12-2022 NEFT/AXISP00347623936/RIUP22/1571/JAI KUMAR 60633.00
[6 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | 0
52201 | Dholari Village Pipe laying work | 2022-09-05 | 1 | 468994 | 0 | 468994 | 84419 | 553413 | 4690 | 23450 | 23450 | 46899 | 84419 | 0 | 370505 | RIUP22/828 | 370505 |  |  |  | 370505 | 30-09-2022 NEFT/AXISP00323985688/RIUP22/828/JAI KUMAR 370505.00
52201 | GST Release Note | 2022-10-19 | 1 | 84419 | 0 | 84419 |  | 84419 | 0 | 0 | 0 | 0 | 0 | 0 | 84419 | RIUP22/1117 | 84419 |  |  |  | 84419 | 07-11-2022 NEFT/AXISP00335257357/RIUP22/1117/JAI KUMAR 84419.00
52201 | Dholari Village Pipe laying work | 2022-12-02 | 3 | 375678 | 17982 | 357696 | 64385 | 422081 | 3577 | 17885 | 35770 | 35770 | 64385 | 208286 | 56408 | RIUP22/1782 | 99000 |  |  |  | 99000 | 04-01-2023 NEFT/AXISP00351791578/RIUP22/1782/JAI KUMAR 99000.00
52201 | GST Release Note | 2023-01-24 | 3 | 64385 |  | 64385 | 0 | 64385 | 0 | 0 | 0 | 0 | 0 | 0 | 64385 | RIUP22/1898 | 49500 |  |  |  | 49500 | 18-01-2023 NEFT/AXISP00355710811/RIUP22/1898/JAI KUMAR ₹ 49,500.00
52201 | Dholari Village Pipe laying work | 2023-06-28 | 5 | 285168.7 | 103397 | 181772 | 32719 | 214491 | 1818 | 9089 | 9089 | 0 | 32719 | 0 | 161776 | RIUP22/1958 | 99000 |  |  |  | 99000 | 23-01-2023 NEFT/AXISP00356693750/RIUP22/1958/JAI KUMAR ₹ 99,000.00
52201 | [15 empty] | RIUP23/1211 | 35069 |  |  |  | 35069 | 25-07-2023 NEFT/AXISP00409244024/RIUP23/1211/JAI KUMAR 35069.00