## Sheet1
Subcontractor: | S S ENTERPRISES _ SAJID KHAN
State: | Uttar Pradesh
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Painting and finishing hold | Hold amount | Final_Amount |  | Total_Amount | UTR | Advance Village Wise
[9 empty] | 1% | 5% | 10% | 10% |  | 0.1
60116 | [16 empty] | 60116
60116 | Miyan Kasba Village Pipe Line Restoration Work |  | 21 | 268208 |  | 268208 | 48277.44 | 316485.44 | 2682.08 | 13410.4 | 26820.8 | 26820.8 | 48277.44 |  |  | 198473.92 |  | 148500 | 20-11-2023 NEFT/AXISP00445254608/RIUP23/3351/S S ENTERPRISES/BDBL0001338 ₹ 1,48,500.00
60116 | Miyan Kasba Village Pipe Line Restoration Work | 2024-03-27 | 24 | 182018 |  | 182018 | 32763.24 | 214781.24 | 1820.18 | 9100.9 | 18201.8 | 18201.8 | 32763.24 |  | 18123 | 116570.32 |  | 49974 | 01-12-2023 NEFT/AXISP00448952428/RIUP23/3394/S S ENTERPRISES/BDBL0001338 ₹ 49,974.00
60116 | Miyan Kasba Village Pipe Line Restoration Work |  | 11 | 302724 |  | 302724 | 54490.32 | 357214.32 | 3027.24 | 15136.2 | 30272.4 | 30272.4 | 54490.32 |  | 54687 | 169328.76 |  | 116569 | 22-12-2023 NEFT/AXISP00454984301/RIUP23/3703/S S ENTERPRISES/BDBL0001338 116569.00
60116 | GST |  | 21 & 24 | 81040.68 | [11 empty] | 81040.68 |  | 81040 | 23-02-2024 NEFT/AXISP00473671430/RIUP23/4496/S S ENTERPRISES/BDBL0001338 ₹ 81,040.00
60116 | GST |  | 11 | 54490.32 | [11 empty] | 54490.32 |  | 169329 | 26-09-2024 NEFT/AXISP00544686579/RIUP24/1379/S S ENTERPRISES/BDBL0001338 169329.00
60116 | [19 empty] | 54492
[8 empty] | Total Payable Amount Rs. - |  | 37647.5 | 75295 | 75295 | 135531 | 0 | 72810 | 619904 |  | 565412 | Total Paid | 54492
[18 empty] | 54492 | Balance Payable
M/s S S Enterprises
2024-11-29
[6 empty] | Total Hold |  | 188237.5
[6 empty] | Total Debit |  | 80115
[6 empty] | Advance/ Surplus |  | 54492
[6 empty] | GST Remaining |  | 0