## Sheet1
Subcontractor: | Shree Shyam Enterprises
State: | Uttar Pradesh | [5 empty] | Pipeline Laying work
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold Amount For Quantity excess against DPR | Final_Amount | Total_Amount | UTR | Advance Village Wise
[9 empty] | 1% | 5% | 10% | 10%
61882 | Yousufpur Village Pipeline laying work | 2024-03-21 | 2 | 375276 | 52500 | 322776 | 58100 | 380876 | 3227.76 | 16139 | 32278 | 32278 | 58100 | 0 | 238853 | 148500 | 09-02-2024 NEFT/AXISP00469899338/RIUP23/4633/SHRI SHYAM ENTERPR/BARB0DHINDH 148500.00
61882 | Yousufpur Village Pipeline laying work | 2024-06-30 | 1 | 61058 |  | 61058 | 10990 | 72048 | 610.58 | 3053 | 6106 | 6106 | 10990 | 0 | 45182 | 90353 | 26-04-2024 NEFT/AXISP00493991576/RIUP23/5331/SHRI SHYAM ENTERPR/BARB0DHINDH 90353.00
61882 | GST |  | 2 | 58100 | [10 empty] | 58100
61882 | GST |  | 1 | 10990 | [10 empty] | 10990
61882 | [17 empty] | 114272
62111 | BALANCE REINSTATEMENT WORK AT RATANPURI village | 2024-03-20 | 1 | 37290 |  | 37290 | 6712 | 44002 | 372.9 | 1865 | 3729 | 3729 | 6712 | 0 | 27594 | 27594 | 24-04-2024 NEFT/AXISP00493457024/RIUP24/0157/SHRI SHYAM ENTERPR/BARB0DHINDH 27594.00
62111
62111 | [17 empty] | 0
62111
[10 empty] | 21057 | 42113 | 42113 | 75802 | 0 | 380719 | 266447 |  | 114272
114272
Shree Shyam Enterprises
2025-03-10
[10 empty] | Total Hold |  | 0
[10 empty] | Advance / Surplus |  | 114272
[10 empty] | Debit |  | Nil
[10 empty] | GST Remaining |  | 75802
Qty as per updated Dawing
|  |  | Dia | Length | CUM |  |  | ITEM | DPR | CUM | EXCESS | RATE | AMT
|  |  | 63 | 5175 | 4794.2 | As per updated drawing |  | 90MM | 588 | 625.9 | 37.9 | 95 | 3600.5
|  |  | 75 | 694 | 678.9 |  |  | j HOOK | 0 | 674 | 674 | 8 | 5392
|  |  | 90 | 588 | 625.9 |  | As per old DPR | BOE | 37.13 | 301.7 | 264.57 | 50 | 13228.5
|  |  | 110 | 434 | 421.6 | [6 empty] | hold amt | 22221
|  |  | 160 | 774 | 768 | [6 empty] | prev hold | #REF!
|  |  | 200 | 273 | 189.5 | [6 empty] | to be hold | #REF!
|  |  | Total | 7938