## Sheet1
Subcontractor: | Yashank Enterprises
State: | Uttar Pradesh
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | R A Bill | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | Hydro_Testing | On_Commission | Finishing and Painting | GST_SD_Amount | Hold Amount against Material | Final_Amount |  | Total_Amount | UTR | Village Wise Advance
[8 empty] | 18% |  | 1% | 5% | 10% | 10% | 5% | 18%
59167
59167 | Buwara Kalan Khatauli Village Pipe Laying Work | 2023-09-20 | 1 | 1 | 350068 | 0 | 350068 | 63012 | 413080 | 3501 | 17503 | 35006.8 | 35006.8 | 0 | 63012 | 151734 | 107316.4 |  | 148500 | 12-09-2023 NEFT/AXISP00423960534/RIUP23/1974/YASHANK ENTERPRISE 148500.00 | -172125.32
59167 | Buwara Kalan Khatauli Village Pipe Laying Work | 2023-11-10 | 4 | 4 | 605746 | 0 | 605746 | 109034.28 | 714780.28 | 6057.46 | 30287.3 | 60574.6 | 60574.6 |  | 109034.28 | 4943 | 443309.04 |  | 107316 | 17-10-2023 NEFT/AXISP00435088307/RIUP23/2464/YASHANK ENTERPRISE/SBIN0016607 107316.00
59167 | Buwara Kalan Khatauli Village Pipe Laying Work | 2023-12-01 | 5 | 5 | 1330488 | 75000 | 1255488 | 225987.84 | 1481475.84 | 12554.88 | 62774.4 | 125548.8 | 125548.8 |  | 225987.84 | 3580 | 925481.12 |  | 198000 | 10-11-2023 NEFT/AXISP00443464526/RIUP23/3256/YASHANK ENTERPRISE/SBIN0016607 198000.00
59167 | GST Release Note |  |  | 1 | 63012 | [11 empty] | 63012 |  | 245309 | 30-11-2023 NEFT/AXISP00447912057/RIUP23/3478/YASHANK ENTERPRISE/SBIN0016607 245309.00
59167 | GST Release Note |  |  | 4 | 109034.28 | [11 empty] | 109034.28 |  | 925481 | 15-12-2023 NEFT/AXISP00448856963/RIUP23/3740/YASHANK ENTERPRISE/SBIN0016607 ₹ 925481.00
59167 | GST Release Note |  |  | 5 | 225987.84 | [11 empty] | 225987.84 |  | 63012 | 23-01-2024 NEFT/AXISP00464221607/RIUP23/4296/YASHANK ENTERPRISE/SBIN0016607 63012.00
59167 | [18 empty] | 225988 | 13-02-2024 NEFT/AXISP00471059300/RIUP23/4485/YASHANK ENTERPRISE/SBIN0016607 ₹ 2,25,988.00
59167 | [18 empty] | 132660 | 20-08-2024 NEFT/AXISP00530112318/RIUP24/1502/YASHANK ENTERPRISE/SBIN0016607 132660.00
59325
59325 | Rampur Village Reinstating of GP work | 2023-10-26 | 2 | 2 | 189932 | 0 | 189932 | 34188 | 224120 | 1899 | 9497 | 0 | 0 | 0 | 34188 | 0 | 178536 |  | 99000 | 18-09-2023 NEFT/AXISP00425751844/RIUP23/2098/YASHANK ENTERPRISE/SBIN0016607 99000.00 | 0
59325 | GST Release Note |  |  | 2 | 34188 | [11 empty] | 34188 |  | 79536 | 01-11-2023 NEFT/AXISP00439227016/RIUP23/3008/YASHANK ENTERPRISE/SBIN0016607 79536.00
59325 | [18 empty] | 34188 | 23-01-2024 NEFT/AXISP00464221606/RIUP23/4297/YASHANK ENTERPRISE/SBIN0016607 34188.00
59413
59413 | Saidpur village - Khatauli block - pipeline work | 2023-12-20 | 2 | 10 | 682204 | 45200 | 637004 | 114661 | 751665 | 6370 | 31850 | 63700.4 | 63700.4 | 0 | 114661 | 0 | 471383 |  | 148500 | 27-09-2023 NEFT/AXISP00427829831/RIUP23/2338/YASHANK ENTERPRISE/SBIN0016607 148500.00 | -1
59413 | GST Release Note |  |  |  | 114661 | [11 empty] | 114661 |  | 322884 | 01-01-2024 NEFT/AXISP00457977969/RIUP23/4033/YASHANK ENTERPRISE/SBIN0016607 ₹ 3,22,884.00
59413 | [18 empty] | 114661 | 08-08-2024 NEFT/AXISP00526375816/RIUP24/1253/YASHANK ENTERPRISE/SBIN0016607 114661.00
59734
59734 | Chacharpur village - Khatauli block - pipeline work | 2023-11-04 | 2 | 3 | 966465 | 116425 | 850040 | 153007 | 1003047 | 8500 | 42502 | 85004 | 85004 | 0 | 153007 | 28024 | 601006 |  | 148500 | 13-10-2023 NEFT/AXISP00434019645/RIUP23/2632/YASHANK ENTERPRISE/SBIN0016607 148500.00 | -1
59734 | GST Release Note |  |  | 3 | 153007 | [11 empty] | 153007 |  | 346500 | 13-11-2023 NEFT/AXISP00416756862/RIUP23/3277/YASHANK ENTERPRISES 346500.00
59734 | [18 empty] | 106007 | 24-01-2024 NEFT/AXISP00464671613/RIUP23/4444/YASHANK ENTERPRISE/SBIN0016607 106007.00
59734 | [18 empty] | 153007 | 20-06-2024 NEFT/AXISP00510553856/RIUP24/0176/YASHANK ENTERPRISE/SBIN0016607 153007.00
59912
59912 | Wazidpur Khurd village - Khatauli - pipeline work | [17 empty] | 198000 | 26-10-2023 NEFT/AXISP00437006005/RIUP23/2880/YASHANK ENTERPRISE/SBIN0016607 198000.00 | -198000
59912
60158
60158 | Bahpur village - Khatauli - PH work | 2024-01-29 | 6 | 16 | 343500 | 0 | 343500 | 61830 | 405330 | 3435 | 17175 | 0 | 0 | 0 | 61830 | 0 | 322890 |  | 148500 | 22-11-2023 NEFT/AXISP00445662197/RIUP23/3376/YASHANK ENTERPRISE/SBIN0016607 ₹ 1,48,500.00 | 0
60158 | GST |  |  | 16 | [12 empty] | 61830 |  | 174390 | 23-02-2024 NEFT/AXISP00473725242/RIUP23/4798/YASHANK ENTERPRISE/SBIN0016607 ₹ 1,74,390.00
60158 | [18 empty] | 61830 | 29-04-2024 NEFT/AXISP00494414233/RIUP24/0171/YASHANK ENTERPRISE/SBIN0016607 61830.00
60229
60229 | Mohiddinpur village - Khataulli - Pipeline work | 2023-12-14 | 6 | 9 | 590794 | 0 | 590794 | 106343 | 697137 | 5908 | 29540 | 59079.4 | 59079.4 | 0 | 106343 | 0 | 437187.2 |  | 198000 | 24-11-2023 NEFT/AXISP00446292730/RIUP23/3401/YASHANK ENTERPRISE/SBIN0016607 198000.00 | -0.8
60229 | GST |  |  | 9 | 106343 | [11 empty] | 106343 |  | 239188 | 01-01-2024 NEFT/AXISP00457977968/RIUP23/4008/YASHANK ENTERPRISE/SBIN0016607 ₹ 2,39,188.00
60229 | [18 empty] | 106343 | 23-01-2024 NEFT/AXISP00464221608/RIUP23/4393/YASHANK ENTERPRISE/SBIN0016607 106343.00
60230
60230 | Bhoopkheri village - Khatauli - pipeline work | 2023-12-10 | 6 | 8 | 780673 | 56250 | 724423 | 130396 | 854819 | 7244 | 36221 | 72442.3 |  | 0 | 130396 | 0 | 608515.7 |  | 198000 | 24-11-2023 NEFT/AXISP00446292731/RIUP23/3402/YASHANK ENTERPRISE/SBIN0016607 198000.00 | -0.3
60230 | GST |  |  | 8 | 130396 | [11 empty] | 130396 |  | 410516 | 15-12-2023 NEFT/AXISP00453272894/RIUP23/3742/YASHANK ENTERPRISE/SBIN0016607 410516.00
60230 | [18 empty] | 130396 | 23-01-2024 NEFT/AXISP00464221609/RIUP23/4392/YASHANK ENTERPRISE/SBIN0016607 130396.00
60327
60327 | JANSATH village BALANCE PIPELINE & REINSTATEMENT WORK BLOCK JANSATH | 2024-02-17 | 6 | 18 | 638227 | 75000 | 563227 | 101381 | 664608 | 5632 | 28161 | 56322.7 | 56322.7 | 0 | 101381 | 0 | 416788.6 |  | 198000 | 29-11-2023 NEFT/AXISP00447355242/RIUP23/3495/YASHANK ENTERPRISE/SBIN0016607 198000.00 | 0.6
60327 | GST |  |  | 18 | 101381 | [11 empty] | 101381 |  | 218788 | 23-02-2024 NEFT/AXISP00473458156/RIUP23/4803/YASHANK ENTERPRISE/SBIN0016607 218788.00
60327 | [18 empty] | 101381 | 20-08-2024 NEFT/AXISP00530112326/RIUP24/0173/YASHANK ENTERPRISE/SBIN0016607 101381.00
60359
60359 | Samuli village Pipline work | 2023-12-10 | 6 | 7 | 732660 | 75000 | 657660 | 118379 | 776039 | 6577 | 32883 | 65766 |  | 0 | 118379 | 0 | 552434 |  | 198000 | 01-12-2023 NEFT/AXISP00448554463/RIUP23/3551/YASHANK ENTERPRISE/SBIN0016607 ₹ 1,98,000.00 | 0
60359 | GST |  |  | 7 | 118379 | [11 empty] | 118379 |  | 354434 | 15-12-2023 NEFT/AXISP00447458963/RIUP23/3741/YASHANK ENTERPRISE/SBIN0016607 ₹ 354434.00
60359 | [18 empty] | 118379 | 24-01-2024 NEFT/AXISP00464671615/RIUP23/4391/YASHANK ENTERPRISE/SBIN0016607 118379.00
60520
60520 | MUJAHIDPUR village BALANCE PIPELINE & REINSTATEMENT WORK AT MUJAHIDPUR | 2023-12-07 | 6 | 6 | 372545 | 0 | 372545 | 67058 | 439603 | 3725 | 18627 | 37254.5 | 37254.5 | 0 | 67058 | 0 | 275684 |  | 198000 | 06-12-2023 NEFT/AXISP00450230176/RIUP23/3627/YASHANK ENTERPRISE/SBIN0016607 198000.00 | 1
60520 | GST |  |  | 6 | 67058 | [11 empty] | 67058 |  | 77683 | 18-12-2023 NEFT/AXISP00453885478/RIUP23/3826/YASHANK ENTERPRISE/SBIN0016607 77683.00
60520 | [18 empty] | 67058 | 24-01-2024 NEFT/AXISP00464671614/RIUP23/4390/YASHANK ENTERPRISE/SBIN0016607 67058.00
60520
60520
60521
60521 | SAIDIPUR RAJU village BALANCE PIPELINE & REINSTATEMENT WORK AT SAIDIPUR RAJU BLOCK JANSATH | 2024-02-17 | 6 | 19 | 825222 | 75000 | 750222 | 135040 | 885262 | 7502 | 37511 | 75022.2 | 75022.2 | 0 | 135040 | 347264 | 207900.6 |  | 247500 | 06-12-2023 NEFT/AXISP00450230177/RIUP23/3628/YASHANK ENTERPRISE/SBIN0016607 247500.00 | -39599.4
60521 | GST |  |  | 19 | 135040 | [11 empty] | 135040 |  | 135040 | 21-06-2024 NEFT/AXISP00511014631/RIUP24/0174/YASHANK ENTERPRISE/SBIN0016607 135040.00
60585
60585 | YAHIYAPUR village CONSTRUCTION OF PUMP HOUSE WORK AT YAHIYAPUR BLOCK KHATAULI | 2024-01-29 | 6 | 14 | 343500 | 0 | 343500 | 61830 | 405330 | 3435 | 17175 | 0 | 0 | 0 | 61830 | 0 | 322890 |  | 148500 | 14-12-2023 NEFT/AXISP00452878856/RIUP23/3750/YASHANK ENTERPRISE/SBIN0016607 148500.00 | 0
60585 | GST |  |  | 14 | 61830 | [11 empty] | 61830 |  | 174390 | 23-02-2024 NEFT/AXISP00473725241/RIUP23/4799/YASHANK ENTERPRISE/SBIN0016607 ₹ 1,74,390.00
60585 | [18 empty] | 61830 | 01-06-2024 NEFT/AXISP00505106984/RIUP24/0169/YASHANK ENTERPRISE/SBIN0016607 61830.00
60586
60586 | WAZIDPUR village ONSTRUCTION OF PUMP HOUSE WORK AT WAZIDPUR KHURD BLOCK KHATAULI | 2024-01-29 | 6 | 15 | 343500 | 0 | 343500 | 61830 | 405330 | 3435 | 17175 | 0 | 0 | 0 | 61830 | 0 | 322890 |  | 99000 | 14-12-2023 NEFT/AXISP00452878945/RIUP23/3752/YASHANK ENTERPRISE/SBIN0016607 99000.00 | 0
60586 | GST |  |  | 15 | 61830 | [11 empty] | 61830 |  | 223890 | 14-03-2024 NEFT/AXISP00480996459/RIUP23/4802/YASHANK ENTERPRISE/SBIN0016607 223890.00
60586 | [18 empty] | 61830 | 01-06-2024 NEFT/AXISP00505106985/RIUP24/0170/YASHANK ENTERPRISE/SBIN0016607 61830.00
60815
60815 | MORKUKKA village BALANCE PIPELINE & REINSTATEMENT WORK AT MORKUKKA BLOCK SHAHPUR | 2024-01-30 | 6 | 17 | 889542 | 87500 | 802042 | 144368 | 946410 | 8020 | 40102 | 80204.2 | 80204.2 | 0 | 144368 | 0 | 593511.6 |  | 247500 | 19-12-2023 NEFT/AXISP00454102599/RIUP23/3864/YASHANK ENTERPRISE/SBIN0016607 247500.00 | -0.4
60815 | GST |  |  | 17 | 144368 | [11 empty] | 144368 |  | 346012 | 23-02-2024 NEFT/AXISP00473458155/RIUP23/4788/YASHANK ENTERPRISE/SBIN0016607 346012.00
60815 | [18 empty] | 144368 | 18-05-2024 NEFT/AXISP00501160941/RIUP24/0172/YASHANK ENTERPRISE/SBIN0016607 144368.00
61566
61566 | AHRORA village BALANCE REINSTATEMENT WORK AT AHRORA BLOCK JANSATH | 2024-01-25 | 6 | 12 | 662937 | 164250 | 498687 | 89764 | 588451 | 4987 | 24934 | 49868.7 | 49868.7 | 0 | 89764 | 0 | 369028.6 |  | 198000 | 04-01-2024 NEFT/AXISP00459090343/RIUP23/4101/YASHANK ENTERPRISE/SBIN0016607 198000.00 | 0.6
61566 | GST |  |  | 12 | 89764 | [11 empty] | 89764 |  | 171028 | 31-01-2024 NEFT/AXISP00466285364/RIUP23/4513/YASHANK ENTERPRISE/SBIN0016607 ₹ 1,71,028.00
61566 | [18 empty] | 89764 | 18-05-2024 NEFT/AXISP00501160939/RIUP24/0166/YASHANK ENTERPRISE/SBIN0016607 89764.00
61581
61581 | PALDA village REINSTATEMENT WORK AT PALDA BLOCK SHAHPUR | 2024-01-25 | 6 | 13 | 593380 | 143750 | 449630 | 80933 | 530563 | 4496 | 22482 | 44963 | 44963 | 0 | 80933 | 0 | 332726 |  | 198000 | 09-01-2024 NEFT/AXISP00460826676/RIUP23/4174/YASHANK ENTERPRISE/SBIN0016607 198000.00 | 0
61581 | GST |  |  | 13 | 80933 | [11 empty] | 80933 |  | 134726 | 31-01-2024 NEFT/AXISP00466285365/RIUP23/4514/YASHANK ENTERPRISE/SBIN0016607 ₹ 1,34,726.00
61581 | [18 empty] | 80933 | 18-05-2024 NEFT/AXISP00501160940/RIUP24/0168/YASHANK ENTERPRISE/SBIN0016607 80933.00
61582
61582 | RETTANAGLA village BALANCE REINSTATEMENT WORK AT RETTANAGLA BLOCK PURKAZI | 2024-02-29 |  | 21 | 850633 |  | 850633 | 153114 | 1003747 | 8506 | 42532 | 85063.3 | 85063.3 | 0 | 153114 | 0 | 629468.4 |  | 198000 | 09-01-2024 NEFT/AXISP00460826677/RIUP23/4175/YASHANK ENTERPRISE/SBIN0016607 198000.00 | 81468.4
61582 | GST |  |  | 13 | 153114 | [11 empty] | 153114 |  | 200000 | 20-03-2024 NEFT/AXISP00482717101/RIUP23/5067A/YASHANK ENTERPRISE/SBIN0016607 200000.00
61582 | [18 empty] | 153114 | 07-05-2024 NEFT/AXISP00497844236/RIUP24/0344/YASHANK ENTERPRISE/SBIN0016607 153114.00
61582 | [18 empty] | 150000 | 14-05-2024 NEFT/AXISP00499706360/RIUP24/0475/YASHANK ENTERPRISE/SBIN0016607 150000.00
61594
61594 | SAFIPUR PATTI village BALANCE REINSTATEMENT WORK AT SAFIPUR PATTI BLOCK BUDHANA | 2024-03-27 |  | 23 | 867557 |  | 867557 | 156160 | 1023717 | 8676 | 43378 | 86755.7 | 86755.7 | 0 | 156160 | 80300 | 561691.6 |  | 198000 | 09-01-2024 NEFT/AXISP00460826678/RIUP23/4176/YASHANK ENTERPRISE/SBIN0016607 198000.00 | -0.4
61594 | gst |  |  | 23 | 156160 | [11 empty] | 156160 |  | 250000 | 04-07-2024 NEFT/AXISP00515401666/RIUP24/0540/YASHANK ENTERPRISE/SBIN0016607 250000.00
61594 | [18 empty] | 113692 | 22-07-2024 NEFT/AXISP00520480179/RIUP24/1229/YASHANK ENTERPRISE/SBIN0016607 113692.00
61594 | [18 empty] | 156160 | 13-09-2024 NEFT/AXISP00540466587/RIUP24/1594/YASHANK ENTERPRISE/SBIN0016607 156160.00
61794
61794 | KUTUBPUR village BALANCE REINSTATEMENT WORK AT KUTUBPUR BLOCK PURKAZI | 2024-02-29 |  | 20 | 858602 |  | 858602 | 154548 | 1013150 | 8586 | 42930 | 85860.2 | 85860.2 | 0 | 154548 | 0 | 635365.6 |  | 198000 | 17-01-2024 NEFT/AXISP00463099913/RIUP23/4290/YASHANK ENTERPRISE/SBIN0016607 198000.00 | -1.4
61794 | GST |  |  | 20 | 154548 | [11 empty] | 154548 |  | 437367 | 20-03-2024 NEFT/AXISP00482717118/RIUP23/5112/YASHANK ENTERPRISE/SBIN0016607 437367.00
61794 | [18 empty] | 154548 | 18-05-2024 NEFT/AXISP00501160937/RIUP24/0175/YASHANK ENTERPRISE/SBIN0016607 154548.00
61794
61808
61808 | SHAHBAZPUR TIGAI village BALANCE REINSTATEMENT WORK AT SHAHBAZPUR TIGAI BLOCK KHATAULI | 2024-01-25 | 6 | 12 | 409291 | 105000 | 304291 | 54772 | 359063 | 3043 | 15215 | 30429.1 | 30429.1 | 0 | 54772 | 15881 | 209293.8 |  | 209294 | 31-01-2024 NEFT/AXISP00466285366/RIUP23/4512/YASHANK ENTERPRISE/SBIN0016607 ₹ 2,09,294.00 | -0.2
61808 | GST |  |  | 12 | 54772 | [11 empty] | 54772 |  | 54772 | 22-07-2024 NEFT/AXISP00520480182/RIUP24/0167/YASHANK ENTERPRISE/SBIN0016607 54772.00
61808
61821
61821 | BHOHJHAHERI VILLAGE BALANCE REINSTATEMENT & FHTC WORK AT BHOHJHAHERI VILLAGE BLOCK PURKAZI | [17 empty] | 148500 | 25-01-2024 NEFT/AXISP00464983354/RIUP23/4473/YASHANK ENTERPRISE/SBIN0016607 ₹ 1,48,500.00 | -148500
61821
61856
61856 | CHAMRAWALA village BALANCE REINSTATEMENT & FHTC WORK AT CHAMRAWALA BLOCK PURKAZI | [17 empty] | 198000 | 25-01-2024 NEFT/AXISP00464876198/RIUP23/4462/YASHANK ENTERPRISE/SBIN0016607 198000.00 | -198000
63285
63285 | ANTWARA village CONSTRUCTION OF PUMP HOUSE WORK AT ANTWARA | 2024-03-26 | 6 | 22 | 222000 | 0 | 222000 | 39960 | 261960 | 2220 | 11100 |  |  | 0 | 39960 | 0 | 208680 |  | 208680 | 26-04-2024 NEFT/AXISP00493991579/RIUP24/0244/YASHANK ENTERPRISE/SBIN0016607 208680.00 | 114680
63285 | GST |  |  |  | 39960 | [11 empty] | 39960 |  | 39960 | 31-08-2024 NEFT/AXISP00534333412/RIUP24/1156/YASHANK ENTERPRISE/SBIN0016607 ₹ 39,960.00
63285 | ANTWARA village CONSTRUCTION OF PUMP HOUSE WORK AT ANTWARA | 2024-12-14 | 6 | 3 | 122000 | 0 | 122000 | 21960 | 143960 | 1220 | 6100 |  |  | 0 | 21960 | 0 | 114680 |  | 21960 | 24-03-2025 NEFT/AXISP00637858121/RIUP24/3202/YASHANK ENTERPRISE/SBIN0016607 21960.00
63285 | GST |  |  | 3 | 21960 | [11 empty] | 21960
64191
64191 | MUBARIKPUR village RR work | 2024-06-26 | 6 | 1 | 654705 | 0 | 654705 | 117847 | 772552 | 6547 | 32735 | 65470.5 | 65470.5 | 0 | 117847 | 0 | 484482 |  | 99000 | 21-06-2024 NEFT/AXISP00510912034/RIUP24/0938/YASHANK ENTERPRISE/SBIN0016607 99000.00 | 85482
64191 | GST |  |  | 1 | 117847 | [11 empty] | 117847 |  | 150000 | 22-07-2024 NEFT/AXISP00520480174/RIUP24/1040/YASHANK ENTERPRISE/SBIN0016607 150000.00
64191 | [18 empty] | 150000 | 08-08-2024 NEFT/AXISP00526375821/RIUP24/1394/YASHANK ENTERPRISE/SBIN0016607 150000.00
64191 | [18 empty] | 117847 | 14-01-2025 NEFT/AXISP00598257725/RIUP24/2942/YASHANK ENTERPRISE/SBIN0016607 117847.00
64354
64354 | Antwara village - BW work | [17 empty] | 99000 | 28-06-2024 NEFT/AXISP00512718430/RIUP24/0996/YASHANK ENTERPRISE/SBIN0016607 99000.00 | -99000
64467
64467 | RAIPUR NAGLI village CONSTRUCTION OF BOUNDARY WALL WORK AT RAIPUR NAGLI | 2024-12-14 | 5 | 5 | 304794 | 0 | 304794 | 54863 | 359657 | 3048 | 15240 |  |  | 0 | 54863 | 0 | 286506 |  | 99000 | 08-08-2024 NEFT/AXISP00526375820/RIUP24/1393/YASHANK ENTERPRISE/SBIN0016607 99000.00 | 242369
64467 | GST |  |  | 5 | 54863 | [11 empty] | 54863
64468
64468 | Phulat village - BW work | 2024-12-14 | 4 | 4 | 240188 | 0 | 240188 | 43234 | 283422 | 2402 | 12009 |  |  | 0 | 43234 | 0 | 225777 |  | 43234 | 24-03-2025 NEFT/AXISP00637858122/RIUP24/3203/YASHANK ENTERPRISE/SBIN0016607 43234.00 | 225777
64468 | GST |  |  | 4 | 43234 | [11 empty] | 43234
64468
65865
65865 | JABARDASTPUR URF MANTODI village BOUNDARY WALL WORK AT JABARDASTPUR URF MANTODI BLOCK -JANSATH | [17 empty] | 99000 | 13-09-2024 NEFT/AXISP00540466588/RIUP24/1794/YASHANK ENTERPRISE/SBIN0016607 99000.00 | -99000
67331
67331 | KHATAULI village CONSTRUCTION OF WATER RECHARGE UNIT work KHATAULI | 2024-12-14 | 4 | 2 | 140000 | 0 | 140000 | 25200 | 165200 | 1400 | 7000 |  |  | 0 | 25200 | 70000 | 61600 |  |  |  | 86800
67331 | GST |  |  | 2 | 25200 | [11 empty] | 25200
68215
68215 | RASOOLPUR KAILORA KHATAULI village CONSTRUCTION OF APPROACH ROAD, AREA DEVELOPMENT work -RASOOLPUR KAILORA KHATAULI | 2025-02-28 | 4 | 6 | 117846 | 0 | 117846 | 21212 | 139058 | 1178.46 | 5892.3 |  |  | 0 | 21212 | 0 | 110775.24 |  |  |  | 131987.24
68215 | GST |  |  | 2 | 21212 | [11 empty] | 21212
68215
[11 empty] | 737638.7 | 1264336.4 | 1126128.1 | 0 | 2655500.12 | 631726 | 13719709.62 |  | 13705374 |  | 14335.62
14335.62
Yashank Enterprises
2025-03-22
[13 empty] | Total Hold |  | 3128103.2
[13 empty] | DPR Hold |  | 631726
[13 empty] | Advance / Surplus |  | 14335.62
[13 empty] | Debit |  | Nil
[13 empty] | GST Remaining |  | Nil