## Sheet1
Subcontractor: | Rana Construction
State: | Uttar Pradesh |  | Rana Construction |  |  |  | Pipeline Laying work
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold Amount For Quantity excess against DPR | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | SD (5%) | Advance paid | Total_Amount | UTR
[9 empty] | 1% | 5% | 10% | 10% | [6 empty] | 1% | 5%
58062
58062 | Adampur Village Pipeline laying work | 2023-06-21 | 1 | 99550 | 9907.7 | 89642.3 | 16136 | 105778.3 | 896.423 | 4482.115 | 8964.23 | 8964.23 | 16136 | 0 | 66335 |  | RIUP23/945 | 66336 | 0 | 0 | 0 | 66336 | 01-07-2023 NEFT/AXISP00402820433/RIUP23/945/RANA CONSTRUCTIO 66336.00
58062 | Adampur Village Pipeline laying work | 2023-09-11 | 3 | 382869.5 | 31524 | 351345.5 | 63242 | 414587.5 | 3513.455 | 17567.275 | 35134.55 | 35134.55 | 63242 | 9885 | 250111 |  | RIUP23/2092 | 250111 | 0 | 0 | 0 | 250111 | 22-09-2023 NEFT/AXISP00426907956/RIUP23/2092/RANA CONSTRUCTION/HDFC0004496 250111.00
58062 | GST |  | 1 & 3 | 79378 | [10 empty] | 79378 | [6 empty] | 79378 | 02-12-2023 NEFT/AXISP00449103426/RIUP23/3457/RANA CONSTRUCTION/HDFC0004496 79378.00
58062
[16 empty] | 57751 | [7 empty] | -1
57751 | Adampur Village Pipeline laying work | 2023-09-21 | 1 | 637478 | 0 | 637478 | 114746 | 752224 | 6374.78 | 31873.9 | 63747.8 | 63747.8 | 114746 | 43121 | 428613 |  | RIUP23/945 | 0 | 0 | 0 | 0 | 428613 | 30-09-2023 NEFT/AXISP00428978261/RIUP23/2387/RANA CONTRACTOR/PUNB0165910 428613.00
57751 | Adampur Village Pipeline laying work | 2023-11-06 | 2 | 129336 | 0 | 129336 | 23280 | 152616 | 1293.36 | 6466.8 | 12933.6 | 12933.6 | 23280 | 37374 | 58335 |  |  |  | 0 | 0 | 0 | 49500 | 09-11-2023 NEFT/AXISP00442779063/RIUP23/3200/RANA CONTRACTOR/PUNB0165910 49500.00
57751 | GST |  | 1 | 114746 | [10 empty] | 114746 | [6 empty] | 114746 | 27-12-2023 NEFT/AXISP00455698582/RIUP23/3777/RANA CONTRACTOR/PUNB0165910 114746.00
57751 | GST |  | 2 | 23280 | [10 empty] | 23280 | [6 empty] | 23280 | 02-05-2024 NEFT/AXISP00496371081/RIUP24/0196/RANA CONTRACTOR/PUNB0165910 ₹ 23,280.00
57751 | Adampur Village Pipeline laying work | 2024-02-22 | 4 | 472909 | 106391 | 366518 | 65973 | 432491 | 3665.18 | 18325.9 | 36651.8 | 36651.8 | 65973 | 33887 | 237336 | [6 empty] | 107480 | 02-05-2024 NEFT/AXISP00496371080/RIUP24/0197/RANA CONTRACTOR/PUNB0165910 ₹ 1,07,480.00
57751 | Adampur Village Pipeline laying work | 2024-03-26 | 5 | 148122 | 0 | 148122 | 26662 | 174784 | 1481.22 | 7406.1 | 14812.2 | 14812.2 | 26662 | 2130 | 107480 |  |  |  | 0 | 0 | 0 | 8833 | 28-05-2024 NEFT/AXISP00503313478/RIUP23/4954/RANA CONTRACTOR/PUNB0165910 8833.00
57751 | [21 empty] | 120000 | 28-05-2024 NEFT/AXISP00503313480/RIUP23/4955/RANA CONTRACTOR/PUNB0165910 120000.00
57751 | [21 empty] | 117335 | 03-08-2024 NEFT/AXISP00524511263/RIUP24/0897/RANA CONTRACTOR/PUNB0165910 117335.00 | 3
[12 empty] | Total Payable Amount Rs. - |  |  | 1365614 |  |  |  |  | Total Paid Amount Rs. - |  | 1365612
[20 empty] | Balance Payable Amount Rs. - |  | 2
[5 empty] | ITEM | EXCESS | RATE | AMOUNT
[5 empty] | Dism BOE | 20.2 | 50 | 1010
[5 empty] | Dism C C | 35.5 | 250 | 8875
[7 empty] | Hold Amt | 9885