## Sheet1
Subcontractor: | laviesh Contractors
State: | Uttar Pradesh
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold Amount For Quantity excess against DPR | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | Total_Amount | UTR
[9 empty] | 1% | 5% | 10% | 10% | [6 empty] | 1%
58886
58886 | Naunagali village pipe line work | 2023-08-12 | 1 | 423664 | 54042 | 369622 | 66532 | 436154 | 3696.22 | 18481.1 | 36962.2 | 36962.2 | 66532 |  | 273520 |  | RIUP23/1659 | 200000 | 2000 | 198000 | 22-08-2023 IFT/IFT23234016785/RIUP23/1659 LAVISH CONTRACTOR 198000.00
58886 | Naunagali village pipe line work | 2023-09-13 | 2 | 156750 | 36028 | 120722 | 21730 | 142452 | 1207.22 | 6036.1 | 12072.2 | 12072.2 | 21730 |  | 89334 |  | RIUP23/1917 | 75522 |  | 75522 | 08-09-2023 IFT/IFT23251034859/RIUP23/1917/LAVISH CONTRACTOR 75522.00
58886 | GST Release Note |  | 1.2 | 88262 | [10 empty] | 88262 |  | RIUP23/2268 | 89335 |  | 89335 | 26-09-2023 IFT/IFT23269023084/RIUP23/2268/LAVISH CONTRACTOR 89335.00
58886 | Naunagali village pipe line work | 2023-12-18 | 3 | 192510 | 18014 | 174496 | 31409 | 205905 | 1744.96 | 8724.8 | 17449.6 | 17449.6 | 31409 | 9828 | 119299 |  | RIUP23/2966 | 50000 | 500 | 49500 | 27-10-2023 IFT/IFT23300027465/RIUP23/2966/LAVISH CONTRACTOR 49500.00
58886 | [16 empty] | RIUP23/2966 | 69798 |  | 69798 | 30-12-2023 IFT/IFT23364191583/RIUP23/4020/LAVISH CONTRACTOR 69798.00
[14 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 0 | 0 |  |  |  |  | 0
0
[10 empty] | 33242 | 66484 | 66484 |  | Total Payable Amount Rs. - | 570415 |  | Total Paid Amount Rs. - |  |  | 482155
[17 empty] | Balance |  |  | 88260
Aman Enterprisess
Updated On 26-02-2024 ( By Vikash )
[9 empty] | Total Hold |  | 166210
[9 empty] | Advance / Surplus |  | 88260
Debit