## Sheet1
Subcontractor: | Aarya Chaudhary Construction
State: | Uttar Pradesh
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS (1%) | SD (5%) | On Commissioning | Hydro Testing | Hold the Amount because the Qty. is more then the DPR | GST_SD_Amount | Final_Amount |  | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% | 10% | 10% |  | 18%
2 | [15 empty] | 59345
59345 | Phulat-Khatauli Village - Drilling Work | 2023-10-04 | 1 | 288460 |  | 288460 | 51922.8 | 340383 | 2884.6 | 14423 | 0 | 0 | 0 | 51922.8 | 271153 |  | 99000 | 20-09-2023 IFT/IFT23263007400/RIUP23/2131/AARYA CHOUDHARY CO 99000.00
59345 | GST Release Note | 2023-11-18 | 1 | 51922 | [10 empty] | 51922 |  | 172152 | 25-10-2023 IFT/IFT23298013280/RIUP23/2846/AARYA CHOUDHARY CO 172152.00
[6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 51922 | 24-11-2023 IFT/IFT23328069273/RIUP23/3361/AARYA CHOUDHARY CO 51922.00
1 | [15 empty] | 59619
59619 | Kadli Village Drilling Work | 2023-10-16 | 2 | 299768 |  | 299768 | 53958 | 353726 | 2997.68 | 14988.4 | 0 | 0 | 0 | 53958 | 281782 |  | 99000 | 20-09-2023 IFT/IFT23263007400/RIUP23/2131/AARYA CHOUDHARY CO 99000.00
59619 | GST Release Note | 2023-11-18 | 1 | 53958 | [10 empty] | 53958 |  | 182782 | 26-10-2023 IFT/IFT23299033074/RIUP23/2889/AARYA CHOUDHARY CO ₹ 1,82,782.00
59619 | [16 empty] | 53958 | 24-11-2023 IFT/IFT23328069274/RIUP23/3362/AARYA CHOUDHARY CO 53958.00
9 | [15 empty] | 60037
60037 | Umarpur lisoda Village BOREWELL DRILLING Work | 06.11.23 | 3 | 294653 |  | 294653 | 53037.54 | 347691 | 2946.53 | 14732.65 | 0 | 0 |  | 53037.54 | 276974 |  | 99000 | 06-12-2023 IFT/IFT23340064957/RIUP23/3632/AARYA CHOUDHARY CO 99000.00
60037 | GST Release Note | 06.11.23 | 3 | 53038 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 53038 |  | 177974 | 20-12-2023 IFT/IFT23354005099/RIUP23/3746/AARYA CHOUDHARY CO 177974.00
60037 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 53038 | 03-01-2024 IFT/IFT24003039016/RIUP23/4004/AARYA CHOUDHARY CO 53038.00
5 | [15 empty] | 61000
61000 | KHATAULI Village DRILLING Work |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 99000 | 22-12-2023 IFT/IFT23356037809/RIUP23/3929/AARYA CHOUDHARY CO 99000.00
3 | [15 empty] | 61577
61577 | PAL Village BOREWELL DRILLING Work | 2024-01-16 | 4 | 322431 |  | 322431 | 58037.58 | 380469 | 3224.31 | 16121.55 | 0 | 0 | 0 | 58037.58 | 303086 |  | 99000 | 09-01-2024 IFT/IFT24009010981/RIUP23/4172/AARYA CHOUDHARY CO 99000.00
61577 | GST Release Note | 16.01.24 | 4 | 58038 | [10 empty] | 58038 |  | 204085 | 24-01-2024 IFT/IFT24024026248/RIUP23/4418/AARYA CHOUDHARY CO 204085.00
61577 | [16 empty] | 58038 | 20-02-2024 IFT/IFT24051018000/RIUP23/4744/AARYA CHOUDHARY CO ₹ 58,038.00
4 | [15 empty] | 61579
61579 | GANGDHAR Village CONSTRUTION OF PUMP HOUSE Work | 05.3.24 | 6 | 222000 |  | 222000 | 39960 | 261960 | 2220 | 11100 | 0 | 0 | 0 | 39960 | 208680 |  | 99000 | 09-01-2024 IFT/IFT24009010982/RIUP23/4173/AARYA CHOUDHARY CO 99000.00
61579 | GANGDHAR Village CONSTRUTION OF PUMP HOUSE Work | 21.03.2024 | 8 | 122000 |  | 122000 | 21960 | 143960 | 1220 | 6100 | 0 | 0 |  | 21960 | 114680 |  | 109680 | 18-03-2024 IFT/IFT24078011924/RIUP23/5105/AARYA CHOUDHARY CO 109680.00
61579 | GST Release Note |  | 6 | 39960 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 39960 |  | 114680 | 26-04-2024 IFT/IFT24117022558/RIUP24/007/AARYA CHOUDHARY CO 114680.00
61579 | GST Release Note |  | 8 | 21960 | [10 empty] | 21960 |  | 39960 | 20-06-2024 IFT/IFT24172008885/RIUP24/0532/AARYA CHOUDHARY CO ₹ 39,960.00
[17 empty] | 21960 | 29-06-2024 IFT/IFT24181086756/RIUP24/0970/AARYA CHOUDHARY CO 21960.00
8 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 61883
61883 | Kadli Village CONSTRUTION OF PUMP HOUSE Work | 2024-06-10 | 2 | 222000 |  | 222000 | 39960 | 261960 | 2220 | 11100 | 0 | 0 | 0 | 39960 | 208680 |  | 99000 | 09-02-2024 IFT/IFT24040015439/RIUP23/4631/AARYA CHOUDHARY CO 99000.00
61883 | Kadli Village CONSTRUTION OF PUMP HOUSE Work |  | 2 | 39960 | [10 empty] | 39960 |  | 50000 | 22-07-2024 IFT/IFT24204033866/RIUP24/0973/AARYA CHOUDHARY CO 50000.00
61883 | Kadli Village CONSTRUTION OF PUMP HOUSE Work | [15 empty] | 59680 | 08-08-2024 IFT/IFT24221031162/RIUP24/1395/AARYA CHOUDHARY CO 59680.00
61883 | Kadli Village CONSTRUTION OF PUMP HOUSE Work | [15 empty] | 39960 | 23-09-2024 IFT/IFT24267033869/RIUP24/1531/AARYA CHOUDHARY CO 39960.00 -7476581.52
7 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 61884
61884 | Anti Village CONSTRUTION OF PUMP HOUSE Work | 2024-04-10 | 1 | 222000 |  | 222000 | 39960 | 261960 | 2220 | 11100 | 0 | 0 |  | 39960 | 208680 |  | 99000 | 09-02-2024 IFT/IFT24040015440/RIUP23/4632/AARYA CHOUDHARY CO 99000.00
61884 | GST Release Note |  | 1 | 39960 | [6 empty] | 0 | 0 |  | 0 | 39960 |  | 109680 | 28-05-2024 IFT/IFT24149026961/RIUP24/0486/AARYA CHOUDHARY CO 109680.00
61884 | [16 empty] | 39960 | 28-06-2024 IFT/IFT24180052301/RIUP24/0821/AARYA CHOUDHARY CO 39960.00
6 | [15 empty] | 62110
62110 | NAGLA MUBARIK Village BOREWELL DRILLING Work | 04.02.24 | 5 | 323349.5 |  | 323349.5 | 58202.91 | 381552 | 3233.495 | 16167.475 | 0 | 0 | 0 | 58202.91 | 303948 |  | 303949 | 16-02-2024 IFT/IFT24047018640/RIUP23/4685/AARYA CHOUDHARY CO ₹ 3,03,949.00
62110 | GST Release Note |  | 5 | 58202.91 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 58202.91 |  | 58203 | 16-03-2024 IFT/IFT24076024649/RIUP23/5156/AARYA CHOUDHARY CO 58203.00
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
10 | [15 empty] | 62404
62404 | Water Rechareg Unit
11 | [15 empty] | 62718
62718 | Shahpur Village BOREWELL DRILLING Work | 2024-03-18 | 7 | 281239 | 21364 | 259875 | 46777.5 | 306653 | 2598.75 | 12993.75 | 0 | 0 |  | 46777.5 | 244283 |  | 99000 | 18-03-2024 IFT/IFT24078043208/RIUP23/5177/AARYA CHOUDHARY CO 99000.00
62718 | GST Release Note |  | 7 | 46777.5 | [10 empty] | 46777.5 |  | 145282 | 06-04-2024 IFT/IFT24097097234/RIUP24/010/AARYA CHOUDHARY CO 145282.00
62718 | [16 empty] | 46778 | 21-06-2024 IFT/IFT24173029477/RIUP24/0533/AARYA CHOUDHARY CO 46778.00