## Sheet1
Subcontractor: | M/s Hasan Contractor
State: | Uttar Pradesh
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After Debit Amt | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold Amount For Material | Final_Amount | PAYMENT NOTE No. | Amount | TDS Amount @ 2% on BASIC AMOUNT | Total_Amount | UTR | Advance Village Wise
[7 empty] | 18% |  | 1% | 5% | 5% | 10% | 18% |  |  |  |  | 2%
56767 | Jaitpur Village Pipe layig Work | 2023-04-17 | 2 | 251582 | 0 | 251582 | 45284.76 | 296866.76 | 2516 | 12579 | 25158 | 25158 | 45284.76 | 0 | 186171 |  |  | 0 | 99000 | 20-04-2023 20-04-2023 NEFT/AXISP00383281369/SPUP23/0209/HASAN CONTRACTO 99000.00 | -0.24
56767 | GST Release Note |  | 2 | 45284.76 | [10 empty] | 45284.76 |  |  | 0 | 87171 | 12-05-2023 NEFT/AXISP00389861565/RIUP23/217/HASANCONTRACTOR 87171.00
56767 | [14 empty] | 0 |  |  | 0 | 45285 | 24-05-2023 NEFT/AXISP00392230451/RIUP23/345/HASAN CONTRACTOR 45285.00
0
56765 | Faloda Village Pipe layig Work | 2023-08-11 | 6 | 1186695 | 16560 | 1170135 | 210624.3 | 1380759.3 | 11701 | 58507 | 58507 | 117014 | 210624.3 | 239405 | 685001 |  |  | 0 | 198000 | 20-04-2023 20-04-2023 NEFT/AXISP00383281370/SPUP23/0208/HASAN CONTRACTO 198000.00 | 0
56765 | GST Release Note | 2023-09-11 | 6 | 210624 | 0 | 210624 |  | 210624 | [6 empty] | 210624 |  |  | 0 | 49500 | 12-05-2023 NEFT/AXISP00389894135/RIUP23/224/HASAN CONTRACTOR 49500.00
56765 | [17 empty] | 0 | 99000 | 19-06-2023 NEFT/AXISP00399550943/RIUP23/727/HASAN CONTRACTOR 99000.00
56765 | [18 empty] | 338501 | 22-08-2023 NEFT/AXISP00417367264/RIUP23/1640/HASAN CONTRACTOR 338501.00
56765 | [18 empty] | 210624 | 30-09-2023 NEFT/AXISP00429071462/RIUP23/2318/HASAN CONTRACTOR/BARB0MUZNAG 210624.00
54742 | Dulhera Village Pipe laying work | 2023-03-29 | 1 | 212028.3 | 0 | 212028.3 | 38165 | 250193.3 | 2120 | 10601 | 10601 | 21203 | 38165 | 21940.5 | 145563 |  |  | 0 | 145562 | 2023 April 05 ---------- Hasan Contractors ------------- AXISP00378614200 ------------- Rs. 1,45,562 | 1
54742 | DPR Excess Hold Amount | 2023-04-07 | 1 | 21940 | [10 empty] | 21940 |  |  | 0 | 21940 | 2023 April 07 ---------- Hasan Contractors ------------- AXISP00379707435 ------------- Rs. 21,940
54742 | GST Release Note | 2023-05-22 | 1 | 38165 | [10 empty] | 38165 |  |  | 0 | 38165 | 23-05-2023 NEFT/AXISP00392043095/RIUP23/346/HASAN CONTRACTOR ₹ 38,165.00
54742 | Dulhera Village Pipe laying work | 2023-10-25 | 8 | 1017774.7 | 7020 | 1010754.7 | 181936 | 1192690.7 | 10108 | 50538 | 50538 | 101075 | 181936 | 49702 | 748794 |  |  |  | 748794 | 13-11-2023 NEFT/AXISP00416756865/RIUP23/2976/ HASNA CONTR 748794.00
54742 | GST Release Note |  | 8 | 181936 | [10 empty] | 181936 |  |  |  | 181936 | 13-02-2024 NEFT/AXISP00470943293/RIUP23/4294/HASAN CONTRACTOR/BARB0MUZNAG 181936.00
59249 | Ghussilkhera Village Pipe laying work | 2023-09-13 | 7 | 165000 | 5600 | 159400 | 28692 | 188092 | 1594 | 7970 |  |  | 28692 | 0 | 149836 |  |  |  | 149836 | 13-10-2023 NEFT/AXISP00434019636/RIUP23/2094/HASAN CONTRACTOR/BARB0MUZNAG 149836.00 | 0
59249 | GST Release Note |  | 7 | 28692 | [10 empty] | 28692 |  |  |  | 28692 | 20-02-2024 NEFT/AXISP00472620881/RIUP23/4753/HASAN CONTRACTOR/BARB0MUZNAG ₹ 28,692.00
58520 | Kacholi Village Pipe laying work | 2023-08-03 | 4 | 918117 | 3540 | 914577 | 164623.86 | 1079200.86 | 9145.77 | 45729 | 45729 | 91458 | 164623.86 | 248384 | 474131 | RIUP23/1639 | 474131 | 0 | 474131 | 28-08-2023 NEFT/AXISP00418870937/RIUP23/1639/HASAN CONTRACTOR/BARB0MUZNAG 474131.00 | 0
58520 | GST RELEASE NOTE |  | 4 | 164623.86 |  | 164623.86 |  | 164623.86 | [6 empty] | 164624 | RIUP23/1639 | 164624 | 0 | 164624 | 19-12-2023 NEFT/AXISP00454102601/RIUP23/3812/HASAN CONTRACTOR/BARB0MUZNAG 164624.00
58520 | Kacholi Village Pipe laying work | 2024-05-14 | 11 | 217952 | 0 | 217952 | 39231.36 | 257183.36 | 2179.52 | 10898 | 21795 | 21795 | 39231.36 | 114575 | 46709 |  |  |  | 39231 | 13-09-2024 NEFT/AXISP00540414552/RIUP24/1131/HASAN CONTRACTOR/BARB0MUZNAG 39231.00
58520 | GST RELEASE NOTE |  | 11 | 39231.36 | [10 empty] | 39231.36 |  |  |  | 46709.36 | 13-09-2024 NEFT/AXISP00540414553/RIUP24/0626/HASAN CONTRACTOR/BARB0MUZNAG 46709.00
62203 | BALANCE PIPE LAYING WORK AT LAKHAN VILLAGE | 2024-02-08 | 9 | 457065 | 246890 | 210175 | 37831.5 | 248006.5 | 2101.75 | 10509 | 21018 | 21018 | 37831.5 | 140908 | 14620 |  |  |  | 14620 | 14-05-2024 NEFT/AXISP00499706379/RIUP23/4785/HASAN CONTRACTOR/BARB0MUZNAG 14620.00 | 20048.5
62203 | Gst RELEASE NOTE |  | 9 | 37831.5 | [10 empty] | 37831.5 |  |  |  | 37832 | 17-06-2024 NEFT YESIG41690031112-BARB0MUZNAG-HASAN CONTRACTOR-RIUP24/0582 RS 37,832.00
62203 | BALANCE PIPE LAYING WORK AT LAKHAN VILLAGE | 2024-08-18 | 12 | 142871 | 0 | 142871 | 25716.78 | 168587.78 | 1428.71 | 7144 | 14287 | 14287 | 25716.78 | 36175 | 69549 |  |  |  | 49500 | 13-09-2024 NEFT/AXISP00540414563/RIUP24/1781/HASAN CONTRACTOR/BARB0MUZNAG 49500.00
62203 | Gst RELEASE NOTE |  | 12 | 25716.78 | [10 empty] | 25716.78
63328 | ATALI VILLAGE BLOCK BAGHRA PIPE LAYING WORK | 10.04.24 | 10 | 270000 |  | 270000 | 48600 | 318600 | 2700 | 13500 |  |  | 48600 |  | 253800 |  |  |  | 253800 | 24-04-2024 NEFT/AXISP00493457023/RIUP24/0152/HASAN CONTRACTOR/BARB0MUZNAG 253800.00 | 0
63328 | GST RELEASE NOTE |  | 10 | 48600 | [10 empty] | 48600 |  |  |  | 48600 | 13-06-2024 NEFT/AXISP00509097741/RIUP24/0534/HASAN CONTRACTOR/BARB0MUZNAG 48600.00
M/s Hasan Contractor
2024-09-20
[9 empty] | Hold Amount |  | #REF!
[9 empty] | Advance / Surplus |  | #REF!
[9 empty] | Debit |  | Nil
[9 empty] | GST Remaining |  | cleae