## Sheet1
Subcontractor: | Hammer Projects
State: | Uttar Pradesh | [6 empty] | OHT Construction work
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On Commissioning | GST_SD_Amount | Final_Amount | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | SD (5%) | Advance paid | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% | 0% | 18% |  |  |  | 1% | 5%
57638 | Dhanena Village OHT Construction work 150kl 12 m | 2023-09-07 | 5 | 371250 | 255537 | 115713 | 20828 | 136541 | 1157 | 5786 | 0 | 20828 | 108770 | RIUP23/1046 | 100000 | 1000 | 0 | 0 | 99000 | 10-07-2023 NEFT/AXISP00405672807/RIUP23/1046/HAMMER PROJECT 98000.00
57638 | [13 empty] | RIUP23/1341 | 50000 | 500 | 0 | 0 | 49500 | 02-08-2023 NEFT/AXISP00411992216/RIUP23/1341/HAMMER PROJECT 49000.00
57638 | [18 empty] | 49000 | 14-09-2023 NEFT/AXISP00424961338/RIUP23/2024/HAMMER PROJECT PRI/BDBL0001577 49000.00
57638 | [18 empty] | 98000 | 26-10-2023 NEFT/AXISP00437006001/RIUP23/2876/HAMMER PROJECT PRI/BDBL0001577 98000.00
-186730
57662 | Jandheri Village OHT Construction work 125kl 12 m | 2023-09-07 | 6 | 337500 | 318701 | 18799 | 3383.82 | 22182.82 | 188 | 940 | 0 | 3383.82 | 17671 | RIUP23/516 | 50000 | 1000 | 0 | 0 | 49000 | 05-06-2023 NEFT/AXISP00395669171/RIUP23/517/HAMMER PROJECT P 49000.00
57662 | Jandheri Village OHT Construction work 125kl 12 m | 2023-09-26 | 8 | 225000 | 76278 | 148722 | 26769.96 | 175491.96 | 1487 | 7436 | 0 | 26769.96 | 139799 | RIUP23/1341 | 50000 | 1000 | 0 | 0 | 49000 | 02-08-2023 NEFT/AXISP00411992215/RIUP23/1340/HAMMER PROJECT 49000.00
57662 | GST | 2023-10-16 | 6 | 3383 |  | 3383 | 0 | 3383 | 0 | 0 | 0 | 0 | 3383 | RIUP23/2026 | 50000 | 1000 |  |  | 49000 | 14-09-2023 NEFT/AXISP00424961336/RIUP23/2026/HAMMER PROJECT PRI/BDBL0001577 49000.00
57662 | GST | 2023-10-16 | 8 | 26769 |  | 26769 | 0 | 26769 | 0 | 0 | 0 | 0 | 26769 | RIUP23/2388 | 8795 | 0 |  |  | 8795 | 30-09-2023 NEFT/AXISP00429213815/RIUP23/2388/HAMMER PROJECT PRI/BDBL0001577 8795.00
57662 | [18 empty] | 26770 | 25-10-2023 NEFT/AXISP00436731133/RIUP23/2753/HAMMER PROJECT PRI/BDBL0001577 26770.00
57662 | [18 empty] | 147000 | 26-10-2023 NEFT/AXISP00437006002/RIUP23/2877/HAMMER PROJECT PRI/BDBL0001577 147000.00
-141943
57659 | Gohrani Village OHT Construction work 300kl 14 m | 2023-09-26 | 9 | 567000 | 205737 | 361263 | 65027 | 426290 | 7225 | 18063 | 0 | 65027 | 335975 | RIUP23/514 | 100000 | 1000 |  |  | 99000 | 05-06-2023 NEFT/AXISP00395669168/RIUP23/514/HAMMER PROJECT P 98000.00
57659 | GST | 2023-10-16 | 9 | 65027 | 0 | 65027 | 0 | 65027 | 0 | 0 | 0 | 0 | 65027 | RIUP23/2025 | 50000 | 500 |  |  | 49000 | 14-09-2023 NEFT/AXISP00424961337/RIUP23/2025/HAMMER PROJECT PRI/BDBL0001577 49000.00
57659 | [13 empty] | RIUP23/2389 |  |  |  |  | 188975 | 30-09-2023 NEFT/AXISP00428978259/RIUP23/2389/HAMMER PROJECT PRI/BDBL0001577 188975.00
57659 | [13 empty] | RIUP23/2752 |  |  |  |  | 65027 | 26-10-2023 NEFT/AXISP00437006006/RIUP23/2752/HAMMER PROJECT PRI/BDBL0001577 65027.00
57659
57659 | [20 empty] | -1000
57659
57659
|  | 316387 | 51 | 1595929 | 856253 | 739676 | 116008.78 | 855684.78 | 10057 | 32225 | 0 | 116008.78 | 697394 |  |  |  | Total Paid Amount Rs. - |  | 1027067
[17 empty] | Balance Payable Amount Rs. - |  | -329673