## SHEET1
Subcontractor: | Rajpal contractor
State: | Uttar Pradesh
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | Painting & Fininshing/ On Commissioning | Hydro_Testing | GST_SD_Amount | Hold Amount For Quantity excess against DPR | Final_Amount |  | Total_Amount | UTR | Advance Village Wise
[9 empty] | 1% | 5% | 10% | 10%
55446
55446 | BARNABI village PH Construction Work | 2023-03-07 | 2 | 228600 | 53649.59 | 174950.41 | 31491 | 206441 | 1749.5041 | 8747.5205 | 0 | 0 | 31491 | 8747.5 | 155705 |  | 155704 | 09-03-2023NEFT/AXISP00369981447/RIUP22/2528/RAJPAL SON OF S ₹ 1,55,704.00 | 1
55446 | Barnabi village Pump house work | 2023-03-28 | 3 | 152400 | 0 | 152400 | 27432 | 179832 | 1524 | 15240 | 0 | 0 | 27432 | 0 | 135636 |  | 135636 | 24-04-202324-04-2023NEFT/AXISP00383950327/SPUP23/0230/RAJPAL SON OF S 135636.00
55446 | GST Release Note | 2023-05-03 | 2 | 31491 | [10 empty] | 31491 |  | 31491 | 10-05-2023NEFT/AXISP00389057557/RIUP23/164/RAJPAL SON OF SU ₹ 31,491.00
55446 | GST Release Note | 2023-06-12 | 3 | 27432 | [10 empty] | 27432 |  | 27432 | 17-08-2023NEFT/AXISP00416328858/RIUP23/755/RAJPAL SON OF SU ₹ 27,432.00
58563
58563 | Jalalpur village B wall work | 2023-07-21 | 8 | 14350 | 350 | 14000 | 2520 | 16520 | 140 | 700 |  |  | 2520 |  | 13160 |  | 13160 | 11-08-2023NEFT/AXISP00415257204/RIUP23/1466/RAJPAL SON OF S ₹ 13,160.00 | 0
58563 | GST Release Note | 2023-09-15 | 8 | 2520 | [10 empty] | 2520 |  | 2520 | 18-09-2023NEFT/AXISP00425751840/RIUP23/2058/RAJPAL SON OF SURJ/HDFC0001913 2520.00
58796
58796 | Barnabi Pathar village B Wall work | 2023-08-01 | 7 | 359800 | 38150 | 321650 | 57897 | 379547 | 3216.5 | 16082.5 | 32165 |  | 57897 |  | 270186 |  | 270185 | 07-09-2023NEFT/AXISP00422654373/RIUP23/1846/RAJPAL SON OF SURJ/HDFC0001913 270185.00 | 1
58796 | GST Release Note |  | 7 | 57897 | [10 empty] | 57897 |  | 57897 | 18-09-2023NEFT/AXISP00425751838/RIUP23/2060/RAJPAL SON OF SURJ/HDFC0001913 57897.00
58796 | Barnabi Pathar village B Wall work | 2023-12-19 | 26 | 68775 | 46813 | 21962 | 3953 | 25915 | 219.62 | 1098.1 |  |  | 3953 |  | 20644 |  | 20644 | 17-01-2024NEFT/AXISP00463197278/RIUP23/4188/RAJPAL SON OF SURJ/HDFC0001913 20644.00
58796 | GST Release Note |  | 26 | 3953 | [10 empty] | 3953 |  | 3953 | 05-02-2024NEFT/AXISP00468222687/RIUP23/4406/RAJPAL SON OF SURJ/HDFC0001913 3953.00
58797
58797 | BADHEV KANNUKHERA Village Pump House work | 2023-08-01 | 9 | 75000 | 0 | 75000 | 13500 | 88500 | 750 | 3750 | 0 |  | 13500 |  | 70500 |  | 70500 | 28-08-2023NEFT/AXISP00418773000/RIUP23/1733/RAJPAL SON OF SURJ/HDFC0001913 70500.00 | 0
58797 | GST Release Note |  | 9 | 13500 | [10 empty] | 13500 |  | 13500 | 18-09-2023NEFT/AXISP00425751839/RIUP23/2059/RAJPAL SON OF SURJ/HDFC0001913 13500.00
58797
59370
59370 | Khabeerpur village Pump housew Work | 2023-09-19 | 12 | 304800 | 61926 | 242874 | 43717 | 286591 | 2428.74 | 12143.7 | 0 | 0 | 43717 | 0 | 228301 |  | 228301 | 30-09-2023NEFT/AXISP00429163522/RIUP23/2394/RAJPAL SON OF SURJ/HDFC0001913 228301.00 | 0
59370 | GST Release Note | 2023-10-18 | 12 | 43717 | [10 empty] | 43717 |  | 43717 | 08-11-2023NEFT/AXISP00441999413/RIUP23/2933/RAJPAL SON OF SURJ/HDFC0001913 43717.00
59011
59011 | Titarsi village Pump housew Work | 2023-06-06 | 11 | 125000 | 7630 | 117370 | 21127 | 138497 | 1173.7 | 5868.5 | 0 | 0 | 21127 | 5869 | 104458 |  | 49500 | 25-08-2023NEFT/AXISP00418410655/RIUP23/1718/RAJPAL SON OF SURJ/HDFC0001913 49500.00 | -1
59011 | GST Release Note | 2023-10-18 | 11 | 21126 | [10 empty] | 21126 |  | 54958 | 13-09-2023NEFT/AXISP00424687454/RIUP23/1981/RAJPAL SON OF SURJ/HDFC0001913 54958.00
59011 | [16 empty] | 21127 | 08-11-2023NEFT/AXISP00441999442/RIUP23/2932/RAJPAL SON OF SURJ/HDFC0001913 21127.00 35488888.56 CBB
56243
56243 | Hurmrajpur Sahpur village PH Construction Work | 2023-04-04 | 4 | 190500 | 43271.34 | 147228.66 | 26501 | 173730 | 1472.2866 | 14722.866 | 0 | 0 | 26501 | 0 | 131033 |  | 131033 | 19-04-202319-04-2023NEFT/AXISP00382918217/SPUP23/0153/RAJPAL SON OF S 131033.00 | 0
56243 | Hurmrajpur Sahpur village PH Construction Work | 2023-06-03 | 5 | 190500 | 0 | 190500 | 34290 | 224790 | 1905 | 9525 | 0 | 0 | 34290 | 19050 | 160020 |  | 160020 | 21-06-2023NEFT/AXISP00399921606/RIUP23/768/RAJPAL SON OF SU 160020.00
56243 | GST Release Note |  | 4 & 5 | 60791 | [10 empty] | 60791 |  | 60791 | 21-07-2023NEFT/AXISP00408446753/RIUP23/1125/RAJPAL SON OF S 60791.00
58562
58562 | Jalalpur village Pump housew Work | 2023-07-21 | 7 | 57000 | 0 | 57000 | 10260 | 67260 | 570 | 2850 | 0 | 0 | 10260 | 0 | 53580 |  | 53580 | 01-08-2023NEFT/AXISP00411711486/RIUP23/1318/RAJPAL SON OF S 53580.00 | 0
58562 | GST Release Note |  | 7 | 10260 | [10 empty] | 10260 |  | 10260 | 18-09-2023NEFT/AXISP00425751841/RIUP23/2057/RAJPAL SON OF SURJ/HDFC0001913 10260.00
58557
58557 | Jalalpur village DG paltform Work | 2023-07-19 | 6 | 40000 | 9537.5 | 30462.5 | 5483 | 35946 | 304.625 | 1523.125 | 0 | 0 | 5483 | 0 | 28635 |  | 28635 | 08-11-2023NEFT/AXISP00441999429/RIUP23/2999/RAJPAL SON OF SURJ/HDFC0001913 28635.00 | 5483
58557 | GST Release Note |  | 6 | 5483 | [10 empty] | 5483
59316
59316 | Kheda Gadai Village Pump house Pending Work | 2023-10-09 | 14 | 145000 | 0 | 145000 | 26100 | 171100 | 1450 | 7250 | 0 | 0 | 26100 | 0 | 136300 |  | 136300 | 25-10-2023NEFT/AXISP00436681642/RIUP23/2839/RAJPAL SON OF SURJ/HDFC0001913 136300.00 | 0
59316 | GST Release Note | 2023-11-15 | 14 | 26100 | [10 empty] | 26100 |  | 26100 | 18-11-2023NEFT/AXISP00445057537/RIUP23/3312/RAJPAL SON OF SURJ/HDFC0001913 26100.00
0
59826
59826 | Goharni Village Pump house Pending Work | 2023-10-09 | 13 | 170000 | 33187 | 136813 | 24626 | 161439 | 1368.13 | 6840.65 | 0 | 0 | 24626 | 0 | 128604 |  | 128603 | 25-10-2023NEFT/AXISP00436681643/RIUP23/2838/RAJPAL SON OF SURJ/HDFC0001913 128603.00 | 1
59826 | GST Release Note | 2023-11-15 | 13 | 24626 | [10 empty] | 24626 |  | 24626 | 18-11-2023NEFT/AXISP00445057536/RIUP23/3311/RAJPAL SON OF SURJ/HDFC0001913 24626.00
59827
59827 | Jaffarpur Village Pump house Pending Work | 2023-10-09 | 15 | 59900 | 0 | 59900 | 10782 | 70682 | 599 | 2995 | 0 | 0 | 10782 | 0 | 56306 |  | 56306 | 25-10-2023NEFT/AXISP00436681641/RIUP23/2840/RAJPAL SON OF SURJ/HDFC0001913 56306.00 | 0
59827 | GST Release Note |  | 15 | 10782 | [10 empty] | 10782 |  | 10782 | 18-11-2023NEFT/AXISP00445057538/RIUP23/3313/RAJPAL SON OF SURJ/HDFC0001913 10782.00
58887
58887 | Unchgaon Village PH work | 2023-10-09 | 17 | 190500 | 38631 | 151869 | 27336 | 179205 | 1518.69 | 7593.45 | 0 | 0 | 27336 | 0 | 142756 |  | 142757 | 08-11-2023NEFT/AXISP00441999417/RIUP23/2959/RAJPAL SON OF SURJ/HDFC0001913 142757.00 | -2
58887 | Unchgaon Village PH work | 2023-11-08 | 19 | 133350 | 5722 | 127628 | 22973 | 150601 | 1276.28 | 6381.4 | 0 | 0 | 22973 |  | 119970 |  | 27337 | 18-11-2023NEFT/AXISP00445057540/RIUP23/3315/RAJPAL SON OF SURJ/HDFC0001913 27337.00
58887 | GST Release Note | 2023-11-15 | 17 | 27336 | [10 empty] | 27336 |  | 119970 | 29-11-2023NEFT/AXISP00447355219/RIUP23/3332/RAJPAL SON OF SURJ/HDFC0001913 119970.00
58887 | GST Release Note |  | 19 | 22973 | [10 empty] | 22973 |  | 22973 | 27-12-2023NEFT/AXISP00455698607/RIUP23/3821/RAJPAL SON OF SURJ/HDFC0001913 22973.00
59317
59317 | Yarpur Village PH work | 2023-10-21 | 18 | 75000 |  | 75000 | 13500 | 88500 | 750 | 3750 | 0 | 0 | 13500 | 0 | 70500 |  | 70500 | 08-11-2023NEFT/AXISP00441999430/RIUP23/2998/RAJPAL SON OF SURJ/HDFC0001913 70500.00 | 0
59317 | GST Release Note | 2023-11-15 | 18 | 13500 | [10 empty] | 13500 |  | 13500 | 18-11-2023NEFT/AXISP00445057541/RIUP23/3316/RAJPAL SON OF SURJ/HDFC0001913 13500.00
59836
59836 | Mahawatpur village PH work | 2023-10-09 | 16 | 55200 |  | 55200 | 9936 | 65136 | 552 | 2760 | 0 | 0 | 9936 | 0 | 51888 |  | 51888 | 25-10-2023NEFT/AXISP00436928372/RIUP23/2861/RAJPAL SON OF SURJ/HDFC0001913 51888.00 | 0
59836 | GST Release Note | 2023-11-15 | 16 | 9936 | [10 empty] | 9936 |  | 9936 | 18-11-2023NEFT/AXISP00445057539/RIUP23/3314/RAJPAL SON OF SURJ/HDFC0001913 9936.00
60324
60324 | Bidauli village PH work | 2023-11-24 | 21 | 60000 |  | 60000 | 10800 | 70800 | 600 | 3000 | 0 | 0 | 10800 | 0 | 56400 |  | 56400 | 30-11-2023NEFT/AXISP00447586134/RIUP23/3510/RAJPAL SON OF SURJ/HDFC0001913 56400.00 | 0
60324 | GST Release Note |  | 21 | 10800 | [10 empty] | 10800 |  | 10800 | 27-12-2023NEFT/AXISP00455698605/RIUP23/3819/RAJPAL SON OF SURJ/HDFC0001913 10800.00
60325
60325 | Kamalpur villahe PH work | 2023-11-24 | 22 | 80000 |  | 80000 | 14400 | 94400 | 800 | 4000 | 0 | 0 | 14400 | 0 | 75200 |  | 21460 | 30-11-2023NEFT/AXISP00447911604/RIUP23/3509/RAJPAL SON OF SURJ/HDFC0001913 21460.00 | 0
60325 | GST Release Note |  | 22 | 14400 | [10 empty] | 14400 |  | 14400 | 27-12-2023NEFT/AXISP00455698608/RIUP23/3822/RAJPAL SON OF SURJ/HDFC0001913 14400.00
60325 | [16 empty] | 53740 | 02-02-2024NEFT/AXISP00467574861/RIUP23/4346/RAJPAL SON OF SURJ/HDFC0001913 53740.00
60143
60143 | Khevari village PH work | 2023-11-16 | 20 | 209550 | 46665 | 162885 | 29319 | 192204 | 1628.85 | 8144.25 | 0 | 0 | 29319 | 0 | 153111 |  | 99000 | 09-11-2023NEFT/AXISP00442779053/RIUP23/3194/RAJPAL SON OF SURJ/HDFC0001913 99000.00 | -1
60143 | GST Release Note |  | 20 | 29319 | [10 empty] | 29319 |  | 54112 | 02-12-2023NEFT/AXISP00449103410/RIUP23/3555/RAJPAL SON OF SURJ/HDFC0001913 54112.00
60143 | Khevari village PH woprk | 2024-01-06 | 30 | 114300 | 0 | 114300 | 20574 | 134874 | 1143 | 5715 | 0 | 0 | 20574 | 0 | 107442 |  | 29319 | 27-12-2023NEFT/AXISP00455698606/RIUP23/3820/RAJPAL SON OF SURJ/HDFC0001913 29319.00
60143 | GST Release Note |  | 30 | 20574 | [10 empty] | 20574 |  | 107442 | 16-01-2024NEFT/AXISP00462739023/RIUP23/4213/RAJPAL SON OF SURJ/HDFC0001913 107442.00
[17 empty] | 20574 | 28-02-2024NEFT/AXISP00474663210/RIUP23/4740/RAJPAL SON OF SURJ/HDFC0001913 20574.00
60142
60142 | UDPUR VILLAGE PUMP HOUSE WORK | 2023-09-04 | 25 | 228600 | 42294 | 186306 | 33535 | 219841 | 1863.06 | 9315.3 | 0 | 0 | 33535 | 0 | 175127 |  | 69300 | 09-11-2023NEFT/AXISP00442779051/RIUP23/3193/RAJPAL SON OF SURJ/HDFC0001913 69300.00 | -2
60142 | UDPUR VILLAGE PUMP HOUSE WORK | 2024-01-06 | 30 | 95250 | 67510 | 27740 | 4993 | 32733 | 277.4 | 1387 | 0 | 0 | 4993 | 0 | 26075 |  | 105828 | 27-12-2023NEFT/AXISP00455698580/RIUP23/3749/RAJPAL SON OF SURJ/HDFC0001913 105828.00
60142 | GST Release Note |  | 25 | 33535 | [10 empty] | 33535 |  | 26076 | 07-02-2024NEFT/AXISP00469197344/RIUP23/4284/RAJPAL SON OF SURJ/HDFC0001913 26076.00
60142 | GST Release Note |  | 30 | 4993 | [10 empty] | 4993 |  | 4993 | 28-02-2024NEFT/AXISP00474663209/RIUP23/4741/RAJPAL SON OF SURJ/HDFC0001913 4993.00
60142 | [16 empty] | 33535 | 25-04-2024NEFT/AXISP00493738094/RIUP23/5130/RAJPAL SON OF SURJ/HDFC0001913 33535.00
60571
60571 | DHATERA VILLAGE Pump House Pending Work | 2023-12-03 | 23 | 80000 | 0 | 80000 | 14400 | 94400 | 800 | 4000 | 0 | 0 | 14400 | 0 | 75200 |  | 39600 | 22-03-2024NEFT/AXISP00483444836/RIUP23/5257/RAJPAL SON OFSURJ/HDFC0001913 39600.00 | 0
60571 | GST Release Note |  | 23 | 14400 | [10 empty] | 14400 |  | 35600 | 26-04-2024NEFT/AXISP00493978718/RIUP24/002/RAJPAL SON OF SURJ/HDFC0001913 35600.00
60571 | [16 empty] | 14400 | 26-04-2024NEFT/AXISP00493978719/RIUP24/003/RAJPAL SON OF SURJ/HDFC0001913 14400.00
60572
60572 | ULHANI BINAMAZRA VILLAGE Pump House Pending Work | 2023-12-03 | 24 | 80000 | 0 | 80000 | 14400 | 94400 | 800 | 4000 | 0 | 0 | 14400 | 0 | 75200 |  | 14400 | 22-03-2024NEFT/AXISP00483444823/RIUP23/4866/RAJPAL SON OF SURJ/HDFC0001913 14400.00 | 0
60572 | GST Release Note | 2024-02-27 | 24 | 14400 | [10 empty] | 14400 |  | 75200 | 03-08-2024NEFT/AXISP00524511256/RIUP23/4867/RAJPAL SON OF SURJ/HDFC0001913 75200.00
60572
60572
60926
60926 | JANGHERI VILLAGE Pump House Pending Work | 2023-12-19 | 27 | 50000 | 38150 | 11850 | 2133 | 13983 | 118.5 | 592.5 | 0 | 0 | 2133 | 0 | 11139 |  | 11138 | 07-02-2024NEFT/AXISP00469197342/RIUP23/4450/RAJPAL SON OF SURJ/HDFC0001913 11138.00 | 1
60926 | GST Release Note |  | 27 | 2133 | [10 empty] | 2133 |  | 2133 | 07-02-2024NEFT/AXISP00469197343/RIUP23/4451/RAJPAL SON OF SURJ/HDFC0001913 2133.00
60926
60727
60727 | KADARPUR village PH Construction Work | 2024-01-10 | 31 | 323850 | 31962 | 291888 | 52540 | 344428 | 2918.88 | 14594.4 | 0 | 0 | 52540 | 0 | 274374 |  | 99000 | 13-12-2023NEFT/AXISP00452748658/RIUP23/3616A/RAJPAL SON OF SURJ/HDFC0001913 ₹ 99,000.00 | 0
60727 | GST Release Note |  | 31 | 52540 | [10 empty] | 52540 |  | 175374 | 05-02-2024NEFT/AXISP00468222683/RIUP23/4332/RAJPAL SON OF SURJ/HDFC0001913 175374.00
60727 | [16 empty] | 52540 | 28-02-2024NEFT/AXISP00474663208/RIUP23/4742/RAJPAL SON OF SURJ/HDFC0001913 52540.00
60728
60728 | HURMRAJPUR SAHPUR village B.WALL Construction Work | 2024-02-29 | 33 | 332325 | 0 | 332325 | 59819 | 392144 | 3323.25 | 16616.25 | 0 | 0 | 59819 | 0 | 312385 |  | 99000 | 16-01-2024NEFT/AXISP00462742316/RIUP23/4273/RAJPAL SON OF SURJ/HDFC0001913 99000.00 | -1
60728 | GST Release Note |  | 33 | 59819 | [10 empty] | 59819 |  | 150000 | 01-06-2024NEFT/AXISP00505106981/RIUP24/001/RAJPAL SON OF SURJ/HDFC0001913 150000.00
60728 | [16 empty] | 59819 | 03-08-2024NEFT/AXISP00524511259/RIUP24/0614/RAJPAL SON OF SURJ/HDFC0001913 59819.00
[17 empty] | 63386 | 03-08-2024NEFT/AXISP00524511279/RIUP24/1349/RAJPAL SON OF SURJ/HDFC0001913 63386.00
61649
61649 | MULLAPUR Village Pump House Work | 2024-01-06 | 28 | 209550 | 0 | 209550 | 37719 | 247269 | 2095.5 | 10477.5 | 0 | 0 | 37719 | 0 | 196977 |  | 196976 | 01-02-2024NEFT/AXISP00467376689/RIUP23/4200/RAJPAL SON OF SURJ/HDFC0001913 196976.00 | 1
61649 | MULLAPUR Village Pump House Work | 2024-04-04 | 36 | 114300 | 0 | 114300 | 20574 | 134874 | 1143 | 5715 | 0 | 0 | 20574 | 0 | 107442 |  | 37719 | 28-02-2024NEFT/AXISP00474663211/RIUP23/4739/RAJPAL SON OF SURJ/HDFC0001913 37719.00
61649 | GST Release Note |  | 28 | 37719 | [10 empty] | 37719 |  | 107442 | 26-04-2024NEFT/AXISP00493978720/RIUP24/0223/RAJPAL SON OF SURJ/HDFC0001913 107442.00
61649 | GST Release Note | 2024-03-31 | 36 | 20574 | [10 empty] | 20574 |  | 20574 | 14-11-2024NEFT/AXISP00569462145/RIUP24/1763/RAJPAL SON OF SURJ/HDFC0001913 20574.00
63198
63198 | Mioyan KASBA village PH Construction Work | 2024-02-23 | 32 | 323850 | 14497 | 309353 | 55684 | 365037 | 3093.53 | 15467.65 | 0 | 0 | 55684 | 0 | 290791 |  | 150000 | 01-06-2024NEFT/AXISP00505106982/RIUP24/086/RAJPAL SON OF SURJ/HDFC0001913 150000.00 | 0
63198 | GST Release Note |  | 32 | 55684 | [10 empty] | 55684 |  | 140791 | 14-08-2024NEFT/AXISP00528230625/RIUP24/1467/RAJPAL SON OF SURJ/HDFC0001913 140791.00
[17 empty] | 55684 | 14-08-2024NEFT/AXISP00528230627/RIUP24/0616/RAJPAL SON OF SURJ/HDFC0001913 55684.00
63270
63270 | NAGAL ISMAILPUR village PH Construction Work | 2024-03-31 | 35 | 209550 | 0 | 209550 | 37719 | 247269 | 2095.5 | 10477.5 | 0 | 0 | 37719 | 0 | 196977 |  | 196976 | 26-04-2024NEFT/AXISP00493978721/RIUP24/0224/RAJPAL SON OF SURJ/HDFC0001913 196976.00 | 1
63270 | NAGAL ISMAILPUR village PH Construction Work | 2024-04-16 | 1 | 114300 | 0 | 114300 | 20574 | 134874 | 1143 | 5715 | 0 | 0 | 20574 | 0 | 107442 |  | 107442 | 05-07-2024NEFT/AXISP00515770434/RIUP24/0408/RAJPAL SON OF SURJ/HDFC0001913 107442.00
63270 | GST Release Note | 2024-05-07 | 35 & 1 | 58293 | [10 empty] | 58293 |  | 58293 | 05-07-2024NEFT/AXISP00515770433/RIUP24/0617/RAJPAL SON OF SURJ/HDFC0001913 58293.00
63271
63271 | GUJJARPUR village Pump House Repairing Work | 2024-04-02 | 34 | 75000 | 25942 | 49058 | 8830 | 57888 | 490.58 | 2452.9 | 0 | 0 | 8830 | 0 | 46114 |  | 46114 | 17-05-2024NEFT/AXISP00500883069/RIUP24/0222/RAJPAL SON OF SURJ/HDFC0001913 46114.00 | 0
63271 | GST Release Note |  | 34 | 8830 | [10 empty] | 8830 |  | 8830 | 30-08-2024NEFT/AXISP00533718974/RIUP24/0615/RAJPAL SON OF SURJ/HDFC0001913 8830.00
63320
63320 | Naunagali-Purmafi Village Sign Board Work | 2024-05-02 | 2 | 59400 | 0 | 59400 | 10692 | 70092 | 594 | 2970 | 0 | 0 | 10692 | 0 | 55836 |  | 55836 | 17-05-2024NEFT/AXISP00500883087/RIUP24/0494/RAJPAL SON OF SURJ/HDFC0001913 55836.00 | 51012
| Naunagali-Purmafi Village Sign Board Work | 2024-06-01 | 4 | 36000 | 0 | 36000 | 6480 | 42480 | 360 | 1800 | 0 | 0 | 6480 | 0 | 33840
| GST Release Note | 2024-05-02 | 2 | 10692 | [10 empty] | 10692
| GST Release Note | 2024-06-01 | 4 | 6480 | [10 empty] | 6480
64249
64249 | Ulhani Binamazara village BW work | 2024-06-01 | 3 | 277830 | 19075 | 258755 | 46576 | 305331 | 2587.55 | 12937.75 | 0 | 0 | 46576 | 0 | 243229 |  | 125000 | 03-08-2024NEFT/AXISP00524511265/RIUP24/0961/RAJPAL SON OF SURJ/HDFC0001913 125000.00 | 0
| GST Release Note | 2024-06-01 | 3 | 46576 | [10 empty] | 46576 |  | 118229 | 12-09-2024NEFT/AXISP00539728287/RIUP24/1766/RAJPAL SON OF SURJ/HDFC0001913 118229.00
[17 empty] | 46576 | 30-10-2024NEFT/AXISP00561389901/RIUP24/1477/RAJPAL SON OF SURJ/HDFC0001913 46576.00
66418
66418 | AMBETHA YAKUBPUR Village PUMP HOUSE CONSTRUCTION Work | 2024-11-20 | 6 | 323850 | 19075 | 304775 | 54860 | 359635 | 3047.75 | 15238.75 | 0 | 0 | 54860 | 0 | 286488 |  | 200000 | 20-12-2024NEFT/AXISP00587058611/RIUP24/2547/RAJPAL SON OF SURJ/HDFC0001913 200000.00 | 0
66418 | GST Release Note |  | 6 | 54860 | [10 empty] | 54860 |  | 54860 | 08-01-2025NEFT/AXISP00595630486/RIUP24/2772/RAJPAL SON OF SURJ/HDFC0001913 54860.00
66418 | [16 empty] | 50000 | 07-02-2025NEFT/AXISP00612564983/RIUP24/3123/RAJPAL SON OF SURJ/HDFC0001913 50000.00
[17 empty] | 36488 | 09-04-2025NEFT/AXISP00648889482/RIUP25/0059/RAJPAL SON OF SURJ/HDFC0001913 36488.00
66419
66419 | BASI CHUNDIYARI VILLAGE PUMP HOUSE CONSTRUCTION Work | 2024-11-20 | 7 | 323850 | 0 | 323850 | 58293 | 382143 | 3238.5 | 16192.5 | 0 | 0 | 58293 | 0 | 304419 |  | 275000 | 28-11-2024NEFT/AXISP00575911962/RIUP24/2548/RAJPAL SON OF SURJ/HDFC0001913 275000.00 | 29419
66419 | GST Release Note |  | 7 | 58293 | [10 empty] | 58293 |  | 58293 | 08-01-2025NEFT/AXISP00595630487/RIUP24/2773/RAJPAL SON OF SURJ/HDFC0001913 58293.00
66106
66106 | Atta Village RR work | 2024-10-25 | 5 | 237204 | 105799 | 131405 | 23653 | 155058 | 1314.05 | 6570.25 | 13140.5 | 13140.5 | 23653 | 0 | 97239 |  | 75000 | 22-11-2024NEFT/AXISP00573587607/RIUP24/2492/RAJPAL SON OF SURJ/HDFC0001913 75000.00 | 0
66106 | GST Release Note |  | 5 | 23653 | [10 empty] | 23653 |  | 23653 | 28-11-2024NEFT/AXISP00575911961/RIUP24/2552/RAJPAL SON OF SURJ/HDFC0001913 23653.00
[17 empty] | 22239 | 07-03-2025NEFT/AXISP00629925746/RIUP24/3375/RAJPAL SON OF SURJ/HDFC0001913 22239.00
67198
67198 | Manat village Manti Reconstruction & Extend Boundary Wall work | 2024-11-30 | 8 | 132125 | 0 | 132125 | 23783 | 155908 | 1321.25 | 6606.25 | 0 | 0 | 23783 | 124197 | 0 |  | 23783 | 25-03-2025NEFT/AXISP00638559404/RIUP24/3484/RAJPAL SON OF SURJ/HDFC0001913 23783.00 | 0
67198 | GST Release Note |  | 8 | 23783 | [10 empty] | 23783
67494
67494 | MADALPUR VILLAGE PUMP HOUSE CONSTRUCTION Work | 2025-01-04 | 9 | 203500 | 67226 | 136274 | 24529 | 160803 | 1362.74 | 6813.7 | 0 | 0 | 24529 | 0 | 128097 |  | 75000 | 21-01-2025NEFT/AXISP00601114148/RIUP24/2929/RAJPAL SON OF SURJ/HDFC0001913 75000.00 | 39502
67494 | GST Release Note |  | 9 | 24529 | [10 empty] | 24529 |  | 53098 | 07-02-2025NEFT/AXISP00612564984/RIUP24/3124/RAJPAL SON OF SURJ/HDFC0001913 53098.00
67494 | MADALPUR VILLAGE PUMP HOUSE CONSTRUCTION Work | 2025-03-17 | 14 | 120350 | 78324 | 42026 | 7565 | 49591 | 420.26 | 2101.3 | 0 | 0 | 7565 | 0 | 39504 |  | 24530 | 25-03-2025NEFT/AXISP00638559402/RIUP24/3483/RAJPAL SON OF SURJ/HDFC0001913 24530.00
67494 | GST Release Note
67495
67495 | BADHEV KANUKHERA VILLAGE DG FOUNDATION CONSTRUCTION Work | 2025-01-04 | 10 | 40000 | 0 | 40000 | 7200 | 47200 | 400 | 2000 | 0 | 0 | 7200 | 0 | 37600 |  | 37600 | 25-02-2025NEFT/AXISP00621808046/RIUP24/2930/RAJPAL CONTRACTOR/HDFC0001913 37600.00 | 0
67495 | GST Release Note |  | 10 | 7200 | [10 empty] | 7200 |  | 7200 | 07-03-2025NEFT/AXISP00629925747/RIUP24/3374/RAJPAL SON OF SURJ/HDFC0001913 7200.00
67948
67948 | HASSANPUR VILLAGE PIPE LINE ROAD RESTORATION WORK | 2025-01-20 | 11 | 84992 | 0 | 84992 | 15299 | 100291 | 849.92 | 4249.6 | 0 | 0 | 15299 | 0 | 79892 |  | 50000 | 07-03-2025NEFT/AXISP00629925745/RIUP24/3376/RAJPAL SON OF SURJ/HDFC0001913 50000.00 | 45191
67948 | GST Release Note |  | 11 | 15299 | [10 empty] | 15299
68982
68982 | JALALABAD RURAL village PUMP HOUSE WORK | 2025-03-17 | 12 | 323850 | 0 | 323850 | 58293 | 382143 | 3238.5 | 16192.5 | 0 | 0 | 58293 | 0 | 304419 |  | 50000 | 17-04-2025NEFT/AXISP00652635645/RIUP25/0122/RAJPAL SON OF SURJ/HDFC0001913 50000.00 | 114712
68982 | GST Release Note |  | 12 | 58293 | [10 empty] | 58293 |  | 198000 | 03-05-2025NEFT/AXISP00660705842/RIUP25/0207/CHAUHAN CONTRACTOR/HDFC0007662 198000
68983
68983 | KHIAVRI village BOUNDARY WALL WORK | 2025-03-28 | 15 | 388363 |  | 388363 | 69905 | 458268 | 3883.63 | 19418.15 | 0 | 0 | 69905 | 0 | 365061 |  | 100000 | 17-04-2025NEFT/AXISP00652635644/RIUP25/0121/RAJPAL SON OF SURJ/HDFC0001913 100000.00 | 134966
68983 | GST Release Note |  | 15 | 69905 | [10 empty] | 69905 |  | 200000 | 03-05-2025NEFT/AXISP00660705843/RIUP25/0208/RAJPAL SON OF SURJ/HDFC0001913 200000.00