## Sheet1
Subcontractor: | M/s Shree Shree Balaji contractor
State: | Uttar Pradesh | [6 empty] | All work
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | GST_SD_Amount | Hold Amount | Final_Amount | Total_Amount | UTR
[7 empty] | 18% |  | 5% | 10% | 18%
53073 | [13 empty] | 148500 | 14-11-2022 NEFT/AXISP00337247395/RIUP22/1247/SHRI SHRI BALAJ 148500.00
53073
-148500
53074 | Balwakhedi village- PH work | 2023-02-02 | 1 | 370000 | 41730 | 328270 | 59088.6 | 387358.6 | 16414 | 32827 | 59088.6 |  | 279029 | 99000 | 14-11-2022 NEFT/AXISP00337247396/RIUP22/1248/SHRI SHRI BALAJ 99000.00
53074 | GST |  | 1 | 59088.6 | [8 empty] | 59088.6 | 193160 | 24-02-2023 NEFT/AXISP00365393661/RIUP22/2293/SHRI SHRI BALAJ 193160.00
53074 | [13 empty] | 59088 | 21-04-2023 NEFT/AXISP00383558980/RIUP23/040/SHRI SHRI BALAJI 59088.00
-13130.4
53231
53231
0
53232 | Construction of Pump house work Pipalhera village | 2023-02-07 | 3 | 370000 | 41730 | 328270 | 59089 | 387359 | 16414 | 32827 | 59089 |  | 279029 | 292160 | 13-02-2023 NEFT/AXISP00362757396/RIUP22/2155/SHRI SHRI BALAJ ₹ 2,92,160.00
53232 | GST release note |  | 3 | 59089 | [8 empty] | 59089 | 59088 | 21-04-2023 NEFT/AXISP00383558981/RIUP23/041/SHRI SHRI BALAJI 59088.00
-13130
55283 | Badhai kalan Village Boundary wall work | 2023-03-16 | 4 | 242550 | 22800 | 219750 | 39555 | 259305 | 10988 | 21975 | 39555 |  | 186787 | 195577 | 23-03-2023 NEFT/AXISP00373687999/RIUP22/2680/SHRI SHRI BALAJ 195577.00
55283 | GST release note |  | 4 | 39555 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 39555 | 39555 | 21-04-2023 NEFT/AXISP00383558982/RIUP23/042/SHRI SHRI BALAJI 39555.00
55283 | Badhai kalan Village Boundary wall work | 2023-07-19 | 11 | 80850 | 0 | 80850 | 14553 | 95403 | 4043 | 8085 | 14553 | 0 | 68722 | 71956 | 03-08-2023 NEFT/AXISP00412355118/RIUP23/1352/SHRI SHRI BALAJ 71956.00
55283 | GST release note | 2023-08-28 | 11 | 14553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14553 | 14553 | 29-08-2023 NEFT/AXISP00419117076/RIUP23/1779/SHRI SHRI BALAJI C/PUNB0148000 ₹ 14,553.00
55283 | Badhai kalan Village Boundary wall work | 2025-03-05 | 23 | 80850 | 0 | 80850 | 14553 | 95403 | 4043 | 8085 | 14553 | 0 | 68722 | 56595 | 08-04-2025 NEFT/AXISP00648286720/RIUP24/3350/SHRI SHRI BALAJI C/PUNB0148000 56595.00
55283 | GST release note |  | 23 | 14553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14553
14656
56469 | Karwara village -Pump house work | 2023-04-11 | 5 | 222000 | 35165 | 186835 | 33630 | 220465 | 9342 | 18684 | 33630 |  | 158809 | 166283 | 19-04-2023 19-04-2023 NEFT/AXISP00382928305/SPUP23/0147/SHRI SHRI BALAJ 166283.00
56469 | Karwara village -Pump house work | 2023-05-20 | 7 | 159000 | 0 | 159000 | 28620 | 187620 | 7950 | 15900 | 28620 |  | 135150 | 141510 | 30-05-2023 NEFT/AXISP00393348671/RIUP23/441/SHRI SHRI BALAJI 141510.00
56469 | GST release note |  | 5 | 33630 | 0 | [7 empty] | 33630 | 33630 | 14-06-2023 NEFT/AXISP00398362778/RIUP23/587/SHRI SHRI BALAJI ₹ 33,630.00
56469 | GST release note |  | 7 | 28620 | 0 | [5 empty] | 0 |  | 28620 | 28620 | 28-06-2023 NEFT/AXISP00401332313/RIUP23/862/SHRI SHRI BALAJI 28620.00
-13834
56470 | Lalukheri village -Pump house work | 2023-04-11 | 6 | 222000 | 35165 | 186835 | 33630 | 220465 | 9342 | 18684 | 33630 |  | 158809 | 166283 | 19-04-2023 19-04-2023 NEFT/AXISP00382928304/SPUP23/0148/SHRI SHRI BALAJ 166283.00
56470 | GST release note |  | 6 | 33630 | [8 empty] | 33630 | 33630 | 14-06-2023 NEFT/AXISP00398362779/RIUP23/588/SHRI SHRI BALAJI ₹ 33,630.00
56470 | Lalukheri village -Pump house work | 2023-06-08 | 9 | 159000 | 0 | 159000 | 28620 | 187620 | 7950 | 15900 | 28620 |  | 135150 | 141510 | 19-06-2023 NEFT/AXISP00399545678/RIUP23/723/SHRI SHRI BALAJI 141510.00
56470 | GST release note | 2023-07-18 | 9 | 28620 | [8 empty] | 28620 | 28620 | 25-07-2023 NEFT/AXISP00409091570/RIUP23/1204/SHRI SHRI BALAJ 28620.00
-13834
57523 | kutabi Village Pump House work | 2023-05-20 | 8 | 210000 | 38125 | 171875 | 30937.5 | 202812.5 | 8593.75 | 17187.5 | 30937.5 |  | 146094 | 152968 | 29-05-2023 NEFT/AXISP00393029889/RIUP23/408/SHRI SHRI BALAJI 152968.00
57523 | GST release note |  | 8 | 30938 | [8 empty] | 30938 | 30937 | 28-06-2023 NEFT/AXISP00401332312/RIUP23/861/SHRI SHRI BALAJI 30937.00
57523 | kutabi Village Pump House work | 2023-07-19 | 10 | 151000 |  | 151000 | 27180 | 178180 | 7550 | 15100 | 27180 |  | 128350 | 134390 | 02-08-2023 NEFT/AXISP00412149933/RIUP23/1355/SHRI SHRI BALAJ 134390.00
57523 | GST release note | 2023-08-28 | 10 | 27180 | [8 empty] | 27180 | 27180 | 29-08-2023 NEFT/AXISP00419117074/RIUP23/1778/SHRI SHRI BALAJI C/PUNB0148000 ₹ 27,180.00
-12913
58635 | kutabi VillageBoundry wall work | 2023-07-27 | 12 | 253680 | 0 | 253680 | 45662 | 299342 | 12684 | 25368 | 45662 | 2800 | 212828 | 222975 | 10-08-2023 NEFT/AXISP00414796771/RIUP23/1462/SHRI SHRI BALAJ 222975.00
58635 | GST Release Note | 2023-08-28 | 12 | 45662 | [8 empty] | 45662 | 45662 | 29-08-2023 NEFT/AXISP00419117075/RIUP23/1780/SHRI SHRI BALAJI C/PUNB0148000 ₹ 45,662.00
-10147
59134 | Kamalpur VillageBoundry wall work | 2023-09-02 | 13 | 222000 | 0 | 222000 | 39960 | 261960 | 11100 | 22200 | 39960 | 0 | 188700 | 197580 | 07-09-2023 NEFT/AXISP00422654383/RIUP23/1861/SHRI SHRI BALAJI C/PUNB0148000 197580.00
59134 | GST Release note | 2023-10-20 | 13 | 39960 | [8 empty] | 39960 | 39960 | 01-11-2023 NEFT/AXISP00439227039/RIUP23/2916/SHRI SHRI BALAJI C/PUNB0148000 39960.00
59134 |  | 2024-01-24 | 20 | 120900 |  | 120900 | 21762 | 142662 | 6045 | 12090 | 21762 | 0 | 102765 | 60585 | 05-02-2024 NEFT/AXISP00468222697/RIUP23/4499/SHRI SHRI BALAJI C/PUNB0148000 60585.00
59134 | GST release note |  | 20 | 21762 | [8 empty] | 21762 | 21762 | 06-04-2024 NEFT/AXISP00489186676/RIUP23/5224/SHRI SHRI BALAJI C/PUNB0148000 21762.00
59134 | [15 empty] | TDS deducted 5 %
33300
59403 | Kamalpur Village Boundry Wall work | 2023-09-22 | 14 | 253680 | 15200 | 238480 | 42926 | 281406 | 11924 | 23848 | 42926 | 2800 | 199908 | 199908 | 03-10-2023 NEFT/AXISP00430096874/RIUP23/2428/SHRI SHRI BALAJI C/PUNB0148000 199908.00
59403 | GST Release Note | 2023-10-20 | 14 | 42926 | [8 empty] | 42926 | 42926 | 01-11-2023 NEFT/AXISP00439227038/RIUP23/2917/SHRI SHRI BALAJI C/PUNB0148000 42926.00
59403 | Kamalpur Village Boundry Wall work | 2025-03-08 | 24 | 135012.5 | 34500 | 100513 | 18092 | 118605 | 5025.65 | 5025.65 | 18092 |  | 90462 | 30000 | 16-04-2025 NEFT/AXISP00651859285/RIUP25/0090/SHRI SHRI BALAJI C/PUNB0148000 30000.00
59403 | GST Release Note |  | 24 | 18092 | [8 empty] | 18092
59403 | [15 empty] | TDS deducted 5 %
78554
59741 | Jafarpur Village Pump House work | 2023-10-12 | 15 | 210000 | 0 | 210000 | 37800 | 247800 | 10500 | 10500 | 37800 | 0 | 189000 | 189000 | 17-10-2023 NEFT/AXISP00435127255/RIUP23/2673/SHRI SHRI BALAJI C/PUNB0148000 189000.00
59741 | Jafarpur Village Pump House work | 2023-12-07 | 18 | 114900 | 0 | 114900 | 20682 | 135582 | 5745 | 5745 | 20682 | 0 | 103410 | 37800 | 29-12-2023 NEFT/AXISP00456946532/RIUP23/3950/SHRI SHRI BALAJI C/PUNB0148000 ₹ 37,800.00
59741 | GST Release Note | 2023-10-20 | 15 | 37800 | [8 empty] | 37800 | 103410 | 30-12-2023 NEFT/AXISP00457475298/RIUP23/3666/SHRI SHRI BALAJI C/PUNB0148000 103410.00
59741 |  |  | 18 | 20682 | [8 empty] | 20682 | 20682 | 30-12-2023 NEFT/AXISP00457475298/RIUP23/3666/SHRI SHRI BALAJI C/PUNB0148000 103410.00
59741
59741 | [15 empty] | TDS deducted 5 %
0
59963 | DULEHRA Village Pump House work | 2023-10-27 | 16 | 222000 | 0 | 222000 | 39960 | 261960 | 11100 | 11100 | 39960 | 0 | 199800 | 199800 | 01-11-2023 NEFT/AXISP00439227034/RIUP23/2974/SHRI SHRI BALAJI C/PUNB0148000 199800.00
59963 | GST Release Note | 2023-10-20 | 14 | 39960 | [8 empty] | 39960 | 39960 | 29-12-2023 NEFT/AXISP00456946533/RIUP23/3951/SHRI SHRI BALAJI C/PUNB0148000 ₹ 39,960.00
59963 | DULEHRA Village Pump House work | 2025-02-20 | 22 | 139950 | 0 | 139950 | 25191 | 165141 | 6997.5 | 6997.5 | 25191 | 0 | 125955 | 50000 | 12-03-2025 NEFT/AXISP00632194505/RIUP24/3236/SHRI SHRI BALAJI C/PUNB0148000 50000.00
59963 | GST Release Note |  | 14 | 25191 | [8 empty] | 25191 | 30000 | 16-04-2025 NEFT/AXISP00651859286/RIUP25/0091/SHRI SHRI BALAJI C/PUNB0148000 30000.00
71146
61822 | Safipur Patti village- PH work | 2024-01-17 | 19 | 111000 |  | 111000 | 19980 | 130980 | 5550 | 5550 | 19980 | 0 | 99900 | 99900 | 16-02-2024 NEFT/AXISP00472105151/RIUP23/4442/SHRI SHRI BALAJI C/PUNB0148000 99900.00 | TDS deducted 5 %
61822 | GST |  | 19 | 19980 | [8 empty] | 19980 | 19980 | 23-10-2024 NEFT/AXISP00557269329/RIUP23/5223/SHRI SHRI BALAJI C/PUNB0148000 19980.00
0
66787 | DULEHRA Village Boundary Wall work | 2024-11-21 | 21 | 404600 | 0 | 404600 | 72828 | 477428 | 20230 | 20230 | 72828 | 0 | 364140
66787 | GST Release Note |  |  | 72828 | [8 empty] | 72828
66787 | [15 empty] | 436968
[10 empty] | 353908.65 | 754299.1 | 5600 | 4375818.6 | 3966683 |  | 409135.6
409135.6
Shree Shree Balaji Contractor
2025-04-07
[9 empty] | Hold |  | 353908.65
[9 empty] | Total Debit |  | 0
[9 empty] | Advance/ Surplus |  | 409135.6
[9 empty] | GST Remaining |  | -0.5
[9 empty] | DPR excess Hold |  | 5600