## Subtask Report
Task ID | Village Name | Supply (70%) | [5 empty] | Erection (20%) | [5 empty] | Testing (5%) | [5 empty] | Commissioning (5%)
|  | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount
11358 | Aldi | 150 | 748.45 | 112267.5 | 0 | 0 | 112268.1
12121 | Ambetha Asadpur | 60 | 748.45 | 44907 | 0 | 0 | 44907.24
12481 | Bharsi | 60 | 748.45 | 44907 | 0 | 0 | 44907.24
12867 | Braham Khera | 50 | 748.45 | 37422.5 | 0 | 0 | 37422.7
13251 | Chadhaw | 60 | 748.45 | 44907 | 0 | 0 | 44907.24
13623 | Dudhar | 60 | 748.45 | 44907 | 0 | 0 | 44907.05
13984 | Gujjarpur-fatehpur | 60 | 748.45 | 44907 | 0 | 0 | 44907.24
14363 | Hurmazpur-shahpur | 40 | 748.3 | 29932 | 0 | 0 | 29932
14760 | Islampur-Ghasuli | 60 | 748.45 | 44907 | 0 | 0 | 44907.24
15142 | Issopur-Teel | 60 | 748.45 | 44907 | 0 | 0 | 44907.24
15668 | Kandhla Dehat | 180 | 748.45 | 134721 | 0 | 0 | 134721.14
16076 | Khandrawali | 60 | 748.45 | 44907 | 0 | 0 | 44907.24
16473 | khera-kurtan | 90 | 748.45 | 67360.5 | 0 | 0 | 67360.86
16861 | Malakpur | 60 | 748.45 | 44907 | 0 | 0 | 44907.24
17237 | Mimla Talab | 40 | 748.45 | 29938 | 0 | 0 | 29938.16
17622 | Panjokhera | 40 | 748.45 | 29938 | 0 | 0 | 29938.16
18002 | Rampur Khedi | 60 | 748.45 | 44907 | 0 | 0 | 44907.24
18382 | Rasoolpur Gujran | 40 | 748.45 | 29938 | 0 | 0 | 29938.16
Total |  | 0 | 0 | 920587.5 | 0 | 0 | 920591.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0