## Subtask Report
Task ID | Village Name | Supply (70%) | [5 empty] | Erection (20%) | [5 empty] | Testing (5%) | [5 empty] | Commissioning (5%)
|  | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount
12107 | Ambetha Asadpur | 113.7 | 2846.58 | 323656.146 | 80.25 | 228438.04 | 95218.11
13237 | Chadhaw | 113.7 | 2846.58 | 323656.146 | 111.35 | 316966.68 | 6689.47
13609 | Dudhar | 113.7 | 3985.21 | 453118.377 | 0 | 0 | 453118.6 | 113.7 | 1138.63 | 129462.231 | 0 | 0 | 129462.46 | 113.7 | 284.66 | 32365.842 | 0 | 0 | 32365.61 | 113.7 | 284.66 | 32365.842 | 0 | 0 | 32365.61
13970 | Gujjarpur-fatehpur | 113.7 | 2846.58 | 323656.146 | 132.7 | 377741.17 | -54085.02
14348 | Hurmazpur-shahpur | 113.7 | 2846.5 | 323647.05 | 111.8 | 318238.7 | 5408.35
14746 | Islampur-Ghasuli | 113.7 | 2846.58 | 323656.146 | 0 | 0 | 323656.15
15128 | Issopur-Teel | 113.7 | 2846.58 | 323656.146 | 113.7 | 323656.15 | 0
15654 | Kandhla Dehat | 341.1 | 2846.58 | 970968.438 | 122.29 | 348108.27 | 622860.17
16062 | Khandrawali | 113.7 | 2846.58 | 323656.146 | 0 | 0 | 323656.15
16459 | khera-kurtan | 113.7 | 2846.58 | 323656.146 | 107.25 | 305295.71 | 18360.44
16847 | Malakpur | 113.7 | 2846.58 | 323656.146 | 108 | 307430.64 | 16225.51
17223 | Mimla Talab | 113.7 | 2846.58 | 323656.146 | 132.7 | 377741.17 | -54085.02
17607 | Panjokhera | 113.7 | 2846.58 | 323656.146 | 105.65 | 300741.18 | 22914.97
17988 | Rampur Khedi | 113.7 | 2846.58 | 323656.146 | 109.4 | 311415.85 | 12240.3
18368 | Rasoolpur Gujran | 113.7 | 2846.58 | 323656.146 | 125.4 | 356961.13 | -33304.98
Total |  | 0 | 0 | 5631607.67 | 0 | 3872734.69 | 1758873.2 | 0 | 0 | 129462.23 | 0 | 0 | 129462.46 | 0 | 0 | 32365.84 | 0 | 0 | 32365.61 | 0 | 0 | 32365.84 | 0 | 0 | 32365.61