## Subtask Report
Task ID | Village Name | Supply (70%) | [5 empty] | Erection (20%) | [5 empty] | Testing (5%) | [5 empty] | Commissioning (5%)
|  | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount
19110 | Bhanera Jat | 23 | 60687.09 | 1395803.07 | 23 | 1395803.02 | 0 | 23 | 17339.17 | 398800.91 | 23 | 398800.86 | 0 | 23 | 4334.79 | 99700.17 | 0 | 0 | 99700.22 | 23 | 4334.79 | 99700.17 | 0 | 0 | 99700.22
19493 | Dhanena | 20 | 60687.09 | 1213741.8 | 20 | 1213741.76 | 0 | 20 | 17339.17 | 346783.4 | 0 | 0 | 346783.36 | 20 | 4334.79 | 86695.8 | 0 | 0 | 86695.84 | 20 | 4334.79 | 86695.8 | 0 | 0 | 86695.84
19876 | Goharni | 37 | 60687.09 | 2245422.33 | 37 | 2245422.26 | 0 | 37 | 17339.17 | 641549.29 | 0 | 0 | 641549.22 | 37 | 4334.79 | 160387.23 | 0 | 0 | 160387.3 | 37 | 4334.79 | 160387.23 | 0 | 0 | 160387.3
21019 | Jandheri | 16 | 60687.09 | 970993.44 | 16 | 970993.41 | 0 | 16 | 17339.17 | 277426.72 | 0 | 0 | 277426.69 | 16 | 4334.79 | 69356.64 | 0 | 0 | 69356.67 | 16 | 4334.79 | 69356.64 | 0 | 0 | 69356.67
21405 | Kanjarheri | 20 | 60687.09 | 1213741.8 | 20 | 1213741.76 | 0 | 20 | 17339.17 | 346783.4 | 0 | 0 | 346783.36 | 20 | 4334.79 | 86695.8 | 0 | 0 | 86695.84 | 20 | 4334.79 | 86695.8 | 0 | 0 | 86695.84
21788 | Karori Mehrampur | 23 | 60687.09 | 1395803.07 | 23 | 1395803.02 | 0 | 23 | 17339.17 | 398800.91 | 0 | 0 | 398800.86 | 23 | 4334.79 | 99700.17 | 0 | 0 | 99700.22 | 23 | 4334.79 | 99700.17 | 0 | 0 | 99700.22
22546 | Khanpur | 20 | 60687.09 | 1213741.8 | 20 | 1213741.76 | 0 | 20 | 17339.17 | 346783.4 | 0 | 0 | 346783.36 | 20 | 4334.79 | 86695.8 | 0 | 0 | 86695.84 | 20 | 4334.79 | 86695.8 | 0 | 0 | 86695.84
22921 | Kherapatti Bhikki Mazra | 20 | 60687.09 | 1213741.8 | 0 | 0 | 1213741.76 | 20 | 17339.17 | 346783.4 | 0 | 0 | 346783.36 | 20 | 4334.79 | 86695.8 | 0 | 0 | 86695.84 | 20 | 4334.79 | 86695.8 | 0 | 0 | 86695.84
Total |  | 0 | 0 | 10862989.11 | 0 | 9649246.99 | 1213741.76 | 0 | 0 | 3103711.43 | 0 | 398800.86 | 2704910.21 | 0 | 0 | 775927.41 | 0 | 0 | 775927.77 | 0 | 0 | 775927.41 | 0 | 0 | 775927.77