## Sheet1
Name of Work-
Cover Agreement No-
Name Of Contractor-
Name Of TPI Agency-
Name Of Division- | Muzaffarnagar
Name Of Village- | Singara
Block- | Unn
Scheme Id
Measurement Book / Page No-
Date
District | Muzaffarnagar
S.N. | DESCRIPTION | UNIT | QTY. | RATE | BOQ Amount | Previous Billed qty | Previous Billing Amount | In this RA Bill qty | In this RA Billing Amount | Cummulative Billed qty | Commulative billed Amount | Variation Qty | Variation Qty | Remark
1.01 | All the works including Hydrological survey, topographical survey, Design charges including preparation and approval of DPR | LS | 1 | 268000 | 268000 | 1 | 268000 |  | 0 | 1 | 268000 | 0 | 0
2 | Drilling of Borehole for Tube well construction by DC/RC/DTH Rig Machine including transportation, erection, dismantling of Rig and associated T&P complete in all respect including required all material labor etc. |  |  |  | 0 | [7 empty] | 0
2.01 | Transportation, Installation Dismantling of Rig machine and logging of bore hole | Job | 1 | 227796.32 | 227796.32 | [7 empty] | 0
| Supply and Installation | 80% | 1 | 182237.056 | 182237.056 | 1 | 182237.056 |  | 0 | 1 | 182237.056 | 0 | 0
| On water test report | 5% | 1 | 11389.816 | 11389.816 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Post Delivery test | 5% | 1 | 11389.816 | 11389.816 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On tasting | 5% | 1 | 11389.816 | 11389.816 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1 | 11389.816 | 11389.816 |  | 0 |  | 0 | 0 | 0 | 0 | 0
2.02 | Tube well construction |  |  |  | 0 | [7 empty] | 0
2.03 | DC/RC Drilling up to 100Mtr. |  |  |  | 0 | [7 empty] | 0
2.06 | 500 MMØ | Mtr. | 34 | 2147.42 | 73012.28 | [7 empty] | 0
| Supply and Installation | 80% | 34 | 1717.936 | 58409.824 | 25 | 42948.4 |  | 0 | 25 | 42948.4 | 0 | 0
| On water test report | 5% | 34 | 107.371 | 3650.614 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Post Delivery test | 5% | 34 | 107.371 | 3650.614 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On tasting | 5% | 34 | 107.371 | 3650.614 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 34 | 107.371 | 3650.614 |  | 0 |  | 0 | 0 | 0 | 0 | 0
2.07 | 600 MMØ | Mtr. | 66 | 2561.92 | 169086.72 | [7 empty] | 0
| Supply and Installation | 80% | 66 | 2049.536 | 135269.376 | 75 | 153715.2 |  | 0 | 75 | 153715.2 | 9 | 18445.824
| On water test report | 5% | 66 | 128.096 | 8454.336 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Post Delivery test | 5% | 66 | 128.096 | 8454.336 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On tasting | 5% | 66 | 128.096 | 8454.336 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 66 | 128.096 | 8454.336 |  | 0 |  | 0 | 0 | 0 | 0 | 0
2.08 | DC/RC Drilling from 101 MT. To 200 Mtr.Deep |  |  |  | 0 | [7 empty] | 0
2.1 | 500 MMØ | Mtr. | 50 | 2426.49 | 121324.5 | [7 empty] | 0
| Supply and Installation | 80% | 50 | 1941.192 | 97059.6 | 60 | 116471.52 |  | 0 | 60 | 116471.52 | 10 | 19411.92
| On water test report | 5% | 50 | 121.3245 | 6066.225 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Post Delivery test | 5% | 50 | 121.3245 | 6066.225 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On tasting | 5% | 50 | 121.3245 | 6066.225 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 50 | 121.3245 | 6066.225 |  | 0 |  | 0 | 0 | 0 | 0 | 0
3 | Tubwell Assembly: |  |  |  | 0 | [7 empty] | 0
3.01 | MSERW plain pipe,As per IS 4270 |  |  |  | 0 | [7 empty] | 0
3.04 | 200 MMØ | Mtr. | 44 | 2546.94 | 112065.36 | [7 empty] | 0
| Supply and Installation | 80% | 44 | 2037.552 | 89652.288 | 31.87 | 64936.7822 |  | 0 | 31.87 | 64936.7822 | 0 | 0
| On water test report | 5% | 44 | 127.347 | 5603.268 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Post Delivery test | 5% | 44 | 127.347 | 5603.268 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On tasting | 5% | 44 | 127.347 | 5603.268 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 44 | 127.347 | 5603.268 |  | 0 |  | 0 | 0 | 0 | 0 | 0
3.05 | 300 MMØ | Mtr. | 60 | 3795.44 | 227726.4 | [7 empty] | 0
| Supply and Installation | 80% | 60 | 3036.352 | 182181.12 | 66.51 | 201947.7715 |  | 0 | 66.51 | 201947.7715 | 6.51 | 19766.6515
| On water test report | 5% | 60 | 189.772 | 11386.32 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Post Delivery test | 5% | 60 | 189.772 | 11386.32 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On tasting | 5% | 60 | 189.772 | 11386.32 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 60 | 189.772 | 11386.32 |  | 0 |  | 0 | 0 | 0 | 0 | 0
3.06 | MSERW Pipe slotted pipe as per IS 8110 |  |  |  | 0 | [7 empty] | 0
3.09 | 200 MMØ | Mtr. | 36 | 3829.2 | 137851.2 | [7 empty] | 0
| Supply and Installation | 80% | 36 | 3063.36 | 110280.96 | 42.14 | 129089.9904 |  | 0 | 42.14 | 129089.9904 | 6.14 | 18809.0304
| On water test report | 5% | 36 | 191.46 | 6892.56 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Post Delivery test | 5% | 36 | 191.46 | 6892.56 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On tasting | 5% | 36 | 191.46 | 6892.56 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 36 | 191.46 | 6892.56 |  | 0 |  | 0 | 0 | 0 | 0 | 0
3.11 | MS fittings such as clamp, bail plug, reducer, well cap, girder & support structure | LS | 1 | 32256.25 | 32256.25 | [7 empty] | 0
| Supply and Installation | 80% | 1 | 25805 | 25805 | 1 | 25805 |  | 0 | 1 | 25805 | 0 | 0
| On water test report | 5% | 1 | 1612.8125 | 1612.8125 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Post Delivery test | 5% | 1 | 1612.8125 | 1612.8125 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On tasting | 5% | 1 | 1612.8125 | 1612.8125 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1 | 1612.8125 | 1612.8125 |  | 0 |  | 0 | 0 | 0 | 0 | 0
3.12 | MS fittings such as ring & centre guide | RM | 104 | 471.11 | 48995.44 | [7 empty] | 0
| Supply and Installation | 80% | 104 | 376.888 | 39196.352 | 140.72 | 53035.6794 |  | 0 | 140.72 | 53035.6794 | 36.72 | 13839.3274
| On water test report | 5% | 104 | 23.5555 | 2449.772 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Post Delivery test | 5% | 104 | 23.5555 | 2449.772 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On tasting | 5% | 104 | 23.5555 | 2449.772 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 104 | 23.5555 | 2449.772 |  | 0 |  | 0 | 0 | 0 | 0 | 0
4 | Lowering of above assembly with welding of parts complete in all respect with all required material, T&P, labour, etc. |  |  |  | 0 | [7 empty] | 0
4.01 | Lowering up to 100 Mtr. Deep |  |  |  | 0 | [7 empty] | 0
4.04 | 200 MMØ MSERW Plane/Slotted Pipe | Mtr. | 40 | 421.49 | 16859.6 | [7 empty] | 0
| Supply and Installation | 80% | 40 | 337.192 | 13487.68 | 33.24 | 11208.2621 |  | 0 | 33.24 | 11208.2621 | 0 | 0
| On water test report | 5% | 40 | 21.0745 | 842.98 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Post Delivery test | 5% | 40 | 21.0745 | 842.98 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On tasting | 5% | 40 | 21.0745 | 842.98 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 40 | 21.0745 | 842.98 |  | 0 |  | 0 | 0 | 0 | 0 | 0
4.05 | 300 MMØ MSERW Plain/Slotted Pipe | Mtr. | 60 | 485.42 | 29125.2 | [7 empty] | 0
| Supply and Installation | 80% | 60 | 388.336 | 23300.16 | 66.71 | 25905.8946 |  | 0 | 66.71 | 25905.8946 | 6.71 | 2605.7346
| On water test report | 5% | 60 | 24.271 | 1456.26 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Post Delivery test | 5% | 60 | 24.271 | 1456.26 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On tasting | 5% | 60 | 24.271 | 1456.26 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 60 | 24.271 | 1456.26 |  | 0 |  | 0 | 0 | 0 | 0 | 0
4.06 | Lowering from 101 Mtr. To 200 Mtr. Deep |  |  |  | 0 | [7 empty] | 0
4.08 | 200 MMØ MSERW Plane/Slotted Pipe | Mtr. | 40 | 498.59 | 19943.6 | [7 empty] | 0
| Supply and Installation | 80% | 40 | 398.872 | 15954.88 | 40.7 | 16234.0904 |  | 0 | 40.7 | 16234.0904 | 0.7 | 279.2104
| On water test report | 5% | 40 | 24.9295 | 997.18 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Post Delivery test | 5% | 40 | 24.9295 | 997.18 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On tasting | 5% | 40 | 24.9295 | 997.18 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 40 | 24.9295 | 997.18 |  | 0 |  | 0 | 0 | 0 | 0 | 0
5 | Supplying and unconsolidated packing of gravel with suitable size | Cum | 43 | 7491 | 322113 | [7 empty] | 0
| Supply and Installation | 80% | 43 | 5992.8 | 257690.4 | 42 | 251697.6 |  | 0 | 42 | 251697.6 | 0 | 0
| On water test report | 5% | 43 | 374.55 | 16105.65 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Post Delivery test | 5% | 43 | 374.55 | 16105.65 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On tasting | 5% | 43 | 374.55 | 16105.65 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 43 | 374.55 | 16105.65 |  | 0 |  | 0 | 0 | 0 | 0 | 0
6 | Development of Tube well |  |  |  | 0 | [7 empty] | 0
6.03 | Transportation, Installation Dismantling of 250/400/600 PSI Compressor | Job | 1 | 90651.09 | 90651.09 | [7 empty] | 0
| Supply and Installation | 80% | 1 | 72520.872 | 72520.872 | 1 | 72520.872 |  | 0 | 1 | 72520.872 | 0 | 0
| On water test report | 5% | 1 | 4532.5545 | 4532.5545 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Post Delivery test | 5% | 1 | 4532.5545 | 4532.5545 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On tasting | 5% | 1 | 4532.5545 | 4532.5545 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1 | 4532.5545 | 4532.5545 |  | 0 |  | 0 | 0 | 0 | 0 | 0
6.04 | Charges for Development by 250 PSI Compressor per hour | Hr. | 35 | 3640.63 | 127422.05 | [7 empty] | 0
| Supply and Installation | 80% | 35 | 2912.504 | 101937.64 | 30 | 87375.12 |  | 0 | 30 | 87375.12 | 0 | 0
| On water test report | 5% | 35 | 182.0315 | 6371.1025 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Post Delivery test | 5% | 35 | 182.0315 | 6371.1025 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On tasting | 5% | 35 | 182.0315 | 6371.1025 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 35 | 182.0315 | 6371.1025 |  | 0 |  | 0 | 0 | 0 | 0 | 0
6.09 | Transportation, Installation Dismantling of 1/3 Cusec OP Unit and Yield test, water test | Job | 1 | 113339.83 | 113339.83 | [7 empty] | 0
| Supply and Installation | 80% | 1 | 90671.864 | 90671.864 | 1 | 90671.864 |  | 0 | 1 | 90671.864 | 0 | 0
| On water test report | 5% | 1 | 5666.9915 | 5666.9915 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Post Delivery test | 5% | 1 | 5666.9915 | 5666.9915 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On tasting | 5% | 1 | 5666.9915 | 5666.9915 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1 | 5666.9915 | 5666.9915 |  | 0 |  | 0 | 0 | 0 | 0 | 0
6.1 | Charges for Development of TW by 1 cusec OP Unit | Hr. | 70 | 993.24 | 69526.8 | [7 empty] | 0
| Supply and Installation | 80% | 70 | 794.592 | 55621.44 | 64.25 | 51052.536 |  | 0 | 64.25 | 51052.536 | 0 | 0
| On water test report | 5% | 70 | 49.662 | 3476.34 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Post Delivery test | 5% | 70 | 49.662 | 3476.34 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On tasting | 5% | 70 | 49.662 | 3476.34 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 70 | 49.662 | 3476.34 |  | 0 |  | 0 | 0 | 0 | 0 | 0
7 | SITC of Pumping plant including pumps with motors starter, pannel, cable, complete in all respect with all required material T&P labour etc. |  |  |  | 0 | [7 empty] | 0
7.1 | 20 HP | Nos. | 1 | 295145.4 | 295145.4 | [7 empty] | 0
| On supply | 70% | 1 | 206601.78 | 206601.78 | 1 | 206601.78 |  | 0 | 1 | 206601.78 | 0 | 0
| Supply of Cable | 10% | 1 | 29514.54 | 29514.54 | 1 | 29514.54 |  | 0 | 1 | 29514.54 | 0 | 0
| On Erection | 15% | 1 | 44271.81 | 44271.81 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1 | 14757.27 | 14757.27 |  | 0 |  | 0 | 0 | 0 | 0 | 0
7.14.5 | Pressure gauge & Depth gauge with necessary fitting | Nos | 1 | 7440 | 7440 | [7 empty] | 0
| On supply | 70% | 1 | 5208 | 5208 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Erection | 20% | 1 | 1488 | 1488 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On testing | 5% | 1 | 372 | 372 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1 | 372 | 372 |  | 0 |  | 0 | 0 | 0 | 0 | 0
9.03 | Check Valve PN 1.0 DPCV dia 100 mm | Nos. | 1 | 27486.78 | 27486.78 | [7 empty] | 0
| On supply | 70% | 1 | 19240.746 | 19240.746 | 1 | 19240.746 |  | 0 | 1 | 19240.746 | 0 | 0
| On Erection | 20% | 1 | 5497.356 | 5497.356 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On testing | 5% | 1 | 1374.339 | 1374.339 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1 | 1374.339 | 1374.339 |  | 0 |  | 0 | 0 | 0 | 0 | 0
9.06 | Dismantling Joint PN 1.0 dia 100 mm | Nos. | 4 | 3919.21 | 15676.84 | [7 empty] | 0
| On supply | 70% | 4 | 2743.447 | 10973.788 | 2 | 5486.894 |  | 0 | 2 | 5486.894 | 0 | 0
| On Erection | 20% | 4 | 783.842 | 3135.368 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On testing | 5% | 4 | 195.9605 | 783.842 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 4 | 195.9605 | 783.842 |  | 0 |  | 0 | 0 | 0 | 0 | 0
9.09 | SITC of Chain Pulley Blocks |  |  |  | 0 | [7 empty] | 0
9.11 | 2 Tonne | Nos. | 1 | 58362.38 | 58362.38 | [7 empty] | 0
| On supply | 70% | 1 | 40853.666 | 40853.666 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Installation of Chain Pulley Blocks | 20% | 1 | 11672.476 | 11672.476 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On tasting | 5% | 1 | 2918.119 | 2918.119 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1 | 2918.119 | 2918.119 |  | 0 |  | 0 | 0 | 0 | 0 | 0
13.06 | 100 mm Dia size ‐ MS pipe | Mtr. | 47 | 1565.12 | 73560.64 | [7 empty] | 0
| On supply | 70% | 47 | 1095.584 | 51492.448 | 47 | 51492.448 |  | 0 | 47 | 51492.448 | 0 | 0
| Installation of MS pipe | 20% | 47 | 313.024 | 14712.128 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On testion | 5% | 47 | 78.256 | 3678.032 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 47 | 78.256 | 3678.032 |  | 0 |  | 0 | 0 | 0 | 0 | 0
13.07.5 | Process |  |  |  | 0 | [7 empty] | 0
non BOQ -03 | chlorinating system with doser Elctronic Type | Nos | 1 | 26000 | 26000 | [7 empty] | 0
| On supply | 70% | 1 | 18200 | 18200 | 1 | 18200 |  | 0 | 1 | 18200 | 0 | 0
| On Erection | 20% | 1 | 5200 | 5200 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On testing | 5% | 1 | 1300 | 1300 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1 | 1300 | 1300 |  | 0 |  | 0 | 0 | 0 | 0 | 0
56 | Electromagnetic flow meters |  |  |  | 0 | [7 empty] | 0
56.01 | 150mm EMF | Nos. | 1 | 149820 | 149820 | [7 empty] | 0
| On supply | 70% | 1 | 104874 | 104874 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Erection | 20% | 1 | 29964 | 29964 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On testing | 5% | 1 | 7491 | 7491 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1 | 7491 | 7491 |  | 0 |  | 0 | 0 | 0 | 0 | 0
20 | SITC of Solar power plant (for complete plant ) including solar pannel, Structure, invertor etc. complete in all respect with required material, T&P labour | KW | 30 | 86695.84 | 2600875.2 | [7 empty] | 0
| On supply | 70% | 30 | 60687.088 | 1820612.64 | 30 | 1820612.64 |  | 0 | 30 | 1820612.64 | 0 | 0
| On Erection | 20% | 30 | 17339.168 | 520175.04 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On testing | 5% | 30 | 4334.792 | 130043.76 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 30 | 4334.792 | 130043.76 |  | 0 |  | 0 | 0 | 0 | 0 | 0
19 | Internal electrificaton of tube well | LS | 30 | 19976 | 599280 | [7 empty] | 0
49 | Installation of suitable capacity simple T.W. automation system to control operation of the pumping plant with respect to high/low water level in OHT iwith RTU panel , 7" HMI screen , surge device including enrgy meter inside the pump house with arrangement for communication of data with GSM and GPRS system to show required parameters including all accessories etc. complete in all respect as per instructions of Engineer ‐in –charge. | Job | 1 | 374550 | 374550 | [7 empty] | 0
| On supply | 70% | 1 | 262185 | 262185 | 1 | 262185 |  | 0 | 1 | 262185 | 0 | 0
| On Erection | 20% | 1 | 74910 | 74910 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On testing | 5% | 1 | 18727.5 | 18727.5 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1 | 18727.5 | 18727.5 |  | 0 |  | 0 | 0 | 0 | 0 | 0
Additional Item | Battery 150AH 12V | LS |  | 15000 | 0 | [7 empty] | 0
| On supply | 70% | 1 | 10500 | 10500 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Erection | 20% | 1 | 3000 | 3000 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On testing | 5% | 1 | 750 | 750 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1 | 750 | 750 |  | 0 |  | 0 | 0 | 0 | 0 | 0
61 | Cabling- complete cabling for tubewell inlcuding all power and controlcables of all equipments at pumphouse and OHT | Nos. | 1 | 59928 | 59928 | [7 empty] | 0
| On supply | 70% | 1 | 41949.6 | 41949.6 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Erection | 20% | 1 | 11985.6 | 11985.6 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On testing | 5% | 1 | 2996.4 | 2996.4 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1 | 2996.4 | 2996.4 |  | 0 |  | 0 | 0 | 0 | 0 | 0
63 | Elec. Testing- Installation testing and commissioning | Nos. | 1 | 59928 | 59928 | [7 empty] | 0
| On supply | 70% | 1 | 41949.6 | 41949.6 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Erection | 20% | 1 | 11985.6 | 11985.6 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On testing | 5% | 1 | 2996.4 | 2996.4 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1 | 2996.4 | 2996.4 |  | 0 |  | 0 | 0 | 0 | 0 | 0
64 | Additional Work |  |  |  | 0 | [7 empty] | 0
65 | DG Set Rate |  |  |  | 0 | [7 empty] | 0
30 | Supply of DG set 30 KVA | KVA | 1 | 405000 | 405000 | [7 empty] | 0
| On supply | 70% | 1 | 283500 | 283500 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Erection | 20% | 1 | 81000 | 81000 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On testing | 5% | 1 | 20250 | 20250 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1 | 20250 | 20250 |  | 0 |  | 0 | 0 | 0 | 0 | 0
68 | cabling work for DG Set | LS | 1 | 5000 | 5000 | [7 empty] | 0
21 | Construction of 1.3 m high and 115mm thick boundary wall with 230 mmx230 mm thick pillar made in Brick masonry in 1 cement and 4 sand mortar, the spacing between two pillar should not be more than 3.0 m c/c and the depth of foundation should not be less than 0.60m, at the site of water works as per departmental type design and drawing, and, as per specifications given in the bid document including supply of all materials, labour T&P etc.for proper completion of work as per instructions of Engineer ‐in ‐ charge. (Drawing No.D‐1) | Rmt | 113.7 | 5693.16 | 647312.292 | [7 empty] | 0
| Excvation of boundary wall | 10% | 113.7 | 569.316 | 64731.2292 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| PCC of foundation | 10% | 113.7 | 569.316 | 64731.2292 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Supply of row material | 50% | 113.7 | 2846.58 | 323656.146 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Construction of boundary wall | 20% | 113.7 | 1138.632 | 129462.4584 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Finishing & other work | 10% | 113.7 | 569.316 | 64731.2292 |  | 0 |  | 0 | 0 | 0 | 0 | 0
22 | Supply and fixing of 3.6 m x 1.20 m MS gate including fabrication and supply of steel and construction of bounary wall pillars of size 1.35mx0.23mx0.23m with ornamental brick work 115mm th. around RCC, as per departmental type design and drawing (Drawing No. D‐1) and as per specifications laid down in the bid document, including supply of all material, labour,T&P etc.required for proper completion of work as per instructions of Engineer‐in‐charge. | No. | 1 | 51937.6 | 51937.6 | [7 empty] | 0
| On supply | 70% | 1 | 36356.32 | 36356.32 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On Erection | 20% | 1 | 10387.52 | 10387.52 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On testing | 5% | 1 | 2596.88 | 2596.88 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1 | 2596.88 | 2596.88 |  | 0 |  | 0 | 0 | 0 | 0 | 0
23 | Supply and fixing of 1.2m wide MS wicket gate including fabrication and supply of steel and construction of boundary wall pillars etc. as per specifications laid down in the bid document, including supply of all material, labour,T&P etc.required for proper completion of work as per instructions of Engineer‐in‐ charge. | No. | 1 | 18977.2 | 18977.2 | [7 empty] | 0
| Supply of MS gate | 70% | 1 | 13284.04 | 13284.04 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Erectiin of MS gate | 30% | 1 | 5693.16 | 5693.16 |  | 0 |  | 0 | 0 | 0 | 0 | 0
24 | Construction of Interlocking pavement for approach to water works, as per departmental type design and drawing and as per specifications laid down in the bid document, including supply of all materials , labour, T&P etc.required for proper completion of work as per instructions of Engineer ‐in ‐charge. | Sqm. | 66 | 1069.22 | 70568.52 | [7 empty] | 0
| Supply of MS gate | 70% | 66 | 748.454 | 49397.964 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Erectiin of MS gate | 30% | 66 | 320.766 | 21170.556 |  | 0 |  | 0 | 0 | 0 | 0 | 0
25 | Construction of granular sub base by providing coarse grade materials, spreading in uniform layers including watering and compaction complete. | Cum | 12 | 2796.64 | 33559.68 |  | 0 |  | 0 | 0 | 0 | 0 | 0
26 | Construction of WBM by providing grade materials, spreading in uniform layers including watering and compaction complete. | Cum | 8 | 3025.37 | 24202.96 |  | 0 |  | 0 | 0 | 0 | 0 | 0
28 | Provision for inside semicircular drain 200mm dia including supply of all materials, labour and T & P etc. complete. | Rmt | 113.7 | 1605.21 | 182512.377 |  | 0 |  | 0 | 0 | 0 | 0 | 0
46 | Water recharge Mechanism within the water works campus | Sqm | 4 | 67329.82 | 269319.28 |  | 0 |  | 0 | 0 | 0 | 0 | 0
Additional Item | Constructaion of DG Set Foundation | LS |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
29 | Provide all materials, labour, T&P etc. complete and construct Pump house size (3.6x3.0x3.0)m Chlorinating room size (2.5x1.8x3.0)m as per departmental type design and drawing (drawing no‐D‐2) and as per the specifications for civil work given in the bid document, including supply of all material, labour and T&P etc complete as per instructions of Engineer ‐in ‐ charge. | Job | 1 | 610266.8 | 610266.8 | [7 empty] | 0
| Foundation up to plith lavel | 25% | 1 | 152566.7 | 152566.7 | 1 | 152566.7 |  | 0 | 1 | 152566.7 | 0 | 0
| Completion of superstructure & wall with doors & window | 35% | 1 | 213593.38 | 213593.38 | 1 | 213593.38 |  | 0 | 1 | 213593.38 | 0 | 0
| On fionishing civil work | 20% | 1 | 122053.36 | 122053.36 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On finishing electrical installation | 20% | 1 | 122053.36 | 122053.36 |  | 0 |  | 0 | 0 | 0 | 0 | 0
31 | Provide all materials, labour, T&P etc. complete and constructed Bye‐pass chamber for pump house ( 1000 (L) x 1000 (W) x 1150 (H) mm ) drawing (drawing no.D‐3) and as per the specifications for civil work given in the bid document, including supply of all material, labour and T&P etc complete as per instructions of Engineer ‐in ‐charge. | No. | 1 | 17678.76 | 17678.76 | [7 empty] | 0
32 | Supply of all materials labour T&P etc. for complete construction of R.C.C. Over Head Tank of following capacity and staging above ground level with main components, including cost of soil testing and assuming bearing capacity of soil as 8 MT, with supply of design and drawings.All the water retaining components of OHT shall be casted in M‐30 concrete and minimum grade of concrete of foundation and staging should be M‐25 with approved cement, coarse sand and stone grit as per I.S. 11682 and I.S.456Seismic effects and wind load should be taken into consideration as per I.S. 1893 for earthquake resistance and I.S. 875 part‐III for wind load on structure and including 1M wide RCC staircase, 1 m wide R.C.C. M30 balcony, M.S. ladder made of 50x50x6 mm angle section and 20mm plain M.S. bars with hand rails of 20mm medium class G.I. pipes, One aluminum ladder inside the tank from top dome to bottom dome, R.C.C. railing with 20mm dia medium class G.I.pipe (in 3 rows) on both sides of stair case, supported on 50x50x6mm M.S. angle section, spaced at intervals not more than 1.5m, Proper ventilator at top dome in circular shape of 1.2 m dia, Water level indicator fabricated with sensor connecting to automation, Lightening conductor as per I.S.S.2309 or its latest amendments of latest electricity rules, consisting of proper elevation rod with 5 or more fork points as prescribed in ISS 2309‐1969 and ISS 3013‐1966, C.I. manhole of min 60x60cm size with locking arrangement, Supply, fixing, jointing of D.I.D/F Pipes of appropriate size with D.I.D/F specials conforming to IS 8329/2000 as vertical pipes for inlet, outlet, overflow and washout as per latest / relevant I.S. specifications with all jointing materials for proper completion of work, Construction of bed blocks in 1:2:4 PCC with cement, coarse sand and approved stone grit , Construction of washout / overflow chamber and chambers for sluice / butter fly valves as per departmental type design and drawing, Supply of 200 mm dia PVC pipe as per I.S.‐ 4985/2000 for disposal of water from overflow and washout chamber to suitable point outside the water works compound, Painting of all concrete surface and steel pipe works with three coats |  |  |  | 0 | [7 empty] | 0
32.29 | 250 KL 14 M Staging | Job | 1 | 4758657.75 | 4758657.75 | [7 empty] | 0
| foundation upto GL | 20% | 1 | 951731.55 | 951731.55 | 1 | 951731.55 |  | 0 | 1 | 951731.55 | 0 | 0
| Completion of staging and stair | 20% | 1 | 951731.55 | 951731.55 | 0.85 | 808971.8175 |  | 0 | 0.85 | 808971.8175 | 0 | 0
| Completion of ring beam/bottom dome/conical dome with balcony | 20% | 1 | 951731.55 | 951731.55 |  | 0 | 1 | 951731.55 | 1 | 951731.55 | 0 | 0
| Completion of cylindrical wall | 15% | 1 | 713798.6625 | 713798.6625 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Completion of roof dome | 10% | 1 | 95173.155 | 95173.155 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Completion of piping arrangement asceding ladder, finishing work including all appurtenances | 15% | 1 | 142759.7325 | 142759.7325 |  | 0 |  | 0 | 0 | 0 | 0 | 0
33 | Excavation of earth in ordinary soil (loam, clay or sand) for pipe line and rising main trenches including lift upto 1.50 m and lead upto 50 m and refilling watering, ramming of the excavated earth into the trench and also disposal of surplus earth upto 50m from the center of the trenches including supply of all material labour, T&P etc complete as per instructions of Engineer ‐in ‐charge. |  |  |  | 0 | [7 empty] | 0
34 | ordinary soil | Cum. | 4747.39 | 199.55 | 947341.6745 | 2204.21 | 439850.1055 |  | 0 | 2204.21 | 439850.1055 | 0 | 0
35 | Mixed soil with Kankar | Cum. | 1779.74 | 231.91 | 412739.5034 |  | 0 |  | 0 | 0 | 0 | 0 | 0
40 | Supply of following sizes (D.I.) pipes for rising main/distribution system conforming to latest/relevant I.S. 8329/2000 Specifications with all jointing materials such as specials conforming to latest /relevant I.S. specifications, suitable for D.I pipes, as per IS‐1239 /2000 and IS 8329/2000 or their latest amendment including F.O.R. destination and all taxes and insurance etc. with loading, unloading and Carting up to site of work, also including specials for these pipes and lowering them into the trenches and laying true to alignment and gradient and jointing etc. complete (including testing of pipe lines and cutting of pipes for making up the length but excluding the cost of trenches).all complete as per instructions of Engineer ‐in ‐ charge. |  |  |  | 0 | [7 empty] | 0
40.11 | 150 mm dia K‐7 | Rmt | 30 | 1495.68 | 44870.4 |  | 0 |  | 0 | 0 |  |  | 0
| On supply & delivery | 65% | 30 | 972.192 | 29165.76 | 30 | 29165.76 |  | 0 | 30 | 29165.76 | 0 | 0
| With Held Amount | 5% | 30 | 74.784 | 2243.52 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on completion/laying/jointing | 20% | 30 | 299.136 | 8974.08 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on testing | 5% | 30 | 74.784 | 2243.52 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 30 | 74.784 | 2243.52 |  | 0 |  | 0 | 0 | 0 | 0 | 0
41 | Supply of following sizes pipes for distribution system conforming to latest/ relevant I.S. 4984/1995 Specifications with all jointing materials and specials conforming to latest/relevant I.S. specifications including F.O.R. destination and all taxes and insurance etc. with loading, unloading and Carting up to site of work, also including specials for these pipes and lowering them into the trenches and laying true to alignment and gradient and jointing etc. complete (including testing of pipe lines and cutting of pipes for making up the length but excluding the cost of trenches) all complete as per instructions of Engineer ‐in ‐ charge. |  |  |  | 0 | [7 empty] | 0
non boq item-4 | 200 mm dia HDPE Pipe PN‐6: Class PE‐100 | Rmt | 22 | 914.8 | 20125.6 | [7 empty] | 0
| On supply & delivery | 65% | 22 | 594.62 | 13081.64 | 22 | 13081.64 |  | 0 | 22 | 13081.64 | 0 | 0
| With Held Amount | 5% | 22 | 45.74 | 1006.28 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on completion/laying/jointing | 20% | 22 | 182.96 | 4025.12 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on testing | 5% | 22 | 45.74 | 1006.28 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 22 | 45.74 | 1006.28 |  | 0 |  | 0 | 0 | 0 | 0 | 0
non boq item-5 | 160 mm dia HDPE Pipe PN‐6: Class PE‐100 | Rmt | 2964 | 649.92 | 1926362.88 | [7 empty] | 0
| On supply & delivery | 65% | 2964 | 422.448 | 1252135.872 | 2964 | 1252135.872 |  | 0 | 2964 | 1252135.872 | 0 | 0
| With Held Amount | 5% | 2964 | 32.496 | 96318.144 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on completion/laying/jointing | 20% | 2964 | 129.984 | 385272.576 | 227 | 29506.368 |  | 0 | 227 | 29506.368 | 0 | 0
| on testing | 5% | 2964 | 32.496 | 96318.144 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 2964 | 32.496 | 96318.144 |  | 0 |  | 0 | 0 | 0 | 0 | 0
non boq item-6 | 110 mm dia HDPE Pipe PN‐6: Class PE‐100 | Rmt | 493 | 326.32 | 160875.76 | [7 empty] | 0
| On supply & delivery | 65% | 493 | 212.108 | 104569.244 | 493 | 104569.244 |  | 0 | 493 | 104569.244 | 0 | 0
| With Held Amount | 5% | 493 | 16.316 | 8043.788 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on completion/laying/jointing | 20% | 493 | 65.264 | 32175.152 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on testing | 5% | 493 | 16.316 | 8043.788 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 493 | 16.316 | 8043.788 |  | 0 |  | 0 | 0 | 0 | 0 | 0
41.01 | 90 mm dia HDPE Pipe PN‐6: Class PE‐100 | Rmt | 264 | 229.22 | 60514.08 | [7 empty] | 0
| On supply & delivery | 65% | 264 | 148.993 | 39334.152 | 264 | 39334.152 |  | 0 | 264 | 39334.152 | 0 | 0
| With Held Amount | 5% | 264 | 11.461 | 3025.704 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on completion/laying/jointing | 20% | 264 | 45.844 | 12102.816 | 97.8 | 4483.5432 |  | 0 | 97.8 | 4483.5432 | 0 | 0
| on testing | 5% | 264 | 11.461 | 3025.704 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 264 | 11.461 | 3025.704 |  | 0 |  | 0 | 0 | 0 | 0 | 0
41.02 | 75 mm dia HDPE Pipe PN‐6: Class PE‐100 | Rmt | 1612 | 169 | 272428 | [7 empty] | 0
| On supply & delivery | 65% | 1612 | 109.85 | 177078.2 | 1612 | 177078.2 |  | 0 | 1612 | 177078.2 | 0 | 0
| With Held Amount | 5% | 1612 | 8.45 | 13621.4 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on completion/laying/jointing | 20% | 1612 | 33.8 | 54485.6 | 1274.9 | 43091.62 |  | 0 | 1274.9 | 43091.62 | 0 | 0
| on testing | 5% | 1612 | 8.45 | 13621.4 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1612 | 8.45 | 13621.4 |  | 0 |  | 0 | 0 | 0 | 0 | 0
41.03 | 63 mm dia HDPE Pipe PN‐6: Class PE‐100 | Rmt | 3988 | 125.65 | 501092.2 | [7 empty] | 0
| On supply & delivery | 65% | 3988 | 81.6725 | 325709.93 | 3988 | 325709.93 |  | 0 | 3988 | 325709.93 | 0 | 0
| With Held Amount | 5% | 3988 | 6.2825 | 25054.61 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on completion/laying/jointing | 20% | 3988 | 25.13 | 100218.44 | 2490.8 | 62593.804 |  | 0 | 2490.8 | 62593.804 | 0 | 0
| on testing | 5% | 3988 | 6.2825 | 25054.61 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 3988 | 6.2825 | 25054.61 |  | 0 |  | 0 | 0 | 0 | 0 | 0
42 | Supply and carting up to site of work of the following dia DI butterfly /sluice valves, class I, working pressure 10 Kg/cm2 confirming to IS: 780/1969 or its latest amendments, including valve fittings & Dismantling Joints as per requirement F.O.R. destination, and lowering them into the already prepared trenches, fixing in position and jointing them with pipelines and testing etc. complete and also including supply of jointing materials etc. complete .including all taxes and insurance, as per instructions of Engineer ‐in ‐charge. |  |  |  | 0 | [7 empty] | 0
42.04 | Sluice valve ‐ 150 mm dia | Nos. | 5 | 17604.85 | 88024.25 | [7 empty] | 0
| On supply & delivery | 70% | 5 | 12323.395 | 61616.975 |  | 0 | 5 | 61616.975 | 5 | 61616.975 | 0 | 0
| on completion/laying/jointing | 20% | 5 | 3520.97 | 17604.85 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on testing | 5% | 5 | 880.2425 | 4401.2125 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 5 | 880.2425 | 4401.2125 |  | 0 |  | 0 | 0 | 0 | 0 | 0
42.06 | Sluice valve ‐ 100 mm dia | Nos. | 4 | 14437.65 | 57750.6 | [7 empty] | 0
| On supply & delivery | 70% | 4 | 10106.355 | 40425.42 | 2 | 20212.71 | 2 | 20212.71 | 4 | 40425.42 | 0 | 0
| on completion/laying/jointing | 20% | 4 | 2887.53 | 11550.12 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on testing | 5% | 4 | 721.8825 | 2887.53 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 4 | 721.8825 | 2887.53 |  | 0 |  | 0 | 0 | 0 | 0 | 0
44.07 | Sluice valve ‐ 80 mm dia | Nos. | 0 | 12386.12 | 0 | [7 empty] | 0
| On supply & delivery | 70% | 0 | 8670.284 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on completion/laying/jointing | 20% | 0 | 2477.224 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on testing | 5% | 0 | 619.306 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 0 | 619.306 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
non boq item-7 | Sluice valve ‐65 mm dia | Nos. | 1 | 10637.22 | 10637.22 | [7 empty] | 0
| On supply & delivery | 70% | 1 | 7446.054 | 7446.054 |  | 0 | 1 | 7446.054 | 1 | 7446.054 | 0 | 0
| on completion/laying/jointing | 20% | 1 | 2127.444 | 2127.444 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on testing | 5% | 1 | 531.861 | 531.861 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1 | 531.861 | 531.861 |  | 0 |  | 0 | 0 | 0 | 0 | 0
non boq item-8 | Sluice valve ‐ 50 mm dia | Nos. | 1 | 9688.36 | 9688.36 | [7 empty] | 0
| On supply & delivery | 70% | 1 | 6781.852 | 6781.852 |  | 0 | 1 | 6781.852 | 1 | 6781.852 | 0 | 0
| on completion/laying/jointing | 20% | 1 | 1937.672 | 1937.672 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on testing | 5% | 1 | 484.418 | 484.418 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1 | 484.418 | 484.418 |  | 0 |  | 0 | 0 | 0 | 0 | 0
42.09 | Scour valve ‐ 100 mm dia | Nos. | 2 | 12520.24 | 25040.48 | [7 empty] | 0
| On supply & delivery | 70% | 2 | 8764.168 | 17528.336 |  | 0 | 2 | 17528.336 | 2 | 17528.336 | 0 | 0
| on completion/laying/jointing | 20% | 2 | 2504.048 | 5008.096 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on testing | 5% | 2 | 626.012 | 1252.024 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 2 | 626.012 | 1252.024 |  | 0 |  | 0 | 0 | 0 | 0 | 0
42.17 | Supply and installation, testing etc. of single/double ball type air valve conforming to latest/relevent I.S. specifications including all taxes and insurance, carting up to site of work and lowering them into the trenches, fixing in position and jointing them with pipelines and testing etc. complete (including supply of jointing materials and Valve fittings etc complete) as per instructions of Engineer. |  |  |  | 0 | [7 empty] | 0
42.19 | 50 mm | Nos. | 4 | 23142.53 | 92570.12 | [7 empty] | 0
| On supply & delivery | 70% | 4 | 16199.771 | 64799.084 |  | 0 | 4 | 64799.084 | 4 | 64799.084 | 0 | 0
| on completion/laying/jointing | 20% | 4 | 4628.506 | 18514.024 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on testing | 5% | 4 | 1157.1265 | 4628.506 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 4 | 1157.1265 | 4628.506 |  | 0 |  | 0 | 0 | 0 | 0 | 0
42.22 | Supply of under ground sluice value type fire hydrant consisting of 80 mm dia sluice valve, 80mm dia tail pieces, 80mm dia duck foot bend and 80 mm dia standard makes iron coupling with cap and etc. complete conforming to latest/relevent I.S.specifications including all taxes and insurance up to site of work and lowering them into the trenches, fixing in position and jointing them with pipelines and testing etc. complete (including supply of jointing materials and Valve fittings etc. complete as per instructions of Engineer ‐in ‐ charge. | Nos. | 1 | 22470.6 | 22470.6 | [7 empty] | 0
| On supply & delivery | 70% | 1 | 15729.42 | 15729.42 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on completion/laying/jointing | 20% | 1 | 4494.12 | 4494.12 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on testing | 5% | 1 | 1123.53 | 1123.53 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 1 | 1123.53 | 1123.53 |  | 0 |  | 0 | 0 | 0 | 0 | 0
43 | Construction of following type chambers as per department type design and drawing including Heavy duty M.S. Manhole Cover and all materials, labour, T&P etc complete for proper completion of work as per instructions of Engineer ‐in ‐charge. |  |  |  | 0 | [7 empty] | 0
43.01 | Sluice valve chamber (masonry Type) |  |  |  | 0 | [7 empty] | 0
43.02 | dia upto 200 mm ‐ 1000 (L) x 1200 (W) x 1300 (H) mm | No. | 1 | 20974.8 | 20974.8 |  | 0 |  | 0 | 0 | 0 | 0 | 0
43.03 | Sluice valve chamber (surface box Type) | No. | 8 | 4994 | 39952 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| On supply & delivery | 70% | 8 | 3495.8 | 27966.4 |  | 0 | 8 | 27966.4 | 8 | 27966.4 | 0 | 0
| on completion/laying/jointing | 30% | 8 | 1498.2 | 11985.6 |  | 0 |  | 0 | 0 | 0 | 0 | 0
43.04 | Fire Hydrant chamber (750 (L) X 450 (W) X 1000 (H) mm) | No. | 1 | 13983.2 | 13983.2 |  | 0 |  | 0 | 0 | 0 | 0 | 0
43.05 | Air Valve Chamber |  |  |  | 0 | [7 empty] | 0
43.06 | 350 (L) x 350 (W) x 500 (H) mm | No. | 4 | 8989.2 | 35956.8 |  | 0 |  | 0 | 0 | 0 | 0 | 0
43.07 | Scour Valve Chamber |  |  |  | 0 | [7 empty] | 0
43.08 | dia upto 200 mm ‐ 1000 (L) x 1200 (W) x 1300 (H) mm | No. | 2 | 24121.02 | 48242.04 |  | 0 |  | 0 | 0 | 0 | 0 | 0
44 | Design and construct Thrust Block made in R.C.C. with cement, coarse sand & 20 mm gauge stone ballast in proportion of 1:1.5:3, for pipe line, including supply of MS reinforcement wrought to required shape as necessary ,its bending, fixing & binding the same with 0.50 mm thick binding wire in position & necessary centering & shuttering including curing and supply of all materials, labour, T & P etc. required for proper completion of the work and as per specifications for RCC work as per instructions of Engineer ‐in ‐charge. |  |  |  | 0 | [7 empty] | 0
44.01 | Design and construct Thrust Block made in Reinforced Cement concrete (1:1.5:3), with graded stone chips (20 mm nominal size) excluding shuttering and reinforcement, as per technical requirements. | Cum. | 5.19 | 8964.05 | 46523.4195 |  | 0 |  | 0 | 0 | 0 | 0 | 0
44.02 | Providing shuttering for Thrust block using approved stout props and thick hard wood planks of approved thickness with required bracing for concrete works curved or straight including fitting fixing and striking out after completion of works. | Sqm | 7.74 | 419.5 | 3246.93 |  | 0 |  | 0 | 0 | 0 | 0 | 0
44.03 | Providing reinforcement of Thrust block for reinforced concrete work including distribution bars, stirrups, binders etc. initial straightening and removal of loose rust (if necessary), cutting to requisite length, hooking and bending to correct shape, placing in proper position and binding with wire at every inter‐section, complete as per drawing and direction. | MT | 0.39 | 76345.28 | 29774.6592 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| B.O.E. surface | sqm | 9.95 | 99.88 | 993.806 | 9.95 | 993.806 |  | 0 | 9.95 | 993.806 | 0 | 0
| Bituminous surface | sqm | 1674 | 199.76 | 334398.24 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Interlocking Road | sqm | 1356.81 | 154.81 | 210047.7561 | 250.04 | 38708.6924 |  | 0 | 250.04 | 38708.6924 | 0 | 0
| C.C. Road | sqm | 787.82 | 329.56 | 259633.9592 |  | 0 |  | 0 | 0 | 0 | 0 | 0
51 | Reinstatement of the following type of road surface with old and new materials including supply of all materials, labour, T&P etc. required for proper completion of the work as per instructions of Engineer ‐in ‐charge. |  |  |  | 0 | [7 empty] | 0
| B.O.E. surface (50% of existing bricks to be reused) | sqm | 9.95 | 349.58 | 3478.321 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Bituminous surface | sqm | 1674 | 1653.01 | 2767138.74 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Interlocking Road | sqm | 1356.81 | 1069.22 | 1450728.3882 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| C.C. Road | sqm | 787.82 | 1473.23 | 1160640.0586 |  | 0 |  | 0 | 0 | 0 | 0 | 0
52 | Provision for following types of Culvert crossing along the alignment of pipe line complete as per instructions of Engineer ‐in ‐charge. ( casing of pipe is done by concreting) |  |  |  | 0 | [7 empty] | 0
52.01 | Nala/Culvert Crossing ( width ‐3.5 m) upto Dia 300 mm | Nos | 2 | 18977.2 | 37954.4 | [7 empty] | 0
| On supply & delivery | 70% | 0.394 | 13284.04 | 5233.9118 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on completion/laying/jointing | 20% | 0.394 | 3795.44 | 1495.4034 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on testing | 5% | 0.394 | 948.86 | 373.8508 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 0.394 | 948.86 | 373.8508 |  | 0 |  | 0 | 0 | 0 | 0 | 0
52.02 | Trenchless crossings |  |  |  | 0 | [7 empty] | 0
52.03 | Survey site Investigation Planning , design Drawings as per State Road manual and vetting / checked from State Road Divisional Office and taking NOC for trenchless crossing of National highway road and Railway track(crossing length 15m to 25m ), Road for of required dia Rising main pipe with casing pipe as required for proper completion of work required size of MS casing pipe as per drawing and as per (IS:3589 & made from confining to IS:2062) with 750 Micron PU coating internally and 250 micron anti corrosive bituminous paint externally by trenchless technology method at an average depth 3.60 mtr from normal ground level up to top of casing pipe including excavation & filling of Pit, Dewatering arrangement, Supporting system for soil, also including supply and fixing of 2 no Sluice valve ISI Mark, construction of sluice valve chamber etc. all complete work including supply & fixing specials in carrier pipe over main pipe, as per specification given in the bid documents including supply of all materials, labour T&P etc. for proper completion of work as per instruction of Engineer. |  |  |  | 0 | [7 empty] | 0
52.07 | Road Crossing ‐ Excavation in foundation of trench of proper size in soil mixed with moorum, Shingle, Kankar, soft rock, hard rock, including refilling, dressing and ramming earth or sand or bajri, ballast, including providing, supply, carting, lowering, laying and jointing of casing pipe of RCC NP‐3 with appropriate size, with rubber ring joint, sand filling in gap inside RCC pipe, insertion of distribution pipe into the encasing pipe including supply of T&P, including concrete of 150 mm thick in with 40mm gauge brick ballast local sand and cement in proportion of 8:4:1, provision for barricading, labour for traffic diversion etc. Complete for proper completion of work as per instruction of Engineer. |  |  |  | 0 | [7 empty] | 0
52.08 | 50 mm dia. Pipe | Rmt | 60 | 1398.32 | 83899.2 | [7 empty] | 0
| On supply & delivery | 70% | 60 | 978.824 | 58729.44 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on completion/laying/jointing | 20% | 60 | 279.664 | 16779.84 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on testing | 5% | 60 | 69.916 | 4194.96 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 60 | 69.916 | 4194.96 |  | 0 |  | 0 | 0 | 0 | 0 | 0
52.09 | 100 mm dia. Pipe | Rmt | 20 | 1697.96 | 33959.2 | [7 empty] | 0
| On supply & delivery | 70% | 20 | 1188.572 | 23771.44 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on completion/laying/jointing | 20% | 20 | 339.592 | 6791.84 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on testing | 5% | 20 | 84.898 | 1697.96 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 20 | 84.898 | 1697.96 |  | 0 |  | 0 | 0 | 0 | 0 | 0
52.1 | 150 mm dia. Pipe | Rmt | 10 | 1997.6 | 19976 | [7 empty] | 0
| On supply & delivery | 70% | 10 | 1398.32 | 13983.2 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on completion/laying/jointing | 20% | 10 | 399.52 | 3995.2 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on testing | 5% | 10 | 99.88 | 998.8 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 10 | 99.88 | 998.8 |  | 0 |  | 0 | 0 | 0 | 0 | 0
52.11 | 200 mm dia. Pipe | Rmt | 10 | 2397.12 | 23971.2 | [7 empty] | 0
| On supply & delivery | 70% | 10 | 1677.984 | 16779.84 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on completion/laying/jointing | 20% | 10 | 479.424 | 4794.24 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on testing | 5% | 10 | 119.856 | 1198.56 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| on commissioning | 5% | 10 | 119.856 | 1198.56 |  | 0 |  | 0 | 0 | 0 | 0 | 0
53 | Making house connection should be done atleast 2 m inside the boundary wall with provision of tap from distribution line to outer wall of house, with supply of 1 m G.I. pipe ( 15 mm ) ( above ground ) & average 5 mtr. MDPE Pipe ( 20 mm) ( below ground) including specials, saddle, Tap,etc. of suitable size, T&P etc. including excavation, laying and jointing for proper completion of work as per instructions of Engineer as per Dwg 12 ( excluding road restoration) | Nos. | 785 | 3495.8 | 2744203 | [7 empty] | 0
| Supply & installation of Pipe & Fittings for FHTC as per BOQ Specification. |  |  |  | 0 | [7 empty] | 0
| Supply & Delivery of MDPE Pipes & Fittings . | 50% | 785 | 1747.9 | 1372101.5 | 785 | 1372101.5 |  | 0 | 785 | 1372101.5 | 0 | 0
| Supply & Delivery of Saddle & FCV | 10% | 785 | 349.58 | 274420.3 | 785 | 274420.3 |  | 0 | 785 | 274420.3 | 0 | 0
| Supply & Delivery of GI Pipe & Fitting. | 5% | 785 | 174.79 | 137210.15 | 785 | 137210.15 |  | 0 | 785 | 137210.15 | 0 | 0
| With Held Amount | 5% | 785 | 174.79 | 137210.15 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Excavation & Backfilling | 15% | 785 | 524.37 | 411630.45 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Laying & Excavation of HSC items. | 10% | 785 | 349.58 | 274420.3 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Commissioning | 5% | 785 | 174.79 | 137210.15 |  | 0 |  | 0 | 0 | 0 | 0 | 0
54 | Construction of single tap pillar type stand post as per type design | Nos. | 2 | 9988 | 19976
| Supply & Delivery of MDPE Pipes & Fittings . | 50% | 2 | 4994 | 9988 |  | 0 |  | 0 | 0 | 0 | 0
| Supply & Delivery of Saddle & FCV | 10% | 2 | 998.8 | 1997.6 |  | 0 |  | 0 | 0 | 0 | 0
| Supply & Delivery of GI Pipe & Fitting. | 10% | 2 | 998.8 | 1997.6 |  | 0 |  | 0 | 0 | 0 | 0
| Excavation & Backfilling | 15% | 2 | 1498.2 | 2996.4 |  | 0 |  | 0 | 0 | 0 | 0
| Laying & Excavation of HSC items. | 10% | 2 | 998.8 | 1997.6 |  | 0 |  | 0 | 0 | 0 | 0
| Commissioning | 5% | 2 | 499.4 | 998.8 |  | 0 |  | 0 | 0 | 0 | 0
55 | Operation and Maintenance for 10 years of water supply schemes after completion including staff required for operation and maintenance, chemicals, all materails, specials T & P for operation and maintenance excluding electricity charges. | % |  |  | 0