## Subtask Report
Task ID | Village Name | Supply (70%) | [5 empty] | Erection (20%) | [5 empty] | Testing (5%) | [5 empty] | Commissioning (5%)
|  | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount
221 | Alipur | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
616 | Asadpur Bamnauli | 2 | 26568.08 | 26568.08 | 0 | 0 | 26568.08
991 | Badhev kannukheda | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
1393 | Badhupura | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
1783 | Bamnoli | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
2179 | Baraala Kukkarheri | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
2567 | Barnavi Pathar and Mukundpur | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
2962 | Basera Non Allival | 1 | 13284.04 | 13284.04 | 1 | 13284.04 | 0
3362 | Bibipur Hatiya | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
3759 | Binda(Benra) | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
4132 | Dabheri Khurd | 1 | 13284.04 | 13284.04 | 1 | 13284.04 | 0
4511 | Erti | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
4886 | Gandrav | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
5288 | Gogwan | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
5696 | Jangheri | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
6082 | Jharkheri | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
6466 | Keserwa Kalan | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
6837 | Kaserwa Khurd | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
7233 | Loharipur | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
7609 | Mamour Non Aht | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
7988 | Mohammadpur Rai | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
8381 | Mundet Kalan | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
8769 | Naglarai | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
9155 | Panjeth | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
9451 | Potikalan | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
9825 | Ramra | 1 | 13284.04 | 13284.04 | 1 | 13284.04 | 0
10202 | Sahpat Non Ahatml | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
10578 | Titoli | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
10976 | UnchaGaon | 1 | 13284.04 | 13284.04 | 0 | 0 | 13284.04
Total |  | 0 | 0 | 398521.2 | 0 | 39852.12 | 358669.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0