## Subtask Report
Task ID | Village Name | Supply (70%) | [5 empty] | Erection (20%) | [5 empty] | Testing (5%) | [5 empty] | Commissioning (5%)
|  | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount | Tender Qty | Tender Rate | Tender Amount | Previous Bill QTY | Previous Bill Amount | Remaining Amount
18555 | Adampur | 1 | 182237.06 | 182237.06 | 1 | 182237.06 | 0 | [6 empty] | 1 | 11389.82 | 11389.82 | 0 | 0 | 11389.82 | 1 | 11389.82 | 11389.82 | 0 | 0 | 11389.82
18935 | Bhanera Jat | 1 | 182237.06 | 182237.06 | 1 | 182237.06 | 0 | [12 empty] | 1 | 11389.82 | 11389.82 | 0 | 0 | 11389.82
19338 | Dhanena | 1 | 182237.06 | 182237.06 | 1 | 182237.06 | 0 | [12 empty] | 1 | 11389.82 | 11389.82 | 0 | 0 | 11389.82
19719 | Goharni | 1 | 182237.06 | 182237.06 | 1 | 182237.06 | 0 | [12 empty] | 1 | 11389.82 | 11389.82 | 0 | 0 | 11389.82
20121 | Goharpur | 1 | 182237.06 | 182237.06 | 1 | 182237.06 | 0 | [6 empty] | 1 | 11389.82 | 11389.82 | 0 | 0 | 11389.82 | 1 | 11389.82 | 11389.82 | 0 | 0 | 11389.82
20501 | Jalalpur | 1 | 182237.06 | 182237.06 | 1 | 182237.06 | 0 | [12 empty] | 1 | 11389.82 | 11389.82 | 0 | 0 | 11389.82
20862 | Jandheri | 1 | 182237.06 | 182237.06 | 1 | 182237.06 | 0 | [12 empty] | 1 | 11389.82 | 11389.82 | 0 | 0 | 11389.82
21248 | Kanjarheri | 1 | 182237.06 | 182237.06 | 1 | 182237.06 | 0 | [12 empty] | 1 | 11389.82 | 11389.82 | 0 | 0 | 11389.82
21631 | Karori Mehrampur | 1 | 0 | 0 | 1 | 0 | 0 | [12 empty] | 1 | 0 | 0 | 0 | 0 | 0
22012 | Kasampur | 1 | 182237.06 | 182237.06 | 1 | 182237.06 | 0 | [12 empty] | 1 | 11389.82 | 11389.82 | 0 | 0 | 11389.82
22379 | Khanpur | 1 | 182237.06 | 182237.06 | 1 | 182237.06 | 0 | [12 empty] | 1 | 11389.82 | 11389.82 | 0 | 0 | 11389.82
22762 | Kherapatti Bhikki Mazra | 1 | 182237.06 | 182237.06 | 1 | 182237.06 | 0 | [12 empty] | 1 | 11389.82 | 11389.82 | 0 | 0 | 11389.82
23141 | Kheri Bairagi | 1 | 182237.06 | 182237.06 | 1 | 182237.06 | 0 | [12 empty] | 1 | 11389.82 | 11389.82 | 0 | 0 | 11389.82
23531 | Kheri Karmu | 1 | 182237.06 | 182237.06 | 1 | 182237.06 | 0 | [12 empty] | 1 | 11389.82 | 11389.82 | 0 | 0 | 11389.82
23927 | Saihata | 1 | 182237.06 | 182237.06 | 1 | 182237.06 | 0 | [12 empty] | 1 | 11389.82 | 11389.82 | 0 | 0 | 11389.82
Total |  | 0 | 0 | 2551318.84 | 0 | 2551318.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22779.64 | 0 | 0 | 22779.64 | 0 | 0 | 159457.48 | 0 | 0 | 159457.48