## Sheet1
Subcontractor: | Ajay kumar contractor
State: | Uttar Pradesh |  | Ajay kumar contractor |  |  | Pump House work | [7 empty] | 2024-07-23
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | GST_SD_Amount | Hold Amount against Material | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | SD (5%) | Advance paid | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 10% | 18% | [5 empty] | 1% | 5%
55015
55015 | Dakhori Village Pump House work | 2023-02-02 | 1 | 228600 | 0 | 228600 | 41148 | 269748 | 2286 | 22860 | 41148 | 0 | 203454 |  | RIUP22/2255 | 203454 | 0 | 0 | 0 | 203454 | 23-02-2023 NEFT/AXISP00365094602/RIUP22/2255/AJAY KUMAR 203454.00
55015 | Dakhori Village Pump House work | 2023-07-15 | 2 | 152400 | 56372 | 96028 | 17285.04 | 113313.04 | 960.28 | 9602.8 | 17285.04 |  | 85465 |  | RIUP22/2050 | 85464 | 0 | 0 | 0 | 85464 | 15-09-2023 NEFT/AXISP00425358565/RIUP23/2050/AJAY KUMAR 85464.00
55015 | GST Release Note | 2023-02-02 | 1 | 41148 | [8 empty] | 41148 |  | RIUP22/2051 | 41148 | 0 | 0 | 0 | 41148 | 18-09-2023 NEFT/AXISP00425751837/RIUP23/2051/AJAY KUMAR 41148.00
55015 | GST Release Note |  | 2 | 17285.04 | [8 empty] | 17285.04 | [6 empty] | 17285 | 16-07-2024 NEFT O/W-YESIG41980136416-IDIB000S647-AJAY KUMAR-RIUP23/4313 17,285.00
55015
55015
[8 empty] | 383061.04 | 3246.28 | 32462.8 | 58433.04 | 0 | 347352.04 |  |  |  |  | Total Paid Amount Rs. - |  | 347351 | Total Paid
[18 empty] | Balance Payable Amount Rs. - |  | 1.04 | Balance Payable
Ajay Kumar Contrcator
Updated On 23-7-24 - Girija
[11 empty] | Total Hold |  | 32462.8
[11 empty] | DPR Excess Debit |  | 0
[11 empty] | Advance/ Surplus |  | 1.04
[11 empty] | GST Remaining |  | 0