## Sheet1
Subcontractor: | M/s Akram
State: | Uttar Pradesh |  | M/s Akram |  |  |  |  | Pipe Laying work | [7 empty] | 2024-07-23
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold the Amount because the Qty. is more then the DPR | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% | 10% | 10% | 18% | [5 empty] | 1%
59484 | [15 empty] | 59484
59484 | Jangeri Village Pipe line Road work | 2023-11-01 | 1 | 307533 | 83150 | 224383 |  | 224383 | 2243.83 | 11219.15 | 22438.3 | 22438.3 | 0 | 0 | 166043 |  |  |  |  | 148500 | 10-11-2023 NEFT/AXISP00443464525/RIUP23/3255/AKRAM/PUNB0SUPGB5 148500.00
59484 | Jangeri Village Pipe line Road work | 2023-12-25 | 5 | 204287 | 0 | 204287 |  | 204287 | 2042.87 | 10214.35 | 20428.7 | 20428.7 | 0 | 0 | 151172 |  |  |  |  | 17544 | 11-12-2023 NEFT/AXISP00451509782/RIUP23/3431/AKRAM/PUNB0SUPGB5 17544.00
59484 | [19 empty] | 151174 | 09-01-2024 NEFT/AXISP00461001722/RIUP23/4123/AKRAM/PUNB0SUPGB5 151174.00
59484 | [19 empty] | 59400 | 22-03-2024 NEFT/AXISP00483290485/RIUP23/5247/AKRAM/PUNB0SUPGB5 59400.00
66923 | [15 empty] | 66923 | [5 empty] | -59403
66923 | Yousufpur choutra Village UNN Block Pipe line Road work | 2024-12-21 | 1 | 180196 | 57225 | 122971 |  | 122971 | 1229.71 | 6148.55 | 12297.1 | 12297.1 | 0 | 0 | 90999 |  |  |  |  | 75000 | 25-02-2025 NEFT/AXISP00621808047/RIUP24/2882/AKRAM/PUNB0SUPGB5 75000.00
66923
66924 | [15 empty] | 66924 | [5 empty] | 15999
66924 | ODRI FATEHPUR VILLAGE PIPE LINE ROAD RESTORATION WORK AT ODRI FATEHPUR VILLAGE BLOCK-UNN | 2024-12-31 | 7 | 94747 | 0 | 94747 |  | 94747 | 947.47 | 4737.35 | 0 | 0 | 0 | 0 | 89062 |  |  |  |  | 50000 | 29-01-2025 NEFT/AXISP00604547877/RIUP24/3012/AKRAM/PUNB0SUPGB5 50000.00
66924 | [19 empty] | 35000 | 14-02-2025 NEFT/AXISP00616404531/RIUP24/3174/AKRAM/PUNB0SUPGB5 35000.00
66924 | [21 empty] | 4062
[10 empty] | 32319.4 | 55164.1 | 55164.1 | 0 | 0 | 497276 |  | Total Paid Amount Rs. - |  |  | 536618 |  | -39342
[17 empty] | Balance Payable Amount Rs. - |  |  | -39342
| PIPE LINE ROAD RESTORATION WORK AT ODRI FATEHPUR VILLAGE BLOCK-UNN | [8 empty] | Akram
2025-02-26
[10 empty] | Total Hold |  | 142647.6
[10 empty] | DPR Excess Debit |  | 0
[10 empty] | Advance/ Surplus |  | -39342
[10 empty] | GST Remaining |  | 0