## Sheet1
Subcontractor: | Amir construction
State: | Uttar Pradesh |  | Amir construction
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | Hold Amount for additional work done of Lowring work | GST_SD_Amount | Final_Amount |  | PAYMENT NOTE No. | Total_Amount | UTR
[9 empty] | 1% | 5% | 10% | 10%
60107
60107 | Alipur Umerpur village Drilling work | 2023-12-02 | 4 | 232105 | 95375 | 136730 | 24611 | 161341 | 1367 | 6837 | 13673 | 13673 | 0 | 24611 | 101180 |  | RUIP23/3729 | 101181 | 15-12-2023 NEFT/AXISP00453272888/RIUP23/3729/AMIR CONSTRUCTIONS/PUNB0402300 101181.00
60107 | GST RELEASE NOTE |  | 4 | 24612 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 24612
60107
60107
[10 empty] | 6837 | 13673 | 13673 | 0 | 24611 | 125792 |  | Total paid | 101181
[17 empty] | Bal Payable | 24611
| Extra work done against DPR quantity - Drilling work 167.00RMT against 160.00RMT (7RMT X 11000/- = 7700/-) and Lowering work 156.23RMT against 145.00RMT (11.23RMT X 150/- = 1684.50) |  |  | -9384.5
34183
24611