## Sheet1
Subcontractor: | Dev Construction Sachin Kumar
State: | Uttar Pradesh | [5 empty] | Pipeline laying work
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold Amount for excess Qty. against DPR/ Advance | Final_Amount | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | Total_Amount | UTR
[9 empty] | 1% | 5% | 10% | 10% | [5 empty] | 1%
66074 | Ballamazra village Pipeline work | 2024-10-26 | 1 | 50082 | 0 | 50082 | 9014.76 | 59097 | 501 | 2504 | 5008.2 | 5008.2 | 9014.76 | 0 | 37060.84 | SPUP23/2287 | 30000 | 300 | 29700 | 31-10-2024 NEFT/AXISP00561901250/RIUP24/2391/DEV CONSTRUCTION/CNRB0007639 29700.00
66074 | GST Release Note |  | 1 | 9014.76 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 9014.76 |  |  |  | 39600 | 04-12-2024 NEFT/AXISP00579764057/RIUP24/2619/DEV CONSTRUCTION/CNRB0007639 39600.00
66074 | Ballamazra village Pipeline work | 2024-11-25 | 2 | 14600 | 0 | 14600 | 2628 | 17228 | 146 | 730 | 1460 | 1460 | 2628 | 0 | 10804
66074 | GST Release Note |  | 2 | 2628 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 2628
-9792.4
67387 | BARHAM KHERA VILLAGE BALANCE PIPE LINE FHTC Work | 2024-12-26 | 4 | 20509 | 0 | 20509 | 3692 | 24201 | 205.09 | 1025 | 2050.9 | 2050.9 | 3692 | 104 | 15073.11
67387
15073.11
67963 | SAHPAT Village Pipeline & FHTC Balance Work | 2025-02-10 | 5 | 63473 | 0 | 63473 | 11425 | 74898 | 634.73 | 3174 | 6347.3 | 6347.3 | 11425 | 0 | 46970 |  |  |  | 49500 | 03-03-2025 NEFT/AXISP00626657827/RIUP24/3306/DEV CONSTRUCTION/CNRB0007639 49500.00
67963
67963 | [20 empty] | -2530
[10 empty] | 7433 | 14866.4 | 14866.4 | 26759.76 | 104 | 121550.71 | Total Paid Amount Rs.- |  |  | 118800
[16 empty] | Balance Payable Amount Rs.- |  |  | 2750.71 |  | 2750.71
Dev Construction Sachin Kumar
2025-03-04
[9 empty] | Hold Amount |  | 37165.8
[9 empty] | Advance / Surplus |  | 2750.71
[9 empty] | Debit |  | 57225
[9 empty] | GST Remaining |  | 15117