## Sheet1
MZN, UP
| Invoice Reconcilation |  | HD Construction
| Invoice Details | Invoice Date | Invoice No | Basic Amt | Debit | After Debit Amt | 18% GST | Amount | TDS (1%) | SD (5%) | HT ( 10% ) | GST SD (18%) | Hold amount for excess qty. against DPR | Final Amount |  | PAYMENT NOTE No. | Amount | TDS Amount @ 1% on BASIC AMOUNT | Total Amount Paid | UTR | UTR | Advance
[7 empty] | 18% |  | 1% | 5% |  | 18% | [5 empty] | 1%
58899
58899 | BOUNDARY WALL WORK AT FAHIMPUR KHURD VILLAGE | 2023-12-19 | 1 | 334040 | 79762 | 254278 | 45770 | 300048 | 2543 | 12714 |  | 45770 | 0 | 239021
| GST |  |  | 45770 | [9 empty] | 45770
[15 empty] | 58434 | [6 empty] | 284791
58434 | CONSTRUCTION WORK OF OHT AT GP VILLAGE SAIDPUR BLOCK KHATAULI | 2023-12-19 | 2 | 472500 | 254268 | 218232 | 39282 | 257514 | 2182 | 10912 | 21823.2 | 39282 | 0 | 183315 |  | RIUP23/1122 | 1500000 | 15000 | 1485000 | 18-07-2023 NEFT/AXISP00407699534/RIUP23/1122A/H D CONSTRUCTI 1485000.00 | 18-07-2023 NEFT/AXISP00407699534/RIUP23/1122A/H D CONSTRUCTI 1485000.00
| GST |  |  | 39282 | [9 empty] | 39282 |  | RIUP23/2452 | 1000000 | 10000 | 990000 | 03-10-2023 NEFT/AXISP00430209797/RIUP23/2452/H D CONSTRUCTION/SBIN0050699 990000.00 | 03-10-2023 NEFT/AXISP00430209797/RIUP23/2452/H D CONSTRUCTION/SBIN0050699 990000.00
[15 empty] | 58905 | [6 empty] | -2252403
58905 | BOUNDARY WALL WORK AT Basayach VILLAGE | [14 empty] | RIUP23/2433 | 100000 | 1000 | 99000 | 03-10-2023 NEFT/AXISP00429778567/RIUP23/2433/H D CONSTRUCTION/SBIN0050699 99000.00 | 03-10-2023 NEFT/AXISP00429778567/RIUP23/2433/H D CONSTRUCTION/SBIN0050699 99000.00
| GST | [12 empty] | 0
[15 empty] | 58904 | [6 empty] | -99000
58904 | BOUNDARY WALL WORK AT Saidpur VILLAGE
| GST | [12 empty] | 0
[15 empty] | 58903 | [6 empty] | 0
58903 | BOUNDARY WALL WORK AT Yahiyapur VILLAGE
| GST | [12 empty] | 0
[15 empty] | 58901 | [6 empty] | 0
58901 | PUMP HOUSE WORK. AT FAHIMPUR KHURD VILLAGE
| GST |  |  | 0 | [9 empty] | 0 | [7 empty] | 0
[9 empty] | 4725 | 23626 | 21823.2 | 85052 | 0 | 507388 |  | Total Paid Amount Rs. - |  |  | 2574000
-2066612
[16 empty] | Balance Payable Amount Rs. - |  |  | -2066612
[8 empty] | T.I -3, 4 & 5 has no clarity |  |  |  | 0
Updated On 05-07-2024
[8 empty] | Total Hold |  | 45449.2
[8 empty] | Advance / Surplus |  | -2066612
[8 empty] | Debit |  | 10350

## Sheet1 (2)
Subcontractor: | HD Construction
State: | Uttar Pradesh
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | Hydro_Testing | GST_SD_Amount | Hold the Amount because the Qty. is more then the DPR | Final_Amount | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | Total_Amount | UTR | Advance
[7 empty] | 18% |  | 1% | 5% |  | 18% |  |  |  |  | 1%
58895 | SAIDPUR BLOCK KHATAULI Village CONSTRUCTION OF BOUNDARY WALL WORK
58895 | GST Release Note
58906 | SAIDPUR BLOCK KHATAULI Village CONSTRUCTION OF PUMP HOUSE WORK
58909 | KHALWARA BLOCK JANSATH Village CONSTRUCTION OF OHT work
58914 | SAIDiPUR Raju BLOCK Jansath Village CONSTRUCTION OF OHT WORK
58899 | FAHIMPUR KHURD VILLAGE Village BOUNDARY WALL WORK | 2023-12-19 | 1 | 334040 | 79762 | 254278 | 45770 | 300048 | 2543 | 12714 |  | 45770 | 0 | 239021
58899 | GST Release Note |  |  | 45770 | [9 empty] | 45770
284791
58434 | GP VILLAGE SAIDPUR BLOCK KHATAULI Village CONSTRUCTION WORK | 2023-12-19 | 2 | 472500 | 254268 | 218232 | 39282 | 257514 | 2182 | 10912 | 21823.2 | 39282 | 0 | 183315 | RIUP23/1122 | 1500000 | 15000 | 1485000 | 18-07-2023 NEFT/AXISP00407699534/RIUP23/1122A/H D CONSTRUCTI 1485000.00
58434 | GST Release Note |  |  | 39282 | [9 empty] | 39282 | RIUP23/2452 | 1000000 | 10000 | 990000 | 03-10-2023 NEFT/AXISP00430209797/RIUP23/2452/H D CONSTRUCTION/SBIN0050699 990000.00
-2252403
58905 | Basayach VILLAGE BOUNDARY WALL WORK | [13 empty] | RIUP23/2433 | 100000 | 1000 | 99000 | 03-10-2023 NEFT/AXISP00429778567/RIUP23/2433/H D CONSTRUCTION/SBIN0050699 99000.00
58905 | GST Release Note | [12 empty] | 0
-99000
58904 | Saidpur VILLAGE BOUNDARY WALL WORK
58904 | GST Release Note | [12 empty] | 0
0
58903 | Yahiyapur VILLAGE BOUNDARY WALL WORK
58903 | GST Release Note | [12 empty] | 0
0
58901 | FAHIMPUR KHURD VILLAGE PUMP HOUSE WORK.
58901 | GST Release Note |  |  | 0 | [9 empty] | 0 | [5 empty] | 0

## Sheet2
Sub contractor Name | Village Name | Bill Amount | Amount As per Site | Debit | Net Amount | TDS (1%) | SD (5%) | HT ( 10% ) | OC (10%) | GST SD (18%) | Final Amount | Total Amount Paid | Balance
HD Construction
58899 | BOUNDARY WALL WORK FAHIMPUR KHURD VILLAGE | 334040 | 512000 | 79762 | 254278 | 2542.78 | 12713.9 |  |  | 45770.04 | 239021.32
58434 | CONSTRUCTION WORK OF OHT AT GP VILLAGE SAIDPUR BLOCK KHATAULI | 472500 | 505680 | 254268 | 218232 | 2182.32 | 10911.6 | 21823.2 |  | 39281.76 | 183314.88 | 2500000
58905 | CONSTRUCTION OF BOUNDARY WALL WORK AT BASAYACH BLOCK KHATAULI |  | 460000 | [8 empty] | 100000
|  |  | 1477680 | [5 empty] | Total | 85051.8 | 422336.2 | 2600000 | -2177663.8
Rishal Construction
59156 | BALANCE WORK ROAD RESTORATION AT MEDPUR BLOCK SADAR | 295400 | 294000 | 112500 | 182900 | 1829 | 9145 | 18290 | 18290 | 32922 | 96348 | 500000
59157 | Dehchand Village Road Restoration work | 262045 | 265000 | 0 | 262045 | 2620.45 | 13102.25 | 26204.5 | 26204.5 | 47168.1 | 193913.3 | 800000
59158 | Aklor Village Road Restoration work | 353603 | 353000 |  | 353603 | 3536.03 | 17680.15 | 35360.3 | 35360.3 | 63648.54 | 261666.22 | 700000
59159 | Kallarpur Village Road Restoration work | 691783 | 748000 | 57750 | 634033 | 6340.33 | 31701.65 | 63403.3 | 63403.3 | 114125.94 | 439282.42 | 600000
60026 | Kacholi Village Road Restoration work | 254678 | 254000 |  | 254678 | 2546.78 | 12733.9 | 25467.8 | 25467.8 | 45842.04 | 188461.72 | 500000
60719 | BALANCE REINSTATEMENT WORK AT BHAISANI Village BLOCK PURKAZI | 320521 | 333000 | 37500 | 283021 | 2830.21 | 14151.05 | 28302.1 |  | 50943.78 | 237737.64
|  |  | 2247000 | [6 empty] | Total | 1417409.3 | 3100000 | -1682590.7