## Sheet1
S.NO. | BLOCK | VILLAGE | PIPELAYING STATUS | OHT DRAWING STATUS |  | STATUS DRILING/PEA GRAVEL PACKING | DEVELOPMENT |  | PUMP INSTALLATION STATUS | DG FOUNDATION | DG AVAILABLE AT SITE | HEADER CONNECTIVITY | SOLAR ISTALLATION STATUS | LT PANEL INSTALLATION | RTU PANEL INSTALLATION | CHLORINATION SYSTEM INSTALLATION | REGULAR WATER SUPPLY | ROAD RESTORATION | STATUS OF BOUNDARY WALL | BOUNDARY WALL PAINTAING | BOARD FIXING | GATE FIXING | PUMP HOUSE STATUS | PUMP HOUSE PAINTAING | OHT STATUS | NAME OF OHT WORKING AGENCY | MANPOWER STATUS | REMARK | TOTAL 25 VILLEGE
|  |  |  | Capacity | Status |  | COMPRESOR% | OP UNIT%
1 | UNN | DATHERA | FINISH | 300KL 16MTR | Approved | COMP. | YES | YES | COMPLETE | YES | YES | DONE | YES | YES | YES | PENDING | YES | WIP | COMPLETED | PENDING |  |  | COMPLETED | YES | UPTO FIRST BRACE BEAM | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP | RECTIFICATION WIP | PLINTH PROTCATION PENDING
2 | UNN | TODA | FINSIH | 325KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | PENDING | YES | YES | YES | PENDING | PENDING | YES | WIP | COMPLETED | PENDING |  |  | COMPLETED | PENDING | COLUMN UPTO 1RST BRACE BEAM TOP TO 2ND BRACE BEAM BOTTOM | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP
3 | UNN | KHORSAMA | FINISH | 225KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | YES | YES | YES | YES | YES | YES | YES | COMPLETED | COMPLETED | PENDING |  |  | COMPLETED | PENDING | UPTO 1ST BRACE BEAM | SKYLINE | WIP | MANPOWER PROBELEM | NEW TEAM FOR LIKEGE REPERING ( up to white )
4 | UNN | BALLAMZRA | FINSH | 225KL 12 MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | PENDING | PENDING | YES | PENDING | PENDING | PENDING | YES | WIP | PENDING | PENDING |  |  | COMPLETED | PENDING | COLUMN UPTO 1RST BRACE BEAM TOP TO 2ND BRACE BEAM BOTTOM | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP |  | NEW TEAM FOR LIKEGE REPERING & FHTC ( white wash )
5 | UNN | KERTU | FINISH/HIGHWAY WORK PENDING/RELAYING DUE TO DEPTH ISSUE | 225KL 12 MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | YES | YES | PENDING | PENDING | YES | PENDING | YES | PENDING | COMPLETED | PENDING |  |  | COMPLETED | PENDING | COLUMN UP TO 3RD BRACE BEAM BOTTOM | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP |  | pump / boundray only white
6 | UNN | KHERI KHUSHNAM | FINISH | 200KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | PENDING | YES | YES | YES | YES | PENDING | YES | WIP | COMPLETED | PENDING |  |  | COMPLETED | PENDING | FULL STAGING | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP | MANPOWER PROBELEM | pump/ bounday wall up to white wash
7 | UNN | GUJJARPUR-RAMNAGAR | FINISH | 150KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | YES | YES | YES | YES | YES | YES | PENDING | YES | COMPLETED | WIP | PENDING |  |  | COMPLETED | PENDING | COLUMN UPTO 1RST BRACE BEAM TOP TO 2ND BRACE BEAM BOTTOM | RS CONSTRUCTION (JB) | WIP |  | pump/ bounday wall up to white wash
8 | UNN | KHERKI | FINISH | 125KL 12 MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | PENDING | YES | YES | YES | YES | PENDING | YES | COMPLETED | PENDING | PENDING |  |  | COMPLETED | PENDING | RAFT REINFORCEMENT WIP | JSS SACHIN | WIP |  | pump house white wash
9 | UNN | TANA | WIP/RANA/HDD DEMAND FROM VILLAGERS | 325KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | YES | PENDING | PENDING | YES | YES | PENDING | PENDING | PENDING | PENDING | WIP | PENDING |  |  | COMPLETED | PENDING | FULL STAGING DONE | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | STOP | MANPOWER PROBELEM | NEW TEAM WITH HDD ONLY FOR PIPE LAYING ( bondary wall up to coping & pump house white wash )
10 | UNN | DHINDHALI | WIP | 175KL 12MTR | Approved | COMP. | PENDING | PENDING | WIP | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING |  |  | PENDING | PENDING | 3RD BRACE BEAM above column wip | SHRI RAM | WIP
11 | UNN | GARHI HASANPUR | FINISH ONLY DI LAYING PENDING | 400KL/12MTR | Approved | COMP. | YES | YES | COMPLETE | YES | YES | PENDING | YES | YES | YES | PENDING | PENDING | PENDING | COMPLETED | YES | YES | COMPLETED | COMPLETED | PENDING | UPTO NGL | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | STOP | DWG | NEW TEAM FOR PIPE LAYING AND HTC
12 | UNN | GAGOUR | FINISH IN 3 NOS MAJRA/ PENDING IN MAIN VILLAGE | 275KL/12MTR | Approved | COMP. | YES | YES | COMPLETE | YES | YES | YES | YES | YES | PENDING | PENDING | YES | PENDING | COMPLETED | YES | YES | COMPLETED | COMPLETED | PENDING | FULL STAGING ( STAIR CASE 4th flight ) WIP ) | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP |  | NEW TEAM WITH HDD ONLY FOR PIPE LAYING & 3 NO,S MAZARA ROAD RESTRORATION
13 | UNN | GANGARAMPURA KHEDKI | FINISH | 250KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | YES | YES | YES | YES | YES | YES | PENDING | YES | COMPLETED | COMPLETED | PENDING | YES | COMPLETED | COMPLETED | PENDING | BOTTOM DOME | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP |  | 30 NO,S PENDING ( pump house& bondary only white )
14 | UNN | CHATTELA URF JAINPUR | FINISH | 125KL 12 MTR | Approved | COMP. | YES | YES | COMPLETE | YES | YES | YES | YES | YES | YES | PENDING | YES | COMPLETED | COMPLETED | PENDING |  |  | COMPLETED | PENDING | UPTO COLUMN ABOVE 3rd BRACE BEAM WIP | SHRI RAM | WIP |  | NEW TEAM FOR TAB & OTHER WORK 3 LABOUR & FITER FOR 10 DAYS
15 | UNN | BIDAULI | FINISH | 300KL 14MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | YES | YES | YES | YES | YES | YES | YES | COMPLETED | WIP | PENDING |  |  | COMPLETED | YES | 3RD BRACR BEAM WIP | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP |  | BOUNDARY WALL ONLY PLASTER
16 | UNN | BEDKHERI | FINISH | 225KL 12 MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | PENDING | YES | YES | YES | YES | PENDING | YES | COMPLETED | WIP | PENDING |  |  | COMPLETED | PENDING | UP TO 3RD BRACE BEAM Above column wip | ANKSHRI | WIP
17 | UNN | LAWA DAUPUR | FINISH | 150KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | YES | YES | YES | YES | YES | YES | PENDING | YES | COMPLETED | COMPLETED | WIP | YES | COMPLETED | COMPLETED | WIP | 1ST BRACEBEAM WIP | CS INFRA | WIP | MANPOWER PROBELEM
18 | UNN | MUNDET KHADER | FINISH | 300KL/16MTR | Approved | COMP. | YES | YES | COMPLETE | YES | PENDING | WIP | YES | YES | PENDING | PENDING | YES | WIP | PENDING | PENDING |  |  | COMPLETED | YES | UPTO GL | RAKESH SINGH/ANKSHRI | WIP | 5
19 | UNN | HARSANA | FINISH | 225KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | YES | YES | PENDING | YES | YES | YES | PENDING | YES | WIP | PENDING | PENDING |  |  | COMPLETED | PENDING | UPTO GL | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP |  | KAMIL JI
20 | UNN | PURMAFI | FINISH | 175KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | PENDING | PENDING | YES | YES | PENDING | PENDING | YES | WIP | PENDING | PENDING |  |  | COMPLETED | PENDING | ABOVE 3rd BRACE BEAM COLUMN WIP | SHRI RAM | WIP
21 | UNN | BHAHMERI SHAHPUR | FINISH | 225KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | PENDING | YES | YES | YES | YES | PENDING | YES | WIP | WIP | PENDING |  |  | COMPLETED | PENDING | BOTTOM DOME WIP ( STAIR CASE WIP ) | RS CONSTRUCTION (JB) | WIP
22 | UNN | SUBHRI | FINISH | 200KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | PENDING | YES | YES | YES | YES | PENDING | YES | PENDING | PENDING | PENDING |  |  | COMPLETED | PENDING | UP GL COLUMN WIP | DEV CONSTRUCTION | WIP | MANPOWER PROBELEM | FOR VALVE & TAB & GI FITING FIXING WITH FHTC 4 WORKER FOR 10 DAYS
23 | UNN | HASANPUR | FINISH | 200KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | YES | PENDING | YES | YES | YES | YES | PENDING | YES | WIP | COMPLETED | PENDING | YES | COMPLETED | COMPLETED | PENDING | RAFT R/F FIXING | ANKSHRI | WIP
24 | THANABHAWAN | AHATAH GOSHGARH | WIP | 150KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | PENDING | PENDING | YES | PENDING | PENDING | PENDING | PENDING/ 10.01.24 | WIP | COMPLETED | PENDING | PENDING | PENDING | COMPLETED | PENDING | COLUMN CASTING UPTO 2ND BRACE | RAKESH SINGH/LEFT THE WORK/SHRI RAM | STOP
25 | THANABHAWAN | MAKHERI KADERGARH | FINISH/MARUKHEDI PENDING | 300KL/12MTR | Approved | COMP. | YES | YES | COMPLETE | YES | PENDING | YES | YES | YES | YES | PENDING | YES | COMPLETED | COMPLETED | PENDING | PENDING | PENDING | COMPLETED | PENDING | FULL STAGING | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP | 4
26 | THANABHAWAN | MANAT MANTI | FINISH | 375KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | YES | YES | YES | PENDING | YES | YES | PENDING | TESTING DONE/ISSUE IN SOLAR INSTALLATION DUE TO SHORT SPACE | COMPLETED | COMPLETED | PENDING | PENDING | PENDING | COMPLETED | PENDING | BOTTOM DOM R/F & shuttring FIXING WIP | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP | 5
27 | THANABHAWAN | MAHAVATPUR | FINISH | 150KL/14MTR | Approved | COMP. | YES | YES | COMPLETE | YES | YES | YES | YES | YES | YES | PENDING | YES | COMPLETED | COMPLETED | PENDING | PENDING | PENDING | COMPLETED | YES | 3RD BRACE BEAM WIP | ST ENTERPRISES | WIP | 7
28 | THANABHAWAN | YARPUR | FINISH | 250KL 14 MTR | Approved | COMP. | YES | YES | COMPLETE | YES | PENDING | YES | YES | YES | YES | PENDING | YES | COMPLETED | WIP | PENDING | PENDING | PENDING | COMPLETED | YES | FULL STAGING COM | JAVED/LEFT THE WORK/DHANVI CONSTRUCTION | WIP | 8
29 | THANABHAWAN | KHERAGADAI | WIP | 175KL 16 MTR | Approved | COMP. | YES | YES | COMPLETE | YES | YES | PENDING | YES | YES | YES | PENDING | PENDING/7.01.24 | PENDING | COMPLETED | PENDING | PENDING | PENDING | COMPLETED | YES | COLUMN CASTING UPTO 1ST BRACE BEAM | A.K PANDEY/LEFT THE WORK/SHRI RAM | STOP
30 | THANABHAWAN | KELASHIKARPUR | FINISH | 200KL 14MTR | Approved | COMP. | YES | YES | COMPLETE | YES | YES | YES | YES | YES | YES | PENDING | YES/NEED RE INSTALLED SOLAR MODULE | COMPLETED | COMPLETED | PENDING | PENDING | PENDING | COMPLETED | PENDING | RCC WORK COMPLETED STAIR (WIP) | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP | 4
31 | THANABHAWAN | UMERPUR | FINISH | 250KL 12MTR | Approved | COMP. | PENDING/PROBLEM IN BORE | PENDING | COMPLETE | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING/BOREWELL ISSUE | WIP | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | 1RST BRACE BEAM R/F FIXING | RAKESH SINGH/LEFT THE WORK/VISHAL JI JJM ( Anivarati infraengineers pvt ) | WIP | 4
32 | THANABHAWAN | JAFARPUR | FINISH | 175KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | YES | YES | YES | PENDING | PENDING | PENDING | PENDING | TESTING DONE/ISSUE IN SOLAR INSTALLATION DUE TO SHORT SPACE | WIP | COMPLETED | PENDING | PENDING | PENDING | COMPLETED | YES | HALF HEIGHT | AK PANDEY/LEFT THE WORK/SHRI RAM | WIP | 8
33 | THANABHAWAN | DAKHORI JAMALPUR | WIP | 200KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | YES | YES | PENDING | YES | YES | PENDING | PENDING | PENDING/1.01.24 | PENDING | PENDING | PENDING | PENDING | PENDING | COMPLETED | YES | RCC WORK COMPLETED | RADHE CONSTRUCTION | STOP
34 | THANABHAWAN | AURANGABAD URF GANDHEWARA | FINISH | 200KL 12 MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | PENDING | YES | YES | YES | YES | PENDING | YES | PENDING | COMPLETED | YES | YES | YES | COMPLETED | YES | 1ST LIFT VERTICAL WALL R/F WIP | SWAROOPA | WIP | 1900-01-06
35 | THANABHAWAN | BAHANDAURA | FINISH | 200KL/12MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | YES | YES | YES | YES | PENDING | PENDING | YES | WIP | COMPLETED | PENDING | PENDING | PENDING | COMPLETED | YES | RCC WORK COMPLETED | RADHE CONSTRUCTION | STOP
36 | THANABHAWAN | BHANERAUDDA | WIP | 300KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | YES | PENDING | YES | YES | YES | PENDING | PENDING/10.01.24 | PENDING | COMPLETED | PENDING | PENDING | YES | COMPLETED | PENDING | RCC WORK COMPLETED | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | STOP
37 | THANABHAWAN | MANAKPUR YUNISPUR | FINSH /ROAD CROSSING PENDING | 300KL 14 MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | WIP | PENDING | PENDING | PENDING | COMPLETED | PENDING | INLET AND OUT LET PIPE FIXING WIP | RADHE CONSTRUCTION | WIP | 8
38 | THANABHAWAN | KHIYARI | FINSH/ROAD CROSSING PENDING | 150KL 12MTR | Approved | COMP. | YES | YES | WIP | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING/after pump lowering | PENDING | PENDING | PENDING | PENDING | PENDING | COMPLETED | PENDING | EXCAVATION DONE | SHRI RAM | STOP
39 | SHAMLI | JALALPUR | FINISH | 150KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | YES | YES | YES | YES | YES | YES | YES | YES | COMPLETED | COMPLETED | PENDING | YES | YES | COMPLETED | PENDING | WATER TESING | SUBODH TYAGI JI/ RADHE CONSTRUCTION | WIP | 4
40 | SHAMLI | KARORI MEHARAMPUR | FINISH | 175KL 12MTR | Approved | COMP. | YES | YES | COMPLETE |  | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING |  |  | WIP | PENDING | PCC DONE | SD CONSTRUCTION/JSS SACHIN | WIP | 6 | NEW TEAM
41 | SHAMLI | DHANENA NIYAMTULLAPUR | FINISH | 150KL 12MTR | Approved | COMP. | YES | YES | COMPLETE |  | YES | YES | YES | YES | YES | YES | YES | WIP | COMPLETED | PENDING |  |  | COMPLETED | PENDING | UPTO GL | HAMMER/ANKSHRI | STOP
42 | SHAMLI | GOHRANI | WIP | 300KL 14MTR | Approved | COMP. | YES | YES | COMPLETE |  | PENDING | PENDING | WIP | PENDING | PENDING | PENDING | PENDING | PENDING | COMPLETED | PENDING |  |  | COMPLETED | YES | UPTO GL | ANKSHRI | WIP | 6
43 | SHAMLI | KANJARHERI | FINISH | 150KL 12MTR | Approved | COMP. | YES | YES | WIP |  | PENDING | YES | YES | YES | PENDING | PENDING | YES | WIP | COMPLETED | YES | YES |  | COMPLETED | YES | RAFT STEEL FIXING | JAITARA CONTRACTOR | WIP | 5 | NEW TEAM REPERING WORK PENDING
44 | SHAMLI | JANDHERI | FINISH | 125KL 12MTR | Approved | COMP. | YES | YES | WIP |  | PENDING | YES | YES | YES | YES | YES | YES | COMPLETED | COMPLETED | PENDING |  |  | COMPLETED | YES | FULL STAGING | HAMMER | STOP
45 | KAIRANA | BADHEV KANNUKHEDA | FINISH | 350KL 14MTR | Approved | COMP. | YES | YES | COMPLETE |  | PENDING |  | YES | YES | PENDING | YES | YES | WIP | COMPLETED | PENDING |  |  | COMPLETED | PENDING | FULL STAGING | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | STOP |  | PLINTH PROTCATION PENDING
46 | KAIRANA | TITOLI | FINISH/FHTC REPAIRING PENDING/LEAKAGE REPAIRING PENDING | 325KL/14MTR | Approved | COMP. | YES | YES | WIP |  | YES |  | YES | YES | YES | YES | YES | COMPLETED | COMPLETED | PENDING | YES | COMPLETED | COMPLETED | PENDING | UPTO GL | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP | 3 | PLINTH PROTCATION PENDING |  | 3
47 | KAIRANA | GOGWAN | WIP | 500KL14MTR | Approved | COMP. | YES | YES | COMPLETE |  | PENDING |  | LAND NOT SUFFICIENT | PENDING | PENDING | PENDING | PENDING | PENDING | COMPLETED | PENDING |  |  | COMPLETED | PENDING | PENDING | ANKSHRI | PENDING | STAYE | PLINTH PROTCATION PENDING
48 | KAIRANA | GANDRAV | FINISH/PROBLEM IN DRAINS | 300KL 12 MTR | Approved | COMP. | YES | YES | COMPLETE |  | PENDING |  | YES | YES | YES | YES | YES | COMPLETED | WIP | PENDING |  |  | COMPLETED | PENDING | UP TO RAFT | VAYOM/JANARDHAN | WIP | 7 | WIP/ PUMP PLIASTER COM
49 | KAIRANA | BIBIPUR HATIYA | FINISH | 175KL 16 MTR | Approved | COMP. | YES | YES | WIP |  | PENDING |  | YES | YES | YES | YES | YES | COMPLETED | COMPLETED WITH PAINT | YES |  |  | COMPLETED | PENDING | EXCAVATION DONE | ANKSHRI | WIP | 3 | PUME HOUSE ONLY WHITE WASH
50 | KAIRANA | BASERA NON ALLVVIAL | FINISH | 250KL 14 MTR | Approved | COMP. | YES | YES | COMPLETE |  | YES |  | YES | YES | YES | YES | YES | WIP | COMPLETED | YES | YES | COMPLETED | COMPLETED | PENDING | UP TO GL | VAYOM | STOP
51 | KAIRANA | BARNAVI PATHR & MUKUNDPUR | FINISH/LEAKAGE REPAIRING/FHTC REPAIRING | 350KL/16MTR | Approved | COMP. | YES | YES | COMPLETE |  | PENDING |  | YES | YES | YES | YES | YES | WIP | WIP | PENDING |  |  | COMPLETED | YES | UPTO FIRST BRACE | SWAROOPA | STOP | 2023-12-03
52 | KAIRANA | KASERWAKHURD | WIP/STAY | 300KL16MTR | Approved | COMP. | YES | YES | WIP |  | PENDING |  | STAY | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING |  |  | WIP/STAY | PENDING | EXCAVATION COMPLETED | ANKSHRI | WIP | 3
53 | KANDHLA | LOHARIPUR | FINISH | 125KL 12 MTR | Approved | COMP. | YES | YES | WIP | PENDING | PENDING | PENDING | YES | YES | YES | YES | YES | WIP | PENDING | PENDING |  |  | COMPLETED | YES | UPTO 2ND BRACE BEAM WIP | DEPARTMANTAL/ SD CONSTRUCTION/ JANARADHAN FOOD MILL | STOP |  |  | 7
54 | KANDHLA | RASULPUR GURJAN | WIP | 150KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | PENDING | WIP | YES | YES | YES | YES | YES | PENDING | COMPLETED | PENDING |  |  | COMPLETED | PENDING | UPTO 2ND BRACE BEAM WIP | DEPARTMANTAL/SD CONSTRUCTION/JANARDHAN FOOD MILL | STOP | pume house only wite wash, boundary wall only plaster
55 | KANDHLA | MIMLA TALAB | FINISH | 175KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | PENDING | PENDING | YES | YES | YES | PENDING | YES | WIP | COMPLETED | PENDING |  |  | COMPLETED | PENDING | 1ST BRACE BEAM R/F FIXING | DEPARTMANTAL/ CHANDAN GUPTA/SD CONSTRUCTION/ JANARDHAN FOOD MILL | STOP | pume house only wite wash, boundary wall only plaster |  | 6
56 | KANDHLA | RAMPUR KHEDI | FINISH | 175KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | PENDING | YES | YES | YES | YES | YES | YES | COMPLETED | COMPLETED | PENDING | YES |  | COMPLETED | PENDING | UPTO GL | SD CONSTRUCTION/JANARDHAN FOOD MILL | STOP | pume house only wite wash, boundary wall only plaster
57 | KANDHLA | HURMAJPUR URF SHAHPUR | FINISH | 150KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | PENDING | YES | YES | PENDING | PENDING | YES | YES | WIP | WIP | PENDING | YES |  | COMPLETED | PENDING | FULL HEIGHT | DEPARTMANTAL/ SONU GUPTA/ JANARDHAN FOOD MILL | STOP | PLINTH PROTCATION PENDIG,BOUNDARY WALL COPING WIP
58 | KANDHLA | PANJOKHERA | WIP | 200 KL 12 MTR | Approved | COMP. | YES | YES | COMPLETE | YES | PENDING | PENDING | YES | YES | YES | YES | PENDING/15.011.24 | PENDING | COMPLETED | PENDING |  |  | COMPLETED | PENDING | TOP DOME COMPLETD ( STAIR CASE UP 4TH FLIGHT ) | VAYOM /RAVIS | STOP | PLINTH PROTCATION PENDIG
59 | KANDHLA | BRAHAM KHERA | WIP | 125KL 12 MTR | Approved | COMP. | YES | YES | WIP | YES | PENDING | PENDING | WIP | PENDING | PENDING | PENDING | PENDING/10.01.24 | PENDING | COMPLETED | PENDING |  |  | COMPLETED | YES | UPTO 2ND BRACE BEAM | SD CONSTRUCTION/JANARDHAN FOOD MILL | STOP | PLINTH PROTCATION PENDIG
60 | KANDHLA | ISSOPUR TEEL | WIP | 300KL 12MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | PENDING | PENDING | WIP | PENDING | PENDING | PENDING | PENDING/05.01.24 | PENDING | YET TO BE STARTED | PENDING |  |  | COMPLETED | PENDING | UPTO GL | VAYOM /RAVIS | STOP/NEED ELECTRICAL LINE SHIFTING | PLASTER AND OTHER WORK PENDING | NEW TEAM
61 | UNN | KAMALPUR | FINISH | 100KL 12MTR | Approved | COMP. | YES | YES | WIP | YES | YES | YES | YES | YES | YES | YES | YES | COMPLETED | WIP | PENDING |  |  | COMPLETED | YES | UPTO NGL | SKYLINE | STOP
62 | UNN | SANPLA | FINISH | 100KL 14 MTR | Approved | COMP. | YES | YES | WIP | YES | YES | YES | YES | YES | YES | PENDING | YES | COMPLETED | COMPLETED | YES |  |  | COMPLETED | YES | UP GL | CS INFRA | WIP | MANPOWER PROBELEM
63 | UNN | BHOGI MAZRA | FINISH | 100KL 10MTR | Approved | COMP. | YES | YES | WIP | YES | PENDING | YES | YES | YES | YES | PENDING | YES | COMPLETED | COMPLETED | PENDING |  |  | COMPLETED | PENDING | COLUMN ABOVE 1RST BRACE BEAM TO 2ND BRACE BEAM BOTTOM | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP
64 | UNN | SAKAUTI | FINISH | 150KL 12MTR | Approved | COMP. | YES | YES | WIP | YES | YES | YES | YES | YES | YES | YES | YES | COMPLETED | COMPLETED | PENDING | YES | COMPLETED | COMPLETED | YES | 2ND BRACE BEAM ( WIP ) | SKYLINE | WIP
65 | UNN | KALAMAZRA-AZIZPUR | FINISH | 275KL16MTR | Approved | COMP. | YES | YES | COMPLETE | PENDING | PENDING | PENDING | YES | YES | PENDING | PENDING | YES | WIP | COMPLETED | PENDING |  |  | COMPLETED | PENDING | 2ND BRACE BEAM ABOVE COLUMN CASTING | RS CONSTRUCTION (JB) | WIP
66 | UNN | DARGAHPUR | WIP | 200KL14MTR | Approved | COMP. | YES | YES | WIP | YES | PENDING | PENDING | YES | YES | YES | PENDING | YES IN 1 MAJRA | PENDING | WIP | PENDING |  |  | COMPLETED | PENDING | FULL STAGING DONE | RS CONSTRUCTION (JB) | STOP | MANPOWER PROBELEM
67 | UNN | RAJHAR | WIP | 350KL 14MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING | PENDING | YES | YES | PENDING | PENDING | PENDING/05.01.24 | PENDING | PENDING | PENDING |  |  | COMPLETED | PENDING | BOTTOM DOME RCC COMPLET | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP
68 | UNN | ULLANI BINAMAJRA | FINISH | 275KL/16MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING | PENDING | YES | YES | YES | PENDING | YES | WIP | PENDING | PENDING |  |  | COMPLETED | YES | 1ST BRACE BEAM R/F FIXING | DEV CONSTRUCTION | WIP |  | FOR VALVE & TAB & GI FITING FIXING WITH FHTC 4 WORKER FOR 20 DAYS
69 | UNN | SINGRA | WIP/1 MAJRA PENDING FROM JB SIDE / JB NOT INTRESTED | 250 KL 14 MTR | Approved | COMP. | YES | YES | YES | PENDING | YES | YES | PENDING | PENDING | YES | PENDING | YES ( LEKEGE WIP ) | PENDING | PENDING | PENDING |  |  | COMPLETED | PENDING | UPTO FULL HEIGHT ( STAIR CASE WIP | RS CONSTRUCTION (JB) | WIP |  | NEW TEAM
70 | UNN | PELKHA | FINSH | 200KL 16MTR | Approved | COMP. | YES | YES | YES | YES | PENDING | YES | YES | YES | YES | PENDING | YES | WIP | WIP | PENDING | YES | COMPLETED | COMPLETED | PENDING | 4TH BRACE BEAM WIP | JSS SACHIN | WIP
71 | UNN | RANGANA | WIP/CONTRACTOR NOT INTRESTED/ LAYING PENDING | 300KL 12MTR | Approved | COMP. | YES | YES | YES | YES | YES | PENDING | YES | YES | YES | PENDING | PENDING/08.01.24 | PENDING | COMPLETED | PENDING |  |  | COMPLETED | PENDING | FULL STAGING DONE ( WITH STAIR CASE ) | RS CONSTRUCTION (JB) | STOP |  | NEW TTEAM
72 | UNN | DULLAKHEDI | FINISH | 250KL 14MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING | YES | YES | YES | YES | PENDING | YES | COMPLETED | PENDING | PENDING |  |  | COMPLETED | PENDING | BOTTOM DOME WIP ( STAIR CASE WIP ) | RADHE CONSTRUCTION | WIP
73 | UNN | AMBETHA RIDAN | FINISH | 275KL14MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING | PENDING | YES | YES | YES | PENDING | YES | WIP | COMPLETED | PENDING |  |  | COMPLETED | PENDING | UPTO NGL | RADHE CONSTRUCTION | STOP | MANPOWER PROBELEM
74 | UNN | AKARPUR URF FUSGARH | WIP/CONTRACTOR NOT INTRESTED/ LAYING PENDING | 125KL 12MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING | PENDING | YES | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING |  |  | COMPLETED | PENDING | RAFT R/F FIXING | DEV CONSTRUCTION | STOP
75 | THANABHAWAN | TITARSI PAWERKHERA | FINISH | 150KL 12MTR | Approved | COMP. | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | COMPLETED | COMPLETED | PENDING | YES | PENDING | COMPLETED | YES | COLUMN CASTING UPTO GL | HD CONSTRUCTION/NISHANT | STOP
76 | THANABHAWAN | KHANPUR | FINISH | 150KL 12MTR | Approved | COMP. | YES | YES | YES | YES | YES | YES | YES | YES | YES | PENDING | YES/28.12.23 | WIP | COMPLETED | PENDING | YES | PENDING | COMPLETED | PENDING | PCC DONE | VEERPRATAP/JANARDHAN | WIP | 5
77 | THANABHAWAN | NAGAL ISMAILPUR | WIP | 175KL 12MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING/after pump lowering | PENDING | PENDING | PENDING | PENDING | PENDING | WIP | PENDING | RAFT RING BEAM PENDING | VEERPRATAP/SHRI RAM | STOP
78 | THANABHAWAN | DABHERI | WIP | 125KL 12MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING/LAND ISSUE | NOT ALLOTED | LAND ISSUE
79 | SHAMLI | ADAMPUR | FINSH/PWD ROAD PENDING | 125KL 12MTR | Approved | COMP. | YES | YES | YES |  | YES | PENDING | YES | YES | PENDING | PENDING | PENDING | PENDING | COMPLETED | PENDING |  |  | COMPLETED | PENDING | RAFT STEEL FIXING | SHRI RAM | WIP | 8
80 | SHAMLI | BHIKKI MAJARA | WIP | 150KL 14MTR | Approved | COMP. | YES | YES | PENDING |  | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING |  |  | COMPLETED | PENDING | UPTO GL | AADI SHAKTI | STOP |  | NEW TEAM FOR WITH HDD
81 | KANDHLA | ALDI | FINISH | 325KL 14MTR | Approved | COMP. | YES | YES | YES | PENDING | YES | YES | PENDING | PENDING | PENDING | PENDING | YES | WIP | WIP | PENDING |  |  | COMPLETED | PENDING | TOP DOME COMPLETD ( STAIR CASE UP 10TH FLIGHT WIP ) | GUPTA JI | WIP | 5 | ABOVE PINTH B/W WIP |  | 5
82 | KANDHLA | GUJJARPUR-FATEHPUR | FINISH/ EXCEPTING FATEHPUR | 175KL12MTR | Approved | COMP. | YES | YES | YES | PENDING | YES | YES | YES | YES | YES | YES | YES | COMPLETED | COMPLETED | PENDING |  |  | COMPLETED | PENDING | COLUMN CASTING UPTO GL | DEPARTMANTAL/BHATIYA JI/LEFT THE WORK | STOP/NEED ELECTRICAL LINE SHIFTING |  | PUMP HOUSE ONLY WHITEE WASH,BOUNDARY ONLY PLASTER
83 | KANDHLA | BHARSI | FINISH | 300KL 12MTR | Approved | COMP. | YES | YES | YES | YES | PENDING | YES | YES | YES | YES | YES | YES | COMPLETED | COMPLETED | PENDING |  |  | COMPLETED | PENDING | BOTTOM DOM R/F FIXING | VAYOM /RAVIS | STOP |  | PUMP HOUSE ONLY WHITEE WASH,BOUNDARY ONLY PLASTER
84 | KANDHLA | KHERA KURTAN | WIP | 275KL 12MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING | YES | YES | YES | PENDING | PENDING | PENDING/01.01.24 | PENDING | COMPLETED | PENDING | YES |  | COMPLETED | PENDING | FULL STAGING | VAYOM /RAVIS | STOP |  | PUMP HOUSE ONLY WHITEE WASH,BOUNDARY ONLY PLASTER
85 | UNN | NAI NAGLA NAVEEN | FINISH | 175KL 16 MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING | PENDING | WIP | PENDING | PENDING | PENDING | PENDING/after pump lowering | PENDING | PENDING | PENDING |  |  | COMPLETED | PENDING | STEEL CUTTING & BENDING | DEV CONSTRUCTION | STOP |  | KAMIL JI
86 | UNN | SIKANDARPUR | FINISH | 125KL 12MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING | YES | YES | YES | YES | PENDING | YES | COMPLETED | WIP | PENDING |  |  | COMPLETED | PENDING | UPTO NGL | RS CONSTRUCTION (JB) | STOP | 2023-12-10
87 | UNN | DABHEDHI BAJURGA URF TISANG | FINISH | 175KL 16 MTR | Approved | COMP. | YES | YES | YES | YESS | PENDING | YES | YES | YES | YES | PENDING | YES | PENDING | COMPLETED | YES |  |  | COMPLETED | YES | BOTTOM DOME WIP | ANKSHRI | WIP
88 | UNN | PATNI PRATAPUR | FINISH/HIGHWAY WORK PENDING | 350KL 16MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING | PENDING | YES | YES | YES | PENDING | YES ( LEKEGE WIP ) | PENDING | COMPLETED | PENDING |  |  | COMPLETED | PENDING | UP TO FULL HIGHT | RS CONSTRUCTION (JB) | WIP |  | NEW TEAM
89 | UNN | RAJAK NAGAR | FINISH/PROBLEM IN MAIN LINE LAYING | 150KL 12MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING/local hindrance | COMPLETED | PENDING | PENDING |  |  | PENDING | PENDING | UP TO FULL HIGHT | SHRI RAM | WIP
90 | UNN | YOSUFPUR URF CHAUTRA | FINISH EXCEPTING IRRIGATION DEPARTMENT AREA | 175KL 12MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING |  | WIP | PENDING | PENDING | PENDING | PENDING/partial portion 05.01.23 | PENDING | PENDING | PENDING |  |  | WIP | PENDING | UP TO GL | SHRI RAM | WIP
91 | THANABHAWAN | KAJIPURA,THIRWA,JASANA URF MASTGARH | WIP | 250KL 12 MTR | Approved | COMP. | YES | YES | YES | YES | PENDING | YES | YES | YES | YES | PENDING | YES | WIP | WIP | PENDING | PENDING | PENDING | COMPLETED | PENDING | TOP DOME WIP | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP | 11
92 | THANABHAWAN | NOJAL NJALI | WIP | 275KL 16MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING | PENDING | ELECTRICAL | PENDING | PENDING | PENDING | PENDING/ELECTRICAL CONNECTION | PENDING | PENDING | PENDING | PENDING | PENDING | COMPLETED | PENDING | UPTO NGL | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | STOP
93 | SHAMLI | KHERI KARMU | WIP/STATE HIGHWAY WORK PENDING | 375KL 16MTR | Approved | COMP. | YES | YES | YES |  | PENDING | PENDING | ELECTRICAL | PENDING | PENDING | PENDING | PENDING | PENDING | COMPLETED | PENDING | YES |  | WIP | PENDING | EXCAVATION DONE | RADHE CONSTRUCTION | STOP
94 | SHAMLI | GOHARPUR | FINISH | 75KL 12MTR | Approved | COMP. | YES | YES | YES |  | PENDING |  | ELECTRICAL | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING |  |  | COMPLETED | PENDING | 3RD BRACE BEAM AVOBE COLUMN WIP | SHRI RAM | WIP | 8
95 | KAIRANA | MANNA MAZRA | WIP | 300KL 16MTR | Approved | COMP. | YES | YES | YES |  | PENDING |  | YES | YES | YES | PENDING | PENDING | PENDING | COMPLETED | PENDING | YES | COMPLETED | COMPLETED | PENDING | UP GL | SAMRESH BALA | STOP
96 | KAIRANA | RAMRA | FINISH/EXCEPTING PWD ROAD | 500KL 14 MTR | Approved | COMP. | YES | YES | YES |  | PENDING |  | YES | YES | YES | PENDING | PENDING | PENDING | WIP | PENDING |  |  | COMPLETED | PENDING | UPTO GL | GUPTA JI | STOP
97 | KAIRANA | JHARKHERI | FINISH/FHTC REPAIRING PENDING | 225KL 14MTR | Approved | COMP. | YES | YES | YES |  | YES |  | WIP | PENDING | YES | PENDING | PENDING | PENDING | YET TO START | PENDING |  |  | COMPLETED | PENDING | BOTTOM DOME WIP | VISHAL JJM | WIP | 7 |  |  | 7
98 | KAIRANA | JANGHERI | FINSH/FHTC REPAIRING | 225KL16MTR | Approved | COMP. | YES | YES | YES |  | PENDING |  | YES | YES | YES | YES | YES | COMPLETED | WIP | PENDING |  |  | COMPLETED | YES | UPTO 2ND BRACE BEAM | VAYOM | STOP
99 | KAIRANA | BADHUPURA | FINSH | 200KL 16MTR | Approved | COMP. | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | COMPLETED | WIP | PENDING |  |  | COMPLETED | YES | ABOVE 1RST BRACE BEAM COLUMN WIP | SWAROOPA | WIP | BOUNDRAY WAAL PLASTER ( 5 ) |  |  | 5
100 | KAIRANA | MANDAWAR | FINSH | 250KL 14 MTR | Approved | COMP. | YES | YES | YES |  | YES |  | YES | YES | YES | PENDING | YES | WIP | COMPLETED | PENDING |  |  | COMPLETED | PENDING | FULL STAGING | VAYOM | STOP
101 | KAIRANA | ALIPUR | STOP | 375KL 14MTR | Approved | COMP. | YES | YES | YES |  | PENDING |  | YES | YES | YES | PENDING | PENDING | PENDING | COMPLETED | PENDING | YES | COMPLETED | COMPLETED | PENDING | UPTO GL | SAMRESH BALA | STOP |  | NEW TEAM
102 | KAIRANA | ERTI | FINISH | 175KL 12MTR | Approved | COMP. | YES | YES | YES |  | PENDING |  | YES | YES | YES | PENDING | WIP | PENDING | COMPLETED | PENDING | YES | COMPLETED | COMPLETED | PENDING | UPTO GL | SAMRESH BALA | STOP
103 | KAIRANA | MOHAMMADPUR RAI | FINISH/FHTC REPAIRING | 325KL 16MTR | Approved | COMP. | YES | YES | PENDING |  | PENDING |  | YES | PENDING | PENDING | PENDING | YES | WIP | COMPLETED | PENDING | YES | COMPLETED | COMPLETED | PENDING | 4TH BRACE BEAM WIP | VISHAL JJM | WIP | 10
104 | KAIRANA | PAOTIKALAN | WIP | 500KL 14MTR | Approved | COMP. | YES | YES | PENDING |  | PENDING |  | CLEAR FOR SOLAR | PENDING | PENDING | PENDING | PENDING | PENDING | YET TO START | PENDING |  |  | COMPLETED | PENDING | PENDING | RADHE CONSTRUCTION | LAND DISPUTE
105 | KAIRANA | NAGLA RAI | FINISH | 225KL 16MTR | Approved | COMP. | YES | YES | YES |  | YES |  | TREE CLEARANCE | PENDING | PENDING | PENDING | YES | COMPLETED | YET TO START | PENDING |  |  | COMPLETED | PENDING | UP TO STAGING ( 2ND FLIGHT STAIR CASE WIP ) | ANKSHRI | WIP | 1900-01-07
106 | KAIRANA | MAWI NON AHATMAL | WIP | 250KL 16MTR | Approved | COMP. | YES | YES | YES |  | PENDING |  | YES | YES | PENDING | PENDING | PENDING | PENDING | WIP | PENDING |  |  | COMPLETED | PENDING | EXCAVATION DONE | ANKSHRI | STOP
107 | KAIRANA | UNCHA GAON | WIP | 400KL 16MTR | Approved | COMP. | YES | YES | YES |  | PENDING |  | WIP | PENDING | PENDING | PENDING | PENDING | PENDING | WIP | PENDING |  |  | COMPLETED | PENDING | UPTO FIRST BRACE | VAYOM /ANKSHRI | WIP | 4
108 | KAIRANA | BINDA(BENRA) | FINSIH | 50KL 12MTR | Approved | COMP. | YES | YES | YES |  | PENDING |  | ELECTRICAL | PENDING | PENDING | PENDING | PENDING | COMPLETED | WIP | PENDING | YES | COMPLETED | COMPLETED | PENDING | UPTO GL | SAMRESH BALA | STOP
109 | KAIRANA | JAHANPUR | WIP | 250KLK14MTR | Approved | COMP. | YES | YES | YES |  | PENDING |  | YES | PENDING | PENDING | PENDING | PENDING | PENDING | COMPLETED | PENDING | YES | COMPLETED | COMPLETED | PENDING | BOTTOM DOM R/F FIXING | ANKSHRI | WIP | 7
110 | UNN | UD PUR | FINISH | 250KL18MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING |  | WIP | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING |  |  | WIP | PENDING | PCC COMPLETED | RS CONSTRUCTION (JB) | STOP |  | NEW TEAM
111 | UNN | KHANPUR JATAN | FINISH | 275KL/14MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING |  | WIP | PENDING | PENDING | PENDING | PENDING/HEADER NOT CONNECTED DUE TO OHT WORK | PENDING | PENDING | PENDING |  |  | COMPLETED | PENDING | 1SR BARCE BEAM WIP | RS CONSTRUCTION (JB) | WIP | 2023-12-04 | NEW TEAM
112 | UNN | MIYAN KASBA | WIP/SHRI MITHI MP | 325KL 12 MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING |  | WIP | PENDING | PENDING | PENDING | PENDING/NH PERMISSION | PENDING | PENDING | PENDING |  |  | WIP | PENDING | RAFT COMPLETED | DEV CONSTRUCTION | STOP |  | HDD TEAM FOR NH
113 | UNN | DOKPURA | FINISH | 150KL 16MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING |  | WIP |  |  | PENDING | PENDING/CONTRACTOR LEFT WORK | PENDING | PENDING | PENDING |  |  | WIP | PENDING | 2ND BRACE BEAM R/F FIXING | ANKSHRI | WIP | 2023-12-04 | NEW TAM
114 | UNN | CHONDA HERI,NAUNAGALI | WIP/ DEMAND SEPRATE OHT | 225KL 14MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING |  | WIP |  |  | PENDING | PENDING/ONLY 1 MAZARA | PENDING | YET TO BE STARTED | PENDING |  |  | COMPLETED | PENDING | UPTO FULL HEIGHT | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP
115 | THANABHAWAN | PALTHERI | WIP | 250 KL12 MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING | PENDING | WIP | PENDING | PENDING | PENDING | PENDING/10.01.24 | PENDING | WIP | PENDING | PENDING | PENDING | WIP | PENDING | PAINTAING WIP | SWAROOPA | STOP
116 | THANABHAWAN | JALALABAD RURAL | BOREWELL PENDING | 200KL14MTR | Approved | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING/BOREWELL PENDING | NOT ALLOTED | LAND ISSUE
117 | THANABHAWAN | ABDULLAPUR URF MOURMAJRA | BOREWELL PENDING | 150KL 12MTR | Approved | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING/BOREWELL PENDING | NOT ALLOTED | LAND ISSUE
118 | SHAMLI | KHANPUR. | WIP | 175KL 12MTR | Approved | COMP. | YES | YES | PENDING |  | PENDING | PENDING | PENDING | PENDING |  | PENDING | PENDING | PENDING | WIP | PENDING |  |  | YES | PENDING | EXCAVATION DONE | ANKSHRI | WIP | 6
119 | KAIRANA | DABHERI KHURD | FINISH | 150KL 14MTR | Approved | COMP. | YES | YES | YES |  | PENDING |  | WIP |  |  | PENDING | PENDING | PENDING | COMPLETED | PENDING |  |  | COMPLETED | PENDING | UP TO GL | SWAROOPA | STOP
120 | UNN | ODRI | WIP/AABID | 300KL12MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING |  | PENDING |  |  | PENDING | PENDING/10.01.24 | PENDING | YET TO BE STARTED | PENDING |  |  | WIP | PENDING | EXCAVATION WIP | ANKSHRI | WIP
121 | UNN | BHARI MUSTAFABAD | WIP/PERMISSION FROM IRRIGATION DEPARTMENT | 350KL 18MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING |  | PENDING |  |  | PENDING | PENDING/1 MAZARA after pump lowering | WIP | YET TO BE STARTED | PENDING |  |  | WIP | PENDING | RAFT REINFORCEMENT | DEV CONSTRUCTION | WIP
122 | UNN | MACHRAULI | FINISH | 125KL12MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING |  | PENDING |  |  | PENDING | PENDING/TESTING PENDING FROM VENDOR SIDE | PENDING | Yet to be Started | PENDING |  |  | PENDING | PENDING | UPTO GL | DEV CONSTRUCTION | WIP
123 | UNN | PEER KHERA | FINISH | 125KL12MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING |  | WIP |  |  | PENDING | PENDING/SOLAR WIP | PENDING | YET TO BE STARTED | PENDING |  |  | WIP | PENDING | COLUMN UP TO STAJING LEVEL WIP | SHRI RAM | WIP
124 | UNN | BHATU | WIP/AMAN ENTERPRISES | 175KL12MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING |  | PENDING |  |  | PENDING | PENDING | PENDING | Yet tobe started | PENDING |  |  | WIP | PENDING | RAFT REINFORCEMENT WIP | ANKSHRI | WIP
125 | UNN | MANSURA | WIP/SARAFAT | 275KL14MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING |  | WIP |  |  | PENDING | PENDING/10.01.24 | PENDING | YET TO BE STARTED | PENDING |  |  | WIP | PENDING | UPTO GL | SKYLINE | STOP
126 | UNN | BAJHERI | WIP/MUNDET PRADHAN | 100KL 12 MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING |  | PENDING |  |  | PENDING | PENDING/SOLAR INSTLLATION PENDING | PENDING | PENDING | PENDING |  |  | WIP | PENDING | 1ST BRACE BEAM R/F FIXING | CS INFRA | WIP
127 | UNN | KHERA BAHU | FINISH | 150KL16MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING |  | YES |  |  | PENDING | YES | COMPLETED | PENDING | PENDING |  |  | COMPLETED | PENDING | UPTO 2ND BRACE BEAM | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP
128 | UNN | PANTHU PURA | WIP | 225KL 16MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING |  | WIP |  |  | PENDING | YES IN 1 MAJRA | WIP | PENDING | PENDING |  |  | WIP | PENDING | COLUMN ABOVE 1RST BRACE BEAM TO 2ND BRACE BEAM BOTTOM | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP
129 | UNN | HATH CHHOYA | WIP/CHOUDHARY | 450KL18MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING |  | PENDING |  |  | PENDING | YES | PENDING | PENDING | PENDING |  |  | COMPLETED | PENDING | UPTO NGL | RADHE CONSTRUCTION | STOP
130 | THANABHAWAN | AMBEHTA YAKUBPUR | BOREWELL PENDING | 275KL14MTR | Approved | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING/BOREWELL PENDING | DHANVI COMSTRUCTION(ANKSHRI) | LAND ISSUE
131 | THANABHAWAN | BUNTA | WIP | 300KL12MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING | PENDING | ELECTRICAL | PENDING | PENDING | PENDING | PENDING | PENDING | COMPLETED | PENDING | YES | YES | WIP | PENDING | PENDING | MAYANK | STOP/NEED ELECTRICAL LINE SHIFTING
132 | THANABHAWAN | HIND | WIP | 500KL16MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | WIP | PENDING | PENDING | PENDING | WIP | PENDING | RAFT DONE | SWAROOPA | STOP
133 | THANABHAWAN | AHAMADPUR | FINISH/ROAD CROSSING PENDING | 200KL12MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING | PENDING | WIP | PENDING | PENDING | PENDING | PENDING | COMPLETED | COMPLETED | PENDING | YES | YES | WIP | PENDING | UPTO GL | ST ENTERPRISES | STOP
134 | THANABHAWAN | MADALPUR | WIP | 175KL12MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | WIP | PENDING | ABOVE 3rd BRACE BEAM COLUMN WIP | ST ENTERPRISES | WIP | 6
135 | THANABHAWAN | USMANPUR | BOREWELL PENDING | 150KL 12MTR | Approved | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING/BOREWELL PENDING | NOT ALLOTED | LAND ISSUE
136 | THANABHAWAN | GURANA | WIP | 75KL 12MTR | Approved | COMP. | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | ELECTRICAL | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING/APPROACH ROAD ISSUE | SWAROOPA | APPROACH ROAD ISSUE
137 | THANABHAWAN | KADARPUR | FINISH | 50KL12MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING | PENDING | ELECTRICAL | PENDING | PENDING | PENDING | PENDING/after pump lowering | PENDING | PENDING | PENDING | PENDING | PENDING | COMPLETED | PENDING | PENDING/LAND ISSUE | SWAROOPA | LAND DISPUTE/SUFFICIENT SPACE NOT AVAILABLE
138 | KAIRANA | PANJETH | WIP | 325KL12MTR | Approved | COMP. | YES | YES | YES |  | PENDING |  | WIP |  |  | PENDING | PENDING | PENDING | COMPLETED | PENDING | YES | COMPLETED | COMPLETED | YES | UPTO GL | VISHAL JJM | STOP DUE TO ELECTRICAL WIER
139 | KAIRANA | SAHPAT NON AHMATMAL | WIP | 200KL 12MTR | Approved | COMP. | YES | YES | PENDING |  | PENDING |  | PENDING |  |  | PENDING | PENDING | PENDING | YET TO START | PENDING |  |  | WIP | PENDING | BOTTOM DOM R/F FIXING | ANKSHRI | WIP
140 | KAIRANA | MUNDET KALAN | WIP/STAY | 350KL12MTR | Approved | COMP. | PENDING/STAY | PENDING | PENDING |  | PENDING |  | PENDING |  |  | PENDING | PENDING | PENDING | YET TO START | PENDING |  |  | PENDING | PENDING | PENDING/CONTRACTOR REQUIRED | STAY | STAY FROM COURT
141 | KAIRANA | MALAKPUR | WIP | 250KL12MTR | Approved | COMP. | YES | YES | PENDING |  | PENDING |  | PENDING |  |  | PENDING | PENDING | PENDING | YET TO START | PENDING |  |  | WIP | PENDING | 2ND BRACE BEAM ( WIP ) | ANKSHRI | WIP | 1900-01-05
142 | KAIRANA | KASERWA KALAN | FINISH | 275KL16MTR | Approved | COMP. | YES | YES | YES |  | PENDING |  | YES |  |  | PENDING | YES | COMPLETED | YET TO START | PENDING |  |  | COMPLETED | PENDING | UPTO GL | SWAROOPA | STOP
143 | KANDHLA | KHANDARAWALI | PENDING | 350KL16MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING | PENDING | ELECTRICAL | PENDING | PENDING | PENDING | PENDING | PENDING | YET TO BE STARTED | PENDING |  |  | COMPLETED | PENDING | EXCAVATION WIP | ANKSHRI | STOP |  | PUMP HOSE ONLY WHITE WASH
144 | KANDHLA | ASADPUR & BARNAULI | FINISH | 125KL12MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | YES | PENDING | COMPLETED | YES | YES | YES | COMPLETED | YES | 2ND BRACE BEAM ( WIP ) | CHANDAN GUPTA/SONU GUPTA | WIP | 6 |  |  | 5
145 | KANDHLA | AMBETHA ASADPUR | WIP | 50KL12MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING | PENDING | ELECTRICAL | PENDING | PENDING | PENDING | YES | PENDING | COMPLETED | YES |  |  | COMPLETED | YES | UPTO GL | CHANDAN GUPTA/SONU GUPTA / JANARDHAN FOOD MILL | STOP |  | BORD & GATE FIXING PENDING
146 | KANDHLA | ISLAMPUR GHASAULI | FINISH | 325KL16MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | YES | PENDING | YET TO BE STARTED | PENDING |  |  | COMPLETED | YES | 2ND BRACE BEAM ( WIP ) | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP | 6 |  |  | 6
147 | UNN | BASI CHUNDYARI | WIP/SWAROOPA | 250KL 14MTR | Approved | COMP. | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING |  |  | PENDING | PENDING | RAFT R/F FIXING | SHRI RAM | WIP
148 | UNN | RATAUNDH BIBIPUR | WIP | 175KL12MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING |  |  | WIP | PENDING | Raft RCC COMPLET | ANKSHRI | WIP
149 | KAIRANA | BARAALA KUKKARHERI | WIP | 375KL12MTR | Approved | COMP. | WIP | PENDING | PENDING |  | PENDING |  | PENDING |  |  | PENDING | PENDING | PENDING | YET TO START | PENDING |  |  | PENDING | PENDING | EXCVATION WIP | ANKSHRI | WIP | 5
150 | KAIRANA | MAMOUR NON AHT | WIP | 250KL12MTR | Approved | COMP. | YES | YES | PENDING |  | PENDING |  | PENDING |  |  | PENDING | PENDING | PENDING | YET TO START | PENDING |  |  | WIP | PENDING | Above 2nd brace beam column wip | ANKSHRI | WIP | 8
151 | KAIRANA | BAMNOLI SEKHUPURA | FINISH | 75KL/12MTR | Approved | COMP. | YES | YES | YES |  | PENDING |  | ELECTRICAL |  |  | PENDING | PENDING | COMPLETED | YET TO START | PENDING |  |  | COMPLETED | PENDING | UPTO GL | SAMRESH BALA | STOP
152 | KAIRANA | MAWI TIMALI AHT | WIP | 75KL14MTR | Approved | COMP. | YES | YES | PENDING |  | PENDING |  | ELECTRICAL |  |  | PENDING | PENDING | PENDING | YET TO START | PENDING |  |  | WIP | PENDING | PENDING | ANKSHRI | STOP
153 | KANDHLA | I. KANDHLA DEHAT | PENDING | 500KL12MTR | Approved | COMP. | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | YET TO BE STARTED | PENDING |  |  | PENDING | PENDING | COLUMN ABOVE 1ST BRACE BEAM TOP TO 2ND BRCE BEAM BOTTOM | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP | 9 |  |  | 9
154 | KANDHLA | II. ATTA | FINISH | 75KL/12MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING/after pump lowering | PENDING | YET TO BE STARTED | PENDING |  |  | WIP | PENDING | RAFT REINFORCEMENT | SHIVANAND JI | WIP | 4 |  |  | 4
155 | KANDHLA | III. HAJIPUR DUGADDA(SALEMPUR) | WIP | 75KL12MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING/after pump lowering | PENDING | WIP | PENDING |  |  | COMPLETED | PENDING | UPTO 1ST BRACE BEAM | SONU GUPTA/ JANARDHAN FOOD MILL | STOP |  | ONLY EXCVATION
156 | KANDHLA | I. JASALA | BOREWELL PENDING | 425KL12MTR | Approved | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | YET TO BE STARTED | PENDING |  |  | PENDING | PENDING | PENDING | ANKSHRI | BOREWELL PENDING
157 | KANDHLA | II. NANUPURI | FINISH | 50KL12MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING | PENDING | WIP | PENDING | PENDING | PENDING | PENDING | COMPLETED | YET TO BE STARTED | PENDING |  |  | COMPLETED | PENDING | EXCAVATION DONE | ANKSHRI | STOP | 2023-12-04 | ONLY PIASTER
158 | UNN | KABEERPUR AHATMAL | FINISH | 175KL12MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING |  | WIP |  |  | PENDING | PENDING/PUMP NOT RECEIVED | PENDING | PENDING | PENDING |  |  | COMPLETED | PENDING | 3RD BRACE BEAM WIP | SHRI RAM | WIP |  | NEW TEAM
159 | UNN | JAMALPUR | WIP/SYAM MP | 425KL14MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING |  | PENDING |  |  | PENDING | PENDING | PENDING | PENDING | PENDING |  |  | WIP | PENDING | UPTO 2ND BRACE BEAM | BALISTER/JANARDHAN | STOP
160 | UNN | JIJAULA | WIP | 300KL16MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING |  | PENDING |  |  | PENDING | PENDING | PENDING | PENDING | PENDING |  |  | PENDING | PENDING | 2ND BRACE BEAM ( WIP ) | SHRI RAM | WIP
161 | UNN | BIBIPUR JALALABAD | FINISH | 100KL12MTR | Approved | COMP. | PENDING/PROBLEM IN BORE | PENDING | PENDING | PENDING | PENDING |  | PENDING |  |  | PENDING | PENDING/BOREWELL ISSUE | PENDING | PENDING | PENDING |  |  | PENDING | PENDING | EXCVATION WIP | ANKSHRI | WIP | 2023-12-04
162 | UNN | CHAUSANA | WIP | 100KL12MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING |  | WIP |  |  | PENDING | PENDING | PENDING | PENDING | PENDING |  |  | WIP | PENDING | 2ND BRACE BEAM ABOVE COLUMN WIP | SHRI RAM | WIP
163 | UNN | NAI NAGLA SAKAUTI | FINISH | 50KL12MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING |  | ELECTRICAL |  |  | PENDING | PENDING/ELECTRICAL CONNECTION | WIP | PENDING | PENDING |  |  | PENDING | PENDING | 2ND BRACE BEAM WIP | SHRI RAM | WIP
164 | THANABHAWAN | JANIPUR | WIP/ ARHAM | 75KL12MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING | PENDING | ELECTRICAL | PENDING | PENDING | PENDING | PENDING/10.01.24/after pump lowering | PENDING | PENDING | PENDING | PENDING | PENDING | COMPLETED | PENDING | BOTTOM DOM WIP | SWAROOPA | WIP | 5
165 | THANABHAWAN | MULLAPUR | FINISH | 150KL12MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING/30.12.23 | PENDING | COMPLETED | PENDING | YES | PENDING | WIP | PENDING | COLUMN CASTING UPTO GL | HD CONSTRUCTION/SHRI RAM | STOP
166 | SHAMLI | BHANERA JAT | WIP | 225KL16MTR | Approved | COMP. | YES | YES | PENDING |  | PENDING |  | PENDING |  |  | PENDING | PENDING | PENDING | PENDING | PENDING |  |  | WIP | PENDING | BOTTOM DOME WIP | AADI SHAKTI | WIP | 9
167 | SHAMLI | KASAMPUR | PENDING | 50KL12MTR | Approved | COMP. | YES | YES | PENDING |  | PENDING |  | ELECTRICAL |  |  | PENDING | PENDING | PENDING | WIP | PENDING |  |  | WIP | PENDING | UPTO GL | AADI SHAKTI | STOP |  | NEW TEAM FOR WITH HDD
168 | SHAMLI | SAIHATA | WIP | 75KL12MTR | Approved | COMP. | PENDING | PENDING | PENDING |  | PENDING |  | ELECTRICAL |  |  | PENDING | PENDING | PENDING | PENDING | PENDING |  |  | PENDING | PENDING | PENDING | ANKSHRI | STOP
169 | SHAMLI | KHERI BAIRAGI | WIP | 50KL12MTR | Approved | COMP. | YES | YES | YES |  | PENDING |  | ELECTRICAL |  |  | PENDING | PENDING | PENDING | PENDING | PENDING |  |  | WIP | PENDING | EXCAVATION DONE | AADI SHAKTI | STOP | 5
170 | KANDHLA | DUDHAR | FINISH | 175KL12MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING/after pump lowering | PENDING | YET TO BE STARTED | PENDING |  |  | WIP | PENDING | Raft RCC COMPLET | SHIVANAND JI | WIP | 5 | FOUNDATION BRICK WORK |  | 5
171 | KANDHLA | CHADHAW | WIP | 50KL14MTR | Approved | COMP. | YES | YES | PENDING | PENDING | PENDING | PENDING | ELECTRICAL | PENDING | PENDING | PENDING | PENDING/after pump lowering | PENDING | YET TO BE STARTED | PENDING |  |  | WIP | PENDING | UP TO GL | JANARDHAN ORGANIC FOOD MILL (PRATIK JI) | WIP |  | UP TO DPC LEVEL
172 | KANDHLA | MALAKPUR | WIP | 250KL14MTR | Approved | COMP. | YES | YES | YES | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | YES | PENDING | WIP | PENDING |  |  | COMPLETED | WIP | UPTO 1ST BRACE BEAM | SONU GUPTA/ JANARDHAN FOOD MILL | STOP |  | PUMP HOUSE ONLYWHITE WASH
48
I

## Sheet7
S NO | BLOCK | VILLAGE | PIPELAYING STATUS | WATER SUPPLY STATUS
1 | SHAMLI | JALALPUR | FINISH | YES
2 | SHAMLI | DHANENA NIYAMTULLAPUR | FINISH | YES
3 | SHAMLI | KANJARHERI | FINISH | YES
4 | SHAMLI | JANDHERI | FINISH | YES
5 | SHAMLI | KARORI MEHARAMPUR | FINISH | PENDING
6 | SHAMLI | GOHRANI | WIP | PENDING
7 | SHAMLI | ADAMPUR | FINSH/PWD ROAD PENDING | PENDING
8 | SHAMLI | BHIKKI MAJARA | WIP | PENDING
9 | SHAMLI | KHERI KARMU | WIP/STATE HIGHWAY WORK PENDING | PENDING
10 | SHAMLI | GOHARPUR | FINISH | PENDING
11 | SHAMLI | KHANPUR. | WIP | PENDING
12 | SHAMLI | BHANERA JAT | WIP | PENDING
13 | SHAMLI | KASAMPUR | PENDING | PENDING
14 | SHAMLI | SAIHATA | WIP | PENDING
15 | SHAMLI | KHERI BAIRAGI | WIP | PENDING

## FHTC
SNO | BLOCK | VILLAGE | STATUS OF BORE | FHTC SCOPE | FHTC DONE | REMARK
1 | KANDHLA | KHANDRAWALI | COMPLETED | 1565 |  | PIPELAYING NOT STARTED DUE TO PRADHAN ISSUE
2 | THANABHAWAN | AMBHETA YAKUBPUR | PENDING | 618 |  | LAND NOT ALLOTED
3 | SHAMLI | BHANERA JAT | COMPLETED | 527
4 | THANABHAWAN | USMANPUR | PENDING | 350 |  | LAND NOT ALLOTED
5 | THANABHAWAN | JALALABAD RURAL | PENDING | 340 |  | LAND NOT ALLOTED
6 | THANABHAWAN | ABDULLAPUR URF MORJ MAJARA | PENDING | 318 |  | LAND NOT ALLOTED
7 | SHAMLI | KASAMPUR | COMPLETED | 179
8 | UNN | DHINDHALI | COMPLETED | 613 |  | PIPELAYING FROM HDD METHOD
9 | KANDHLA | JASALA | PENDING | 1250 |  | PIPELAYING NOT STARTED DUE TO PRADHAN ISSUE
10 | UNN | SINGRA | COMPLETED | 385
11 | UNN | BHATU | COMPLETED | 405
12 | THANABHAWAN | GURANA | COMPLETED | 304
13 | SHAMLI | BHIKKI MAJARA | COMPLETED | 475
14 | UNN | JAMALPUR | COMPLETED | 912
15 | THANABHAWAN | BUNTA | COMPLETED | 838
16 | THANABHAWAN | JANIPUR | COMPLETED | 221
17 | UNN | TISANG | COMPLETED | 492
18 | KAIRANA | BARALA KUKARHERI | COMPLETED | 784
19 | THANABHAWAN | PALTHERI | COMPLETED | 494
20 | KANDHLA | MALAKPUR | COMPLETED | 20
21 | THANABHAWAN | MADALPUR | COMPLETED | 366
22 | UNN | RANGANA | COMPLETED | 848
23 | THANABHAWAN | HIND | COMPLETED | 1200

## Sheet6
S No | BLOCK | VILLAGE | PIPELAYING STATUS | WATER SUPPLY STATUS
1 | KANDHLA | LOHARIPUR | FINISH | YES
2 | KANDHLA | RASULPUR GURJAN | WIP | YES
3 | KANDHLA | MIMLA TALAB | FINISH | YES
4 | KANDHLA | RAMPUR KHEDI | FINISH | YES
5 | KANDHLA | HURMAJPUR URF SHAHPUR | FINISH | YES
6 | KANDHLA | ALDI | FINISH | YES
7 | KANDHLA | GUJJARPUR-FATEHPUR | FINISH/ EXCEPTING FATEHPUR | YES
8 | KANDHLA | BHARSI | FINISH | YES
9 | KANDHLA | ASADPUR & BARNAULI | FINISH | YES
10 | KANDHLA | AMBETHA ASADPUR | WIP | YES
11 | KANDHLA | ISLAMPUR GHASAULI | FINISH | YES
12 | KANDHLA | PANJOKHERA | WIP | PENDING/15.011.24
13 | KANDHLA | BRAHAM KHERA | WIP | PENDING/10.01.24
14 | KANDHLA | ISSOPUR TEEL | WIP | PENDING/05.01.24
15 | KANDHLA | KHERA KURTAN | WIP | PENDING/01.01.24
16 | KANDHLA | KHANDARAWALI | PENDING | PENDING
17 | KANDHLA | I. KANDHLA DEHAT | PENDING | PENDING
18 | KANDHLA | II. ATTA | FINISH | PENDING/after pump lowering
19 | KANDHLA | III. HAJIPUR DUGADDA(SALEMPUR) | WIP | PENDING/after pump lowering
20 | KANDHLA | I. JASALA | BOREWELL PENDING | PENDING
21 | KANDHLA | II. NANUPURI | FINISH | PENDING
22 | KANDHLA | DUDHAR | FINISH | PENDING/after pump lowering
23 | KANDHLA | CHADHAW | WIP | PENDING/after pump lowering
24 | KANDHLA | MALAKPUR | WIP | PENDING/02.01.24

## Sheet4
S No | BLOCK | VILLAGE | PIPELAYING STATUS | WATER SUPPLY STATUS
1 | THANABHAWAN | MAKHERI KADERGARH | FINISH/MARUKHEDI PENDING | YES
2 | THANABHAWAN | MAHAVATPUR | FINISH | YES
3 | THANABHAWAN | YARPUR | FINISH | YES
4 | THANABHAWAN | KELASHIKARPUR | FINISH | YES/NEED RE INSTALLED SOLAR MODULE
5 | THANABHAWAN | AURANGABAD URF GANDHEWARA | FINISH | YES
6 | THANABHAWAN | BAHANDAURA | FINISH | YES
7 | THANABHAWAN | TITARSI PAWERKHERA | FINISH | YES
8 | THANABHAWAN | KHANPUR | FINISH | YES/28.12.23
9 | THANABHAWAN | KAJIPURA,THIRWA,JASANA URF MASTGARH | WIP | YES
10 | THANABHAWAN | AHATAH GOSHGARH | WIP | PENDING/ 10.01.24
11 | THANABHAWAN | MANAT MANTI | FINISH | TESTING DONE/ISSUE IN SOLAR INSTALLATION DUE TO SHORT SPACE
12 | THANABHAWAN | KHERAGADAI | WIP | PENDING/7.01.24
13 | THANABHAWAN | UMERPUR | FINISH | PENDING/BOREWELL ISSUE
14 | THANABHAWAN | JAFARPUR | FINISH | TESTING DONE/ISSUE IN SOLAR INSTALLATION DUE TO SHORT SPACE
15 | THANABHAWAN | DAKHORI JAMALPUR | WIP | PENDING/1.01.24
16 | THANABHAWAN | BHANERAUDDA | WIP | PENDING/10.01.24
17 | THANABHAWAN | MANAKPUR YUNISPUR | FINSH /ROAD CROSSING PENDING | PENDING
18 | THANABHAWAN | KHIYARI | FINSH/ROAD CROSSING PENDING | PENDING/after pump lowering
19 | THANABHAWAN | NAGAL ISMAILPUR | WIP | PENDING/after pump lowering
20 | THANABHAWAN | DABHERI | WIP | PENDING
21 | THANABHAWAN | NOJAL NJALI | WIP | PENDING/ELECTRICAL CONNECTION
22 | THANABHAWAN | PALTHERI | WIP | PENDING/10.01.24
23 | THANABHAWAN | JALALABAD RURAL | BOREWELL PENDING | PENDING
24 | THANABHAWAN | ABDULLAPUR URF MOURMAJRA | BOREWELL PENDING | PENDING
25 | THANABHAWAN | AMBEHTA YAKUBPUR | BOREWELL PENDING | PENDING
26 | THANABHAWAN | BUNTA | WIP | PENDING
27 | THANABHAWAN | HIND | WIP | PENDING
28 | THANABHAWAN | AHAMADPUR | FINISH/ROAD CROSSING PENDING | PENDING
29 | THANABHAWAN | MADALPUR | WIP | PENDING
30 | THANABHAWAN | USMANPUR | BOREWELL PENDING | PENDING
31 | THANABHAWAN | GURANA | WIP | PENDING
32 | THANABHAWAN | KADARPUR | FINISH | PENDING/after pump lowering
33 | THANABHAWAN | JANIPUR | WIP/ ARHAM | PENDING/10.01.24/after pump lowering
34 | THANABHAWAN | MULLAPUR | FINISH | PENDING/30.12.23

## Sheet5
S No | BLOCK | VILLAGE | PIPELAYING STATUS | WATER SUPPLY STATUS
1 | KAIRANA | TITOLI | FINISH/FHTC REPAIRING PENDING/LEAKAGE REPAIRING PENDING | YES
2 | KAIRANA | GANDRAV | FINISH/PROBLEM IN DRAINS | YES
3 | KAIRANA | BIBIPUR HATIYA | FINISH | YES
4 | KAIRANA | BASERA NON ALLVVIAL | FINISH | YES
5 | KAIRANA | BARNAVI PATHR & MUKUNDPUR | FINISH/LEAKAGE REPAIRING/FHTC REPAIRING | YES
6 | KAIRANA | JANGHERI | FINSH/FHTC REPAIRING | YES
7 | KAIRANA | BADHUPURA | FINSH | YES
8 | KAIRANA | MANDAWAR | FINSH | YES
9 | KAIRANA | MOHAMMADPUR RAI | FINISH/FHTC REPAIRING | YES
10 | KAIRANA | NAGLA RAI | FINISH | YES
11 | KAIRANA | KASERWA KALAN | FINISH | YES
12 | KAIRANA | GOGWAN | WIP | PENDING
13 | KAIRANA | KASERWAKHURD | WIP/STAY | PENDING
14 | KAIRANA | MANNA MAZRA | WIP | PENDING
15 | KAIRANA | RAMRA | FINISH/EXCEPTING PWD ROAD | PENDING
16 | KAIRANA | JHARKHERI | FINISH/FHTC REPAIRING PENDING | PENDING
17 | KAIRANA | ALIPUR | STOP | PENDING
18 | KAIRANA | ERTI | FINISH | WIP
19 | KAIRANA | PAOTIKALAN | WIP | PENDING
20 | KAIRANA | MAWI NON AHATMAL | WIP | PENDING
21 | KAIRANA | UNCHA GAON | WIP | PENDING
22 | KAIRANA | BINDA(BENRA) | FINSIH | PENDING
23 | KAIRANA | JAHANPUR | WIP | PENDING
24 | KAIRANA | DABHERI KHURD | FINISH | PENDING
25 | KAIRANA | PANJETH | WIP | PENDING
26 | KAIRANA | SAHPAT NON AHMATMAL | WIP | PENDING
27 | KAIRANA | MUNDET KALAN | WIP/STAY | PENDING
28 | KAIRANA | MALAKPUR | WIP | PENDING
29 | KAIRANA | BARAALA KUKKARHERI | WIP | PENDING
30 | KAIRANA | MAMOUR NON AHT | WIP | PENDING
31 | KAIRANA | BAMNOLI SEKHUPURA | FINISH | PENDING
32 | KAIRANA | MAWI TIMALI AHT | WIP | PENDING

## Sheet3
S No | BLOCK | VILLAGE | PIPELAYING STATUS | WATER SUPPLY STATUS
1 | UNN | DATHERA | FINISH | YES
2 | UNN | TODA | FINSIH | YES
3 | UNN | KHORSAMA | FINISH | YES
4 | UNN | BALLAMZRA | FINSH | YES
5 | UNN | KHERI KHUSHNAM | FINISH | YES
6 | UNN | GUJJARPUR-RAMNAGAR | FINISH | YES
7 | UNN | KHERKI | FINISH | YES
8 | UNN | GAGOUR | FINISH IN 3 NOS MAJRA/ PENDING IN MAIN VILLAGE | YES
9 | UNN | GANGARAMPURA KHEDKI | FINISH | YES
10 | UNN | CHATTELA URF JAINPUR | FINISH | YES
11 | UNN | BIDAULI | FINISH | YES
12 | UNN | BEDKHERI | FINISH | YES
13 | UNN | LAWA DAUPUR | FINISH | YES
14 | UNN | MUNDET KHADER | FINISH | YES
15 | UNN | HARSANA | FINISH | YES
16 | UNN | PURMAFI | FINISH | YES
17 | UNN | BHAHMERI SHAHPUR | FINISH | YES
18 | UNN | HASANPUR | FINISH | YES
19 | UNN | KAMALPUR | FINISH | YES
20 | UNN | SANPLA | FINISH | YES
21 | UNN | BHOGI MAZRA | FINISH | YES
22 | UNN | SAKAUTI | FINISH | YES
23 | UNN | KALAMAZRA-AZIZPUR | FINISH | YES
24 | UNN | DARGAHPUR | WIP | YES IN 1 MAJRA
25 | UNN | ULLANI BINAMAJRA | FINISH | YES
26 | UNN | PELKHA | FINSH | YES
27 | UNN | DULLAKHEDI | FINISH | YES
28 | UNN | AMBETHA RIDAN | FINISH | YES
29 | UNN | SIKANDARPUR | FINISH | YES
30 | UNN | DABHEDHI BAJURGA URF TISANG | FINISH | YES
31 | UNN | CHONDA HERI,NAUNAGALI | WIP/ DEMAND SEPRATE OHT | PENDING/ONLY 1 MAZARA
32 | UNN | KHERA BAHU | FINISH | YES
33 | UNN | PANTHU PURA | WIP | YES IN 1 MAJRA
34 | UNN | HATH CHHOYA | WIP/CHOUDHARY | YES
35 | UNN | KERTU | FINISH/HIGHWAY WORK PENDING/RELAYING DUE TO DEPTH ISSUE | PENDING/10.01.24
36 | UNN | TANA | WIP/RANA/HDD DEMAND FROM VILLAGERS | PENDING
37 | UNN | DHINDHALI | WIP | PENDING
38 | UNN | GARHI HASANPUR | FINISH ONLY DI LAYING PENDING | PENDING
39 | UNN | SUBHRI | FINISH | PENDING/LT PANEL CABLE CONNECTING WORK
40 | UNN | RAJHAR | WIP | PENDING/05.01.24
41 | UNN | SINGRA | WIP/1 MAJRA PENDING FROM JB SIDE / JB NOT INTRESTED | PENDING/ 05.01.24
42 | UNN | RANGANA | WIP/CONTRACTOR NOT INTRESTED/ LAYING PENDING | PENDING/08.01.24
43 | UNN | AKARPUR URF FUSGARH | WIP/CONTRACTOR NOT INTRESTED/ LAYING PENDING | PENDING
44 | UNN | NAI NAGLA NAVEEN | FINISH | PENDING/after pump lowering
45 | UNN | PATNI PRATAPUR | FINISH/HIGHWAY WORK PENDING | PENDING/05.01.24
46 | UNN | RAJAK NAGAR | FINISH/PROBLEM IN MAIN LINE LAYING | PENDING/local hindrance
47 | UNN | YOSUFPUR URF CHAUTRA | FINISH EXCEPTING IRRIGATION DEPARTMENT AREA | PENDING/partial portion 05.01.23
48 | UNN | UD PUR | FINISH | PENDING/after pump lowering
49 | UNN | KHANPUR JATAN | FINISH | PENDING/HEADER NOT CONNECTED DUE TO OHT WORK
50 | UNN | MIYAN KASBA | WIP/SHRI MITHI MP | PENDING/NH PERMISSION
51 | UNN | DOKPURA | FINISH | PENDING/CONTRACTOR LEFT WORK
52 | UNN | ODRI | WIP/AABID | PENDING/10.01.24
53 | UNN | BHARI MUSTAFABAD | WIP/PERMISSION FROM IRRIGATION DEPARTMENT | PENDING/1 MAZARA after pump lowering
54 | UNN | MACHRAULI | FINISH | PENDING/TESTING PENDING FROM VENDOR SIDE
55 | UNN | PEER KHERA | FINISH | PENDING/SOLAR WIP
56 | UNN | BHATU | WIP/AMAN ENTERPRISES | PENDING
57 | UNN | MANSURA | WIP/SARAFAT | PENDING/10.01.24
58 | UNN | BAJHERI | WIP/MUNDET PRADHAN | PENDING/SOLAR INSTLLATION PENDING
59 | UNN | BASI CHUNDYARI | WIP/SWAROOPA | PENDING
60 | UNN | RATAUNDH BIBIPUR | WIP | PENDING
61 | UNN | KABEERPUR AHATMAL | FINISH | PENDING/PUMP NOT RECEIVED
62 | UNN | JAMALPUR | WIP/SYAM MP | PENDING
63 | UNN | JIJAULA | WIP | PENDING
64 | UNN | BIBIPUR JALALABAD | FINISH | PENDING/BOREWELL ISSUE
65 | UNN | CHAUSANA | WIP | PENDING
66 | UNN | NAI NAGLA SAKAUTI | FINISH | PENDING/ELECTRICAL CONNECTION

## Sheet2
Sno | Block | Village | Road Restoration
1 | UNN | KHORSAMA | COMPLETED
2 | UNN | GUJJARPUR-RAMNAGAR | COMPLETED
3 | UNN | KHERKI | COMPLETED
4 | UNN | GANGARAMPURA KHEDKI | COMPLETED | 180.6 | 0.91 | 164.346
5 | UNN | CHATTELA URF JAINPUR | COMPLETED
6 | UNN | BIDAULI | COMPLETED
7 | UNN | BEDKHERI | COMPLETED
8 | UNN | LAWA DAUPUR | COMPLETED
9 | THANABHAWAN | MAKHERI KADERGARH | COMPLETED
10 | THANABHAWAN | MANAT MANTI | COMPLETED
11 | THANABHAWAN | MAHAVATPUR | COMPLETED
12 | THANABHAWAN | YARPUR | COMPLETED
13 | THANABHAWAN | KELASHIKARPUR | COMPLETED
14 | SHAMLI | JALALPUR | COMPLETED
15 | SHAMLI | JANDHERI | COMPLETED
16 | KAIRANA | TITOLI | COMPLETED
17 | KAIRANA | GANDRAV | COMPLETED
18 | KAIRANA | BIBIPUR HATIYA | COMPLETED
19 | KANDHLA | RAMPUR KHEDI | COMPLETED
20 | UNN | KAMALPUR | COMPLETED
21 | UNN | SANPLA | COMPLETED
22 | UNN | BHOGI MAZRA | COMPLETED
23 | UNN | SAKAUTI | COMPLETED
24 | UNN | DULLAKHEDI | COMPLETED
25 | THANABHAWAN | TITARSI PAWERKHERA | COMPLETED
26 | KANDHLA | GUJJARPUR-FATEHPUR | COMPLETED
27 | KANDHLA | BHARSI | COMPLETED
28 | UNN | SIKANDARPUR | COMPLETED
29 | UNN | RAJAK NAGAR | COMPLETED
30 | KAIRANA | JANGHERI | COMPLETED
31 | KAIRANA | BADHUPURA | COMPLETED
32 | KAIRANA | NAGLA RAI | COMPLETED
33 | KAIRANA | BINDA(BENRA) | COMPLETED
34 | UNN | KHERA BAHU | COMPLETED
35 | THANABHAWAN | AHAMADPUR | COMPLETED
36 | KAIRANA | KASERWA KALAN | COMPLETED
37 | KAIRANA | BAMNOLI SEKHUPURA | COMPLETED
38 | KANDHLA | II. NANUPURI | COMPLETED