## Sheet1
Subcontractor: | Pankaj Kumar Contractor
State: | Uttar Pradesh
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | painting and finishing 5% | GST_SD_Amount | Hold Amount (Excess work against DPR ) | Final_Amount | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | SD (5%) | Advance paid | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% | 5% | 18% |  |  |  |  | 1% | 5%
53369 | Bhandhura Village Pump house work | 2022-11-19 | 2 | 111000 | 0 | 111000 | 19980 | 130980 | 1110 | 5550 |  | 19980 | 0 | 104340 | RIUP22/1448 | 111000 | 1110 | 5550 | 0 | 104340 | 08-12-2022 NEFT/AXISP00344752117/RIUP22/1448/PANKAJ KUMAR CO 104340.00 | 1
53369 | Bhandhura Village Pump house work | 2023-01-10 | 8 | 148000 | 0 | 148000 | 26640 | 174640 | 1480 | 7400 |  | 26640 |  | 139120 | RIUP22/1851 | 139120 | 0 | 0 | 0 | 139120 | 13-01-2023 NEFT/AXISP00354657707/RIUP22/1851/PANKAJ KUMAR CO 139120.00
53369 | Bhandhura Village Pump house and chamber work | 2023-01-31 | 10 | 64850 | 41495 | 23355 | 4204 | 27559 | 233.55 | 1168 |  | 4204 |  | 21953 | RIUP22/2088 | 21953 | 0 | 0 |  | 21953 | 04-02-2023 NEFT/AXISP00360451531/RIUP22/2088/PANKAJ KUMAR CO ₹ 21,953.00
53369 | GST Release Note | 2023-02-09 | 2 | 19980 |  | 19980 | 0 | 19980 | 0 | 0 |  | 0 |  | 19980 | RIUP22/2221 | 19980 |  |  |  | 19980 | 20-02-2023 NEFT/AXISP00364406842/RIUP22/2221/PANKAJ KUMAR CO 19980.00
53369 | GST Release Note | 2023-03-13 | 8 | 26640 | [9 empty] | 26640 | RIUP22/2600 | 30844 |  |  |  | 30844 | 17-03-2023 NEFT/AXISP00372194508/RIUP22/2600/PANKAJ KUMAR CO 30844.00
53369 | GST Release Note | 2023-03-13 | 10 | 4204 | [9 empty] | 4204 | RIUP23/556 | 50862 |  |  |  | 50862 | 09-06-2023 NEFT/AXISP00397387013/RIUP23/556/PANKAJ KUMAR CON 50862.00
53369 | Bhandhura Village Pump house and chamber work | 2023-05-24 | 5 | 57150 |  | 57150 | 10287 | 67437 | 572 | 2858 |  | 10287 | 2857.5 | 50863 | RIUP23/1115 | 10287 |  |  |  | 10287 | 18-07-2023 NEFT/AXISP00407695585/RIUP23/1115/PANKAJ KUMAR CO 10287.00
53369 | GST Release Note | 2023-06-21 | 5 | 10287 | [9 empty] | 10287
53368 | Kanjerheri Village Drilling work | 2022-11-19 | 3 | 111000 | 0 | 111000 | 19980 | 130980 | 1110 | 5550 |  | 19980 | 0 | 104340 | RIUP22/1447 | 111000 | 1110 | 5550 | 0 | 104340 | 08-12-2022 NEFT/AXISP00344752116/RIUP22/1447/PANKAJ KUMAR CO 104340.00 | -19980
53368 | Kanjerheri Village Drilling work | 2023-01-09 | 7 | 111000 | 0 | 111000 | 19980 | 130980 | 1110 | 5550 |  | 19980 |  | 104340 | RIUP22/1850 | 104340 | 0 | 0 | 0 | 104340 | 13-01-2023 NEFT/AXISP00354657706/RIUP22/1850/PANKAJ KUMAR CO 104340.00
53368 | Kanjerheri Village Drilling work | 2023-01-31 | 9 | 82800 | 41495 | 41305 | 7435 | 48740 | 413 | 2065 |  | 7435 |  | 38827 | RIUP22/2222 | 19980 | 0 | 0 |  | 19980 | 20-02-2023 NEFT/AXISP00364387939/RIUP22/2222/PANKAJ KUMAR CO 19980.00
53368 | GST release note |  | 3 | 19980 |  | 19980 | 0 | 19980 | 0 | 0 |  | 0 |  | 19980 | RIUP22/2601 | 27415 |  |  |  | 27415 | 17-03-2023 NEFT/AXISP00372194509/RIUP22/2601/PANKAJ KUMAR CO 27415.00
53368 | GST release note |  | 7 | 19980 |  | 19980 | 0 | 19980 | 0 | 0 |  | 0 |  | 19980 | RIUP22/2083 | 38827 | 0 | 0 |  | 38827 | 04-02-2023 NEFT/AXISP00360451528/RIUP22/2083/PANKAJ KUMAR CO ₹ 38,827.00
53368 | GST release note |  | 9 | 7435 |  | 7435 | 0 | 7435 | 0 | 0 |  | 0 |  | 7435 | RIUP22/2222 | 19980 |  |  |  | 19980 | 20-02-2023 NEFT/AXISP00364387939/RIUP22/2222/PANKAJ KUMAR CO 19980.00
53368 | Kanjerheri Village Drilling work | 2023-05-24 | 4 | 76200 | 0 | 76200 | 13716 | 89916 | 762 | 3810 | 3810 | 13716 |  | 67818 | RIUP22/2601 | 27415 |  |  |  | 27415 | 17-03-2023 NEFT/AXISP00372194509/RIUP22/2601/PANKAJ KUMAR CO 27415.00
53368 | GST release note | 2023-06-21 | 4 | 13716 | [9 empty] | 13716 | RIUP23/552 | 67818 |  |  |  | 67818 | 09-06-2023 NEFT/AXISP00397387010/RIUP23/552/PANKAJ KUMAR CON 67818.00
53368 | GST release note |  |  | 27415 | [9 empty] | 27415 | [5 empty] | 13716 | 18-07-2023 NEFT/AXISP00407695586/RIUP23/1114/PANKAJ KUMAR CO 13716.00
53368
53175 | Dhanena village Pump House work | 2022-11-19 | 1 | 111000 | 0 | 111000 | 19980 | 130980 | 1110 | 5550 |  | 19980 | 0 | 104340 | RIUP22/1449 | 111000 | 1110 | 5550 | 0 | 104340 | 08-12-2022 NEFT/AXISP00344752118/RIUP22/1449/PANKAJ KUMAR CO 104340.00 | 0
53175 | Dhanena village Pump House work | 2023-01-09 | 6 | 111000 | 0 | 111000 | 19980 | 130980 | 1110 | 5550 |  | 19980 |  | 104340 | RIUP22/1852 | 104340 | 0 | 0 | 0 | 104340 | 18-01-2023 NEFT/AXISP00355697019/RIUP22/1852/PANKAJ KUMAR CO ₹ 1,04,340.00
53175 | GST release note |  | 1 | 19980 |  | 19980 | 0 | 19980 | 0 |  |  |  |  | 19980 | RIUP22/2220 | 19980 | 0 | 0 |  | 19980 | 20-02-2023 NEFT/AXISP00364387938/RIUP22/2220/PANKAJ KUMAR CO 19980.00
53175 | GST release note |  | 6 | 19980 |  | 19980 | 0 | 19980 | 0 | 0 |  | 0 |  | 19980 | RIUP22/2220 | 19980 | 0 | 0 |  | 19980 | 17-03-2023 NEFT/AXISP00372194507/RIUP22/2220/PANKAJ KUMAR CO 19980.00
53175 | Dhanena village Pump House work | 2023-05-24 | 3 | 159000 | 41495 | 117505 | 21151 | 138656 | 1175 | 5875 | 5875.25 | 21151 |  | 104580 | RIUP23/539 | 104580 |  |  |  | 104580 | 07-06-2023 NEFT/AXISP00396261242/RIUP23/539/PANKAJ KUMAR CON 104580.00
53175 | GST release note | 2023-06-21 | 3 | 21151 | [9 empty] | 21151 | RIUP23/1113 | 21151 |  |  |  | 21151 | 18-07-2023 NEFT/AXISP00407695587/RIUP23/1113/PANKAJ KUMAR CO 21151.00
53175
53175
53175
53175
53175
[9 empty] | 10185.55 | 50926 | 9685.25 |  | 2857.5
[9 empty] | Total Payable Amount Rs. - |  |  |  |  | 1155609 |  |  |  | Total Paid Amount Rs. - |  | 1175588
[18 empty] | Balance Payable Amount Rs. - |  | -19979
Pankaj Kumar Contractor Shamli
Updated On 11-12-2024 ( By Nakshatra )
[11 empty] | Total Hold |  | 70796.8
[11 empty] | DPR Excess |  | 2857.5
[11 empty] | Advance / Surplus |  | -19979
[11 empty] | Debit |  | Nil
[11 empty] | GST Remaining |  | Nil