## Sheet1
MZN
| Invoice Reconcilation |  | Rishal Constructions
2024-08-27
| Invoice Details | Invoice Date | Invoice No | Basic Amt | Debit | After Debit Amt | 18% GST | Amount | TDS (2%) | SD (5%) | TD (10%) | OC (10%) | GST SD (18%) | Additional Debit | Final Amount |  | PAYMENT NOTE No. | Amount | TDS Amount @ 1% on BASIC AMOUNT | SD (5%) | Advance paid | Total Amount Paid | UTR
[9 empty] | 1% | 5% | 10% | 10% | [6 empty] | 1% | 5%
59156
59156 | BALANCE WORK ROAD RESTORATION AT MEDPUR BLOCK SADAR | 2023-12-05 | 5 | 295400 | 112500 | 182900 | 32922 | 215822 | 1829 | 9145 | 18290 | 18290 | 32922 | 38998 | 96348 |  | RIUP23/1921 | 300000 | 3000 | 0 | 0 | 297000 | 08-09-2023 NEFT/AXISP00423197096/RIUP23/1921/RISHAL CONSTRUCTIO/HDFC0002516 297000.00
| GST |  |  | 32922 | [10 empty] | 32922 |  | RIUP23/3028 | 200000 | 2000 | 0 | 0 | 198000 | 01-11-2023 NEFT/AXISP00439457385/RIUP23/3028/RISHAL CONSTRUCTIO/HDFC0002516 198000.00
[16 empty] | 59157 | [7 empty] | -365730
59157 | Dehchand Village Road Restoration work | 2023-12-05 | 6 | 262045 | 0 | 262045 | 47168.1 | 309213.1 | 2620.45 | 13102.25 | 26204.5 | 26204.5 | 47168.1 | 0 | 193913.3 |  | RIUP23/1922 | 300000 | 3000 | 0 | 0 | 297000 | 08-09-2023 NEFT/AXISP00423197097/RIUP23/1922/RISHAL CONSTRUCTIO/HDFC0002516 297000.00
| GST |  |  | 47168.1 | [10 empty] | 47168.1 |  | RIUP23/2271 | 500000 | 5000 | 0 | 0 | 495000 | 26-09-2023 NEFT/AXISP00427456612/RIUP23/2271/RISHAL CONSTRUCTIO/HDFC0002516 ₹ 4,95,000.00
[16 empty] | 59158 | [7 empty] | -550918.6
59158 | Aklor Village Road Restoration work | 2023-12-05 | 8 | 353603 | 0 | 353603 | 63648.54 | 417251.54 | 3536.03 | 17680.15 | 35360.3 | 35360.3 | 63648.54 | 0 | 261666.22 |  | RIUP23/1923 | 300000 | 3000 | 0 | 0 | 198000 | 08-09-2023 NEFT/AXISP00423197098/RIUP23/1923/RISHAL CONSTRUCTIO/HDFC0002516 198000.00
| GST |  |  | 63648.54 | [10 empty] | 63648.54 |  |  |  | 0 | 0 | 0 | 495000 | 26-09-2023 NEFT/AXISP00427456610/RIUP23/2272/RISHAL CONSTRUCTIO/HDFC0002516 ₹ 4,95,000.00
[16 empty] | 59159 |  |  | 0 | 0 | 0 | 0 |  | -367685.24
59159 | Kallarpur Village Road Restoration work | 2023-10-30 | 1 | 691783 | 57750 | 634033 | 114125.94 | 748158.94 | 6340.33 | 31701.65 | 63403.3 | 63403.3 | 114125.94 | 29902 | 439282.42 |  | RIUP23/1923 | 500000 | 5000 | 0 | 0 | 495000 | 26-09-2023 NEFT/AXISP00427456608/RIUP23/2273/RISHAL CONSTRUCTIO/HDFC0002516 ₹ 4,95,000.00
| GST |  |  | 114125.94 | [10 empty] | 114125.94 |  | RIUP23/1924 | 100000 | 1000 | 0 | 0 | 99000 | 01-11-2023 NEFT/AXISP00439457386/RIUP23/3029/RISHAL CONSTRUCTIO/HDFC0002516 99000.00
[19 empty] | 0 | 0 | 0 | 0
[16 empty] | 60026 |  |  | 0 | 0 | 0 | 0 |  | -40591.64
60026 | Kacholi Village Road Restoration work | 2023-12-05 | 7 | 254678 | 0 | 254678 | 45842.04 | 300520.04 | 2546.78 | 12733.9 | 25467.8 | 25467.8 | 45842.04 | 0 | 188461.72 |  | RIUP23/3030 | 500000 | 5000 | 0 | 0 | 495000 | 01-11-2023 NEFT/AXISP00439477043/RIUP23/3030/RISHAL CONSTRUCTIO/HDFC0002516 ₹ 4,95,000.00
| GST |  |  | 45842.04 | [10 empty] | 45842.04
[16 empty] | 60522 | [7 empty] | -260696.24
60522 | Barnabi Pathar - RR | 2023-12-01 | 3 | 394209.75 | 19073.75 | 375136 | 67524.48 | 442660.48 | 3751.36 | 18756.8 | 37513.6 | 37513.6 | 67524.48 | 0 | 277600.64
Shamli | GST |  |  | 67524.48 | [10 empty] | 67524.48
[16 empty] | 60523 | [7 empty] | 345125.12
60523 | Titayali - RR | 2023-12-01 | 2 | 90923.25 | 57223.75 | 33699.5 | 6065.91 | 39765.41 | 336.995 | 1684.975 | 3369.95 | 3369.95 | 6065.91 | 0 | 24937.63
Shamli | GST |  |  | 6065.91 | [10 empty] | 6065.91
[16 empty] | 60719 |  |  | 0 | 0 | 0 | 0 |  | 31003.54
60719 | BALANCE REINSTATEMENT WORK AT BHAISANI BLOCK PURKAZI | 2023-12-12 | 4 | 320521 | 37500 | 283021 | 50943.78 | 333964.78 | 2830.21 | 14151.05 | 28302.1 | 0 | 50943.78 | 0 | 237737.64
| GST |  |  | 50943.78 | [10 empty] | 50943.78
288681.42
0
[10 empty] | 118955.775 | 237911.55 | 209609.45 | 428240.79 | 68900 | 2148188.36 |  |  |  | Total Paid Amount Rs. - |  |  | 3069000
[19 empty] | Balance Payable Amount Rs. - |  |  | -920811.64
10 Lakh amount bill has no clarity
Updated On 05-07-2024
[10 empty] | Total Hold |  | 566476.775
[10 empty] | Advance / Surplus |  | -920811.64
[10 empty] | Debit |  | Nil

## Sheet1 (2)
Shamli
| Invoice Reconcilation |  | Rishal Constructions
2024-08-27
| Invoice Details | Invoice Date | Invoice No | Basic Amt | Debit | After Debit Amt | 18% GST | Amount | TDS (2%) | SD (5%) | TD (10%) | OC (10%) | GST SD (18%) | Additional Debit | Final Amount |  | PAYMENT NOTE No. | Amount | TDS Amount @ 1% on BASIC AMOUNT | SD (5%) | Advance paid | Total Amount Paid | UTR
[9 empty] | 1% | 5% | 10% | 10% | [6 empty] | 1% | 5%
[16 empty] | 60523 |  |  | 0 | 0 | 0 | 0
60523 | Pipe Line Road Road Restoration Work-At-Village-TITAYLI | 2023-12-01 | 2 | 90923 | 57225 | 33698 | 6065.64 | 39763.64 | 336.98 | 1684.9 | 3369.8 | 0 | 6065.64 | 0 | 28306.32
[16 empty] | 60522 |  |  | 0 | 0 | 0 | 0
60522 | Pipe Line Road Road Restoration Work-At-Village-Barnabi Pathar | 2023-12-01 | 3 | 394210 | 19075 | 375135 | 67524.3 | 442659.3 | 3751.35 | 18756.75 | 37513.5 | 37513.5 | 67524.3 | 0 | 277599.9
0
[10 empty] | 20441.65 | 40883.3 | 37513.5 | 73589.94 | Total Payable Amount Rs. - | 305906.22 |  |  |  | Total Paid Amount Rs. - |  |  | 0
[19 empty] | Balance Payable Amount Rs. - |  |  | 305906.22

## Sheet1 (3)
Subcontractor: | Rishal Constructions
State: | Uttar Pradesh
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | TD (10%) | On_Commission | GST_SD_Amount | Additional Debit | Final_Amount | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | GST_SD_Amount | Advance paid | Total_Amount | UTR
[9 empty] | 1% | 5% | 10% | 10% | [5 empty] | 1% | 5%
[18 empty] | 0 | 0 | 0 | 0
60523 | TITAYLI Village Pipe Line Road Road Restoration Work | 2023-12-01 | 2 | 90923 | 57225 | 33698 | 6065.64 | 39763.64 | 336.98 | 1684.9 | 0 | 3369.8 | 6065.64 | 0 | 28306.32
[18 empty] | 0 | 0 | 0 | 0
60522 | Barnabi Village Road Restoration Pathar Pipe Line Road Work | 2023-12-01 | 3 | 394210 | 19075 | 375135 | 67524.3 | 442659.3 | 3751.35 | 18756.75 | 37513.5 | 37513.5 | 67524.3 | 0 | 277599.9
59156 | MEDPUR BLOCK SADAR Village BALANCE WORK ROAD RESTORATION AT BALANCE WORK | 2023-12-05 | 5 | 295400 | 112500 | 182900 | 32922 | 215822 | 1829 | 9145 | 18290 | 18290 | 32922 | 38998 | 96348 | RIUP23/1921 | 300000 | 3000 | 0 | 0 | 297000 | 08-09-2023 NEFT/AXISP00423197096/RIUP23/1921/RISHAL CONSTRUCTIO/HDFC0002516 297000.00
59156 | GST Release Note |  | 5 | 32922 | [10 empty] | 32922 | RIUP23/3028 | 200000 | 2000 | 0 | 0 | 198000 | 01-11-2023 NEFT/AXISP00439457385/RIUP23/3028/RISHAL CONSTRUCTIO/HDFC0002516 198000.00
59157 | Dehchand Village Road Restoration work | 2023-12-05 | 6 | 262045 | 0 | 262045 | 47168.1 | 309213.1 | 2620.45 | 13102.25 | 26204.5 | 26204.5 | 47168.1 | 0 | 193913.3 | RIUP23/1922 | 300000 | 3000 | 0 | 0 | 297000 | 08-09-2023 NEFT/AXISP00423197097/RIUP23/1922/RISHAL CONSTRUCTIO/HDFC0002516 297000.00
59157 | GST Release Note |  | 6 | 47168.1 | [10 empty] | 47168.1 | RIUP23/2271 | 500000 | 5000 | 0 | 0 | 495000 | 26-09-2023 NEFT/AXISP00427456612/RIUP23/2271/RISHAL CONSTRUCTIO/HDFC0002516 ₹ 4,95,000.00
59158 | Aklor Village Road Restoration work | 2023-12-05 | 8 | 353603 | 0 | 353603 | 63648.54 | 417251.54 | 3536.03 | 17680.15 | 35360.3 | 35360.3 | 63648.54 | 0 | 261666.22 | RIUP23/1923 | 300000 | 3000 | 0 | 0 | 198000 | 08-09-2023 NEFT/AXISP00423197098/RIUP23/1923/RISHAL CONSTRUCTIO/HDFC0002516 198000.00
59158 | GST Release Note |  | 8 | 63648.54 | [10 empty] | 63648.54 |  |  | 0 | 0 | 0 | 495000 | 26-09-2023 NEFT/AXISP00427456610/RIUP23/2272/RISHAL CONSTRUCTIO/HDFC0002516 ₹ 4,95,000.00
[18 empty] | 0 | 0 | 0 | 0
59159 | Kallarpur Village Road Restoration work | 2023-10-30 | 1 | 691783 | 57750 | 634033 | 114125.94 | 748158.94 | 6340.33 | 31701.65 | 63403.3 | 63403.3 | 114125.94 | 29902 | 439282.42 | RIUP23/1923 | 500000 | 5000 | 0 | 0 | 495000 | 26-09-2023 NEFT/AXISP00427456608/RIUP23/2273/RISHAL CONSTRUCTIO/HDFC0002516 ₹ 4,95,000.00
59159 | GST Release Note |  | 1 | 114125.94 | [10 empty] | 114125.94 | RIUP23/1924 | 100000 | 1000 | 0 | 0 | 99000 | 01-11-2023 NEFT/AXISP00439457386/RIUP23/3029/RISHAL CONSTRUCTIO/HDFC0002516 99000.00
[18 empty] | 0 | 0 | 0 | 0
[18 empty] | 0 | 0 | 0 | 0
60026 | Kacholi Village Road Restoration work | 2023-12-05 | 7 | 254678 | 0 | 254678 | 45842.04 | 300520.04 | 2546.78 | 12733.9 | 25467.8 | 25467.8 | 45842.04 | 0 | 188461.72 | RIUP23/3030 | 500000 | 5000 | 0 | 0 | 495000 | 01-11-2023 NEFT/AXISP00439477043/RIUP23/3030/RISHAL CONSTRUCTIO/HDFC0002516 ₹ 4,95,000.00
60026 | GST Release Note |  | 7 | 45842.04 | [10 empty] | 45842.04
[18 empty] | 0 | 0 | 0 | 0
60719 | AT BHAISANI BLOCK PURKAZI Village BALANCE REINSTATEMENT WORK | 2023-12-12 | 4 | 320521 | 37500 | 283021 | 50943.78 | 333964.78 | 2830.21 | 14151.05 | 28302.1 | 0 | 50943.78 | 0 | 237737.64
60719 | GST Release Note |  | 4 | 50943.78 | [10 empty] | 50943.78