## Sheet1
Subcontractor: | M/S Pramod Contractor
State: | Uttar Pradesh | [14 empty] | 2024-04-29
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | SD (10%) | GST_SD_Amount | Hold Amount For Material | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | SD (5%) | Advance paid | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% | 5% | 10% | 18% | [5 empty] | 1% | 5%
57266
57266 | kalanpur Village Pipe laying work | 2023-07-18 | 3 | 315907.4 | 125874 | 190033 | 34206 | 224239 | 1900 | 9502 | 9502 | 19003 | 34206 | 5282 | 144844 |  | RIUP22/2576 | 100000 | 1000 | 0 | 0 | 99000 | 14-03-2023 NEFT/AXISP00371304713/RIUP22/2576/PRAMOD CONTRACT 99000.00
57266 | kalanpur Village Pipe laying work | 2023-08-12 | 4 | 627770 | 19000 | 608770 | 109578.6 | 718348.6 | 6088 | 30439 | 30439 | 60877 | 109578.6 | 232 | 480695 |  | RIUP23/1261 | 45844 |  |  |  | 45844 | 28-07-2023 NEFT/AXISP00410053396/RIUP23/1261/PRAMOD CONTRACT 45844.00
57266 | GST Release Note | 2023-07-18 | 3 | 34206 |  | 34206 | 0 | 34206 | 0 | [5 empty] | 34206 |  | RIUP23/1837 | 100000 | 1000 |  |  | 99000 | 04-09-2023 NEFT/AXISP00421476874/RIUP23/1837/PRAMOD CONTRACTER 99000.00
57266 | [16 empty] | RIUP23/1860 | 381927 | 0 |  |  | 381927 | 07-09-2023 NEFT/AXISP00422860739/RIUP23/1860/PRAMOD CONTRACTER/PUNB0138010 381927.00
57266 | [21 empty] | 34206 | 17-10-2023 NEFT/AXISP00435129356/RIUP23/2700/PRAMOD CONTRACTER/PUNB0138010 34206.00
[16 empty] | 55775 |  | 0 | 0 | 0 | 0 | 0 | 0
55775 | kalanpur Village Pump House work | 2023-03-20 | 12 | 222000 | 60795 | 161205 | 29017 | 190222 | 1612 | 16121 | 0 | 0 | 29017 |  | 143472 |  | RIUP23/244 | 143472 | 0 | 0 | 0 | 143472 | 16-05-2023 NEFT/AXISP00390411251/RIUP23/244/PRAMOD CONTRACTE 143472.00
55775 | GST Release Note | 2023-05-10 | 12 | 29016 | 0 | [9 empty] | 29016 |  | RIUP23/2699 | 29016 |  |  |  | 29016 | 17-10-2023 NEFT/AXISP00435129355/RIUP23/2699/PRAMOD CONTRACTER/PUNB0138010 29016.00
55775 | kalanpur Village Pump House work | 2023-12-28 | 5 | 111000 | 15000 | 96000 | 17280 | 113280 | 960 | 9600 | 0 | 0 | 17280 |  | 85440
[16 empty] | 55419 |  | 0 | 0 | 0 | 0 | 0 | 0
55419 | KALANPUR VILLAGE PIPE LAYING WORK