## Sheet1
Muzaffarnagar UP
| Invoice Reconcilation |  | Rana Builders |  |  |  |  | Pipe Laying work
Subcontractor: | Rana Builders
State: | Uttar Pradesh
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Only FHTC Amount Hold | Hold the Amount because the Qty. is more then the DPR | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | SD (5%) | Advance paid | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% | 5% | 10% | 18% | [6 empty] | 1% | 5%
52329
52329 | Bhamela Village Pipe laying work. | 2022-11-16 | 13 | 1217974.15 | 17982 | 1199992 | 215999 | 1415991 | 12000 | 60000 | 60000 | 119999 | 215999 |  | 495364 | 452629 |  | RIUP22/703 | 100000 | 1000 |  |  | 99000 | 07-09-2022 NEFT/AXISP00318323974/RIUP22/703/RANA BUILDERS 99000.00
52329 | GST release note |  | 13 | 215999 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 215999 |  | RIUP22/1317 | 353630 | 0 | 0 | 0 | 353630 | 22-11-2022 NEFT/AXISP00339530104/RIUP22/1317/RANA BUILDERS 353630.00
52329 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 |  | RIUP22/1586 | 200000 | 0 | 0 | 0 | 200000 | 21-12-2022 NEFT/AXISP00347873506/RIUP22/1586/RANA BUILDERS 200000.00
52329 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | [6 empty] | 148500 | 18-01-2023 NEFT/AXISP00355710808/RIUP22/1895/RANA BUILDERS ₹ 1,48,500.00
52329 | [22 empty] | 215999 | 21-04-2023 NEFT/AXISP00383377300/SPUP23/0174/RANA BUILDERS 215999.00
52329 | [22 empty] | 99000 | 23-06-2023 NEFT/AXISP003542585245/RIUP23/846/RANA BUILDERS 99000.00
52328
52328 | Nagla Pithora Village Pipe laying work. | 2022-10-08 | 9 | 725956.61 | 0 | 725957 | 130672 | 856629 | 7260 | 36298 | 36298 | 72596 | 130672 |  | 78253.25 | 495252 |  | RIUP22/702 | 100000 | 1000 |  |  | 99000 | 07-09-2022 NEFT/AXISP00318323973/RIUP22/702/RANA BUILDERS 99000.00
52328 | Nagla Pithora Village Pipe laying work. | 2023-02-01 | 17 | 1127865 | 173526 | 954339 | 171781 | 1126120 | 9543 | 47717 | 95434 | 95434 | 171781 |  | 153783 | 552428 |  | RIUP22/959 | 500000 | 5000 | 0 | 0 | 495000 | 12-10-2022 NEFT/AXISP00327681882/RIUP22/959/RANA BUILDERS 495000.00
52328 | Nagla Pithora Village Pipe laying work. | 2023-04-18 | 1 | 117296 | 0 | 117296 | 21113 | 138409 | 1173 | 5865 | 11730 | 11730 | 21113 |  | 0 | 86798 |  | RIUP22/2506 | 300000 | 3000 | 0 |  | 297000 | 08-03-2023 NEFT/AXISP00369766193/RIUP22/2506/RANA BUILDERS 297000.00
52328 | GST release note |  | 9 | 130672 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 130672 | [6 empty] | 243479 | 03-05-2023 NEFT/AXISP00386899986/SPUP23/0354/RANA BUILDERS 243479.00
52328 | GST release note |  | 17 | 171781 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 171781 | [6 empty] | 21113 | 25-05-2023 NEFT/AXISP00392595813/RIUP23/385/RANA BUILDERS 21113.00
52328 | GST release note |  | 1 | 21113 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 21113 | [6 empty] | 171781 | 02-06-2023 NEFT/AXISP00395047095/RIUP23/336/RANA BUILDERS 171781.00
52328 | Nagla Pithora Village Pipe laying work. | 2023-11-30 | 12 | 934580 | 462744 | 471836 | 84930.48 | 556766.48 | 4718 | 23592 | 47183.6 | 47184 | 84930.48 |  | 142811 | 206347.4 | [6 empty] | 130672 | 27-02-2023 NEFT/AXISP00365995614/RIUP22/2310/RANA BUILDERS 130672.00
52328 | GST release note | 2023-11-30 | 12 | 84930.48 | [11 empty] | 84930.48 | [6 empty] | 297000 | 08-03-2023 NEFT/AXISP00369766193/RIUP22/2506/RANA BUILDERS 297000.00
52328 | [22 empty] | 243479 | 03-05-2023 NEFT/AXISP00386899986/SPUP23/0354/RANA BUILDERS 243479.00
52328 | [22 empty] | 21113 | 25-05-2023 NEFT/AXISP00392595813/RIUP23/385/RANA BUILDERS 21113.00
52328 | [22 empty] | 171781 | 02-06-2023 NEFT/AXISP00395047095/RIUP23/336/RANA BUILDERS 171781.00
52328 | [22 empty] | 84930 | 22-12-2023 NEFT/AXISP00455032167/RIUP23/3904/RANA BUILDERS/ICIC0000975 84930.00
52328 | [22 empty] | 206347 | 26-12-2023 NEFT/AXISP00455532161/RIUP23/3678/RANA BUILDERS/ICIC0000975 206347.00
52328 | [22 empty] | 297000 | 13-12-2024 NEFT/AXISP00584365288/RIUP24/2710/RANA BUILDERS/ICIC0000975 297000.00
51771
51771 | Nurnagar Village Pipe laying work | 2022-08-09 | 6 | 229586.7 | 0 | 229587 | 41326 | 270913 | 2296 | 11479 | 11479 | 22959 | 41326 | 5685 | 41326 | 175689 |  | RIUP22/511 | 100000 | 1000 | 0 | 0 | 99000 | 12-08-2022 NEFT/AXISP00311803671/RIUP22/511/RANA BUILDERS 99000.00
51771 | Nurnagar Village Pipe laying work | 2022-09-30 | 8 | 640489.65 | 56643 | 583846.65 | 105092 | 688938.65 | 5838 | 29192 | 29192 | 58385 | 105092 | 66511 | 105092 | 394729 |  | RIUP22/643 | 100000 | 1000 | 0 | 0 | 99000 | 01-09-2022 NEFT/AXISP00316618080/RIUP22/643/RANA BUILDERS 99000.00
51771 | GST Release Note | 2022-09-19 | 6 | 41326 |  | 41326 | 0 | 41326 | 0 | [6 empty] | 41326 |  | RIUP22/883 | 41326 | 0 | 0 | 0 | 41326 | 01-10-2022 NEFT/AXISP00324688885/RIUP22/883/RANA BUILDERS 41326.00
51771 | GST Release Note | 2022-11-18 | 8 | 105092 |  | 105092 | 0 | 105092 | 0 | 0 |  |  |  |  | 0 | 105092 |  | RIUP22/976 | 400000 | 4000 | 0 | 0 | 396000 | 12-10-2022 NEFT/AXISP00327753849/RIUP22/976/RANA BUILDERS 396000.00
51771 | Nurnagar Village Pipe laying work | 2022-12-05 | 14 | 587195 | 108791.1 | 478403.9 | 86113 | 564516.9 | 4784 | 23920 | 23920 | 47840 | 81675 | 167652 | 86113 | 128613 |  | RIUP22/1307 | 105092 | 0 | 0 | 0 | 105092 | 19-11-2022 NEFT/AXISP00339152182/RIUP22/1307/RANA BUILDERS 105092.00
51771 | Nurnagar Village Pipe laying work | 2023-04-18 | 5 | 11704 | 0 | 11704 | 2107 | 13811 | 117 | 585 | 585 | 1170 | 2107 |  | 2107 | 9247 |  | RIUP22/1497 | 105031 | 0 | 0 | 0 | 105031 | 13-12-2022 NEFT/AXISP00346012321/RIUP22/1497/RANA BUILDERS ₹ 1,05,031.00
51771 | GST release note |  | 14 | 81675 | [8 empty] | 0 |  |  | 81675 |  | RIUP22/1894 | 150000 | 0 | 0 | 0 | 150000 | 18-01-2023 NEFT/AXISP00355710807/RIUP22/1894/RANA BUILDERS ₹ 1,48,500.00
51771 | Nurnagar Village Pipe laying work | 2023-08-12 | 10 | 912936.75 | 363510 | 549427 | 98897 | 648324 | 5494 | 27471 | 0 | 0 | 98897 | 0 | 98897 | 417565 |  | SPUP23/0173 | 86113 | 0 |  |  | 86113 | 20-04-2023 20-04-2023 NEFT/AXISP00383281371/SPUP23/0173/RANA BUILDERS 86113.00
51771 | GST release note |  | 5, 10 | 101004 | [11 empty] | 101004 |  |  | 100000 | 0 |  |  | 100000 | 19-07-2023 NEFT/AXISP00407912723/RIUP23/1142/RANA BUILDERS ₹ 99,000.00
51771 | [17 empty] | RIUP23/1643 | 278209 | 0 |  |  | 278209 | 22-08-2023 NEFT/AXISP00417367259/RIUP23/1643/RANA BUILDERS 278209.00
51771 | [22 empty] | 101004 | 30-09-2023 NEFT/AXISP00429227611/RIUP23/2358/RANA BUILDERS/ICIC0000975 101004.00
51558
51558 | Kasoli Village Pipe laying work | 2022-08-09 | 5 | 341426.9 | 53047 | 288380 | 51908.4 | 340288 | 2884 | 14419 | 14419 | 28838 | 51908 |  | 0 | 227820 |  | RIUP22/311 | 50000 | 500 | 0 | 0 | 49500 | 08-07-2022 NEFT O/W-N189221332839341-ICIC0000975-RANA BUILDERS-RIUP22/311--49,500.00
51558 | GST Release Note | 2022-09-19 | 5 | 51908 |  | 51908 | 0 | 51908 | 0 | 0 | 0 | 0 | 0 |  |  | 51908 |  | RIUP22/359 | 100000 | 1000 | 0 | 0 | 99000 | 18-07-2022 NEFT/AXISP00304718866/RIUP22/359/RANA BUILDERS 99000.00
51558 | Kasoli Village Pipe laying work | 2022-11-08 | 12 | 1121550.27 | 137562.3 | 983987.97 | 177117.8346 | 1161106 | 9840 | 49199 | 49199.3985 | 98398.797 | 177118 |  | 114963 | 662388 |  | RIUP22/512 | 100000 | 1000 | 0 | 0 | 99000 | 12-08-2022 NEFT/AXISP00311803672/RIUP22/512/RANA BUILDERS 99000.00
51558 | GST Release Note |  | 12 | 177118 |  | 177118 | 0 | 177118 | 0 | 0 | 0 | 0 | 0 |  |  | 177118 |  | RIUP22/882 | 51908 | 0 | 0 | 0 | 51908 | 01-10-2022 NEFT/AXISP00324688886/RIUP22/882/RANA BUILDERS 51908.00
51558 | Kasoli Village Pipe laying work | 2023-04-18 | 3 | 1680237 | 296704 | 1383533 | 249035.94 | 1632569 | 13835 | 69177 | 69176.65 | 138353.3 | 249036 |  | 155717 | 937274 |  | RIUP22/1298 | 642708 | 0 | 0 | 0 | 642708 | 22-11-2022 NEFT/AXISP00339521127/RIUP22/1298/RANA BUILDERS 642708.00
51558 | GST Release Note | 2023-05-23 | 3 | 249036 | [11 empty] | 249036 |  | SPUP23/0172 | 177118 | 0 | 0 | 0 | 177118 | 20-04-2023 20-04-2023 NEFT/AXISP00383281376/SPUP23/0172/RANA BUILDERS 177118.00
51558 | Kasoli Village Pipe laying work | 2023-11-27 | 11 | 770608 | 187500 | 583108 | 104959.44 | 688067.44 | 5831.08 | 29155.4 | 58310.8 | 58310.8 | 104959.44 |  | 0 | 431499.92 |  | SPUP23/0306 | 838274 | 0 | 0 | 0 | 838274 | 06-05-2023 NEFT/AXISP00388090047/SPUP23/0306/RANA BUILDERS 838274.00
51558 | GST Release Note | 2023-11-27 | 11 | 104959.44 |  | 104959.44 | [9 empty] | 104959.44 |  | RIUP23/384 | 249036 |  |  |  | 249036 | 25-05-2023 NEFT/AXISP00392595812/RIUP23/384/RANA BUILDERS 249036.00
51558 | Kasoli Village Pipe laying work | 2023-12-31 | 13 | 699303 |  | 699303 | 125874.54 | 825177.54 | 6993.03 | 34965.15 | 69930.3 | 69930.3 | 125874.54 |  |  | 517484.22 |  | RIUP23/2012 | 100000 | 1000 |  |  | 99000 | 13-09-2023 NEFT/AXISP00392557856/RIUP23/2012/RANA BUILDERS 99000.00
51558 | GST Release Note | 2023-12-31 | 13 | 125874.54 | [11 empty] | 125874.54 |  | RIUP23/3338 | 100000 | 1000 |  |  | 99000 | 18-11-2023 NEFT/AXISP00445035265/RIUP23/3338/RANA BUILDERS/ICIC0000975 ₹ 99,000.00
51558 | [22 empty] | 233500 | 19-12-2023 NEFT/AXISP00454102602/RIUP23/3670/RANA BUILDERS/ICIC0000975 233500.00
51558 | [22 empty] | 104959 | 22-12-2023 NEFT/AXISP00455032179/RIUP23/3905/RANA BUILDERS/ICIC0000975 104959.00
51558 | [22 empty] | 517485 | 03-02-2024 NEFT/AXISP00468006637/RIUP23/4339/RANA BUILDERS/ICIC0000975 517485.00
51558 | [22 empty] | 125875 | 03-02-2024 NEFT/AXISP00468006636/RIUP23/4484/RANA BUILDERS/ICIC0000975 125875.00
51546 | Gujarheri Village Pipe laying work | 2022-08-10 | 4 | 499771.8 | 47203 | 452569 | 81462.42 | 534031 | 4526 | 22628 | 22628 | 45257 | 81462 |  |  | 357530 | 51546 | RIUP22/312 | 150000 | 1500 | 0 | 0 | 148500 | 08-07-2022 NEFT O/W-N189221332839352-ICIC0000975-RANA BUILDERS-RIUP22/312--148,500.00
51546 | GST Release Note | 2022-09-19 | 4 | 81462 |  | 81462 | 0 | 81462 | 0 | 0 | 0 | 0 | 0 |  |  | 81462 | 26.9.23 | RIUP22/513 | 100000 | 1000 | 0 | 0 | 99000 | 12-08-2022 NEFT/AXISP00311803673/RIUP22/513/RANA BUILDERS 99000.00
51546 | Gujarheri Village Pipe laying work | 2023-04-18 | 2 | 297887 | 47653 | 250234 | 45042.12 | 295276 | 2502 | 12512 | 12512 | 25023 | 45042 |  | 23101 | 174584 |  | RIUP22/600 | 100000 | 1000 | 0 | 0 | 99000 | 24-08-2022 NEFT/AXISP00314011493/RIUP22/600/RANA BUILDERS 99000.00
51546 | GST Release Note | 2023-05-23 | 2 | 45042 |  | 45042 | 0 | 45042 | 0 | 0 |  |  | 0 |  |  | 45042 |  | RIUP22/820 | 81462 | 0 | 0 | 0 | 81462 | 30-09-2022 NEFT/AXISP00323985687/RIUP22/820/RANA BUILDERS 81462.00
51546 | Gujarheri Village Pipe laying work | 2023-07-14 | 9 | 677754 | 351960 | 325794 | 58642.92 | 384436.92 | 3258 | 16290 | 0 | 0 | 58642.92 |  | 29511 | 276735 |  | RIUP22/819 | 11030 | 0 | 0 | 0 | 11030 | 19-11-2022 NEFT/AXISP00339152069/RIUP22/819/RANA BUILDERS 11030.00
51546 | Gujarheri Village Pipe laying work | 2023-07-14 | 8 | 162250 | 0 | 162250 | 29205 | 191455 | 1623 | 8113 | 8113 | 16225 | 29205 |  | 54638 | 73538 |  | SPUP23/0347 | 174585 |  |  |  | 174585 | 02-05-2023 NEFT/AXISP00386545786/SPUP23/0347/RANA BUILDERS 174585.00
51546 | GST Release Note | 2023-09-19 | 8 & 9 | 87848 |  | 87848 | 0 | 87848 | 0 | 0 |  |  | 0 |  |  | 87848 |  | RIUP23/383 | 45042 |  |  |  | 45042 | 25-05-2023 NEFT/AXISP00392595811/RIUP23/383/RANA BUILDERS 45042.00
51546 | [17 empty] | RIUP23/648/ | 100000 | 1000 |  |  | 99000 | 13-06-2023 NEFT/AXISP00398119353/RIUP23/648/RANA BUILDERS 99000.00
51546 | [17 empty] | RIUP23/845 | 200000 | 2000 |  |  | 198000 | 23-06-2023 NEFT/AXISP003542589653/RIUP23/845/RANA BUILDERS 198000.00
51546 | [17 empty] | RIUP23/1214 | 53275 | 0 |  |  | 53275 | 28-07-2023 NEFT/AXISP00410053398/RIUP23/1214/RANA BUILDERS 53275.00
51546 | [22 empty] | 87848 | 27-09-2023 NEFT/AXISP00427962775/RIUP23/2322/RANA BUILDERS/ICIC0000975 87848.00
51536 | Balwakhedi Village Pipe laying work | 2022-08-09 | 3 | 834185.77 | 25175 | 809011 | 145622 | 954633 | 8090 | 40451 | 40451 | 80901 | 145622 |  |  | 639118 | 51536 | RIUP22/327 | 200000 | 2000 | 0 | 0 | 198000 | 11-07-2022 NEFT/AXISP00302944568/RIUP22/327/RANA BUILDERS 198000.00
51536 | GST Release Note | 2022-09-19 | 3 | 145622 |  | 145622 |  | 145622 | 0 | 0 | 0 | 0 | 0 |  |  | 145622 | 26.9.23 | RIUP22/514 | 100000 | 1000 | 0 | 0 | 99000 | 12-08-2022 NEFT/AXISP00311803674/RIUP22/514/RANA BUILDERS 99000.00
51536 | Balwakhedi Village Pipe laying work | 2022-09-22 | 7 | 294800 |  | 294800 | 53064 | 347864 | 2948 | 14740 | 14740 | 29480 | 53064 |  |  | 232892 |  | RIUP22/572 | 200000 | 2000 | 0 | 0 | 198000 | 22-08-2022 NEFT/AXISP00313393104/RIUP/572/RANA BUILDERS 198000.00
51536 | Balwakhedi Village Pipe laying work | 2023-02-01 | 18 | 1068720.78 | 158241 | 910480 | 163886 | 1074366 | 9105 | 45524 | 91048 | 45524 | 163886 |  | 536031 | 183248 |  | RIUP22/825 | 300000 | 3000 | 0 | 0 | 297000 | 26-09-2022 NEFT/AXISP00322503015/RIUP22/825/RANA BUILDERS ₹ 2,97,000.00
51536 | GST Release Note | 2022-09-19 | 7 | 53064 |  | 53064 |  | 53064 | 0 | 0 | 0 | 0 | 0 |  |  | 53064 |  | RIUP22/1288 | 80011 | 0 |  |  | 80011 | 18-11-2022 NEFT/AXISP00338955137/RIUP22/1288/RANA BUILDERS 80011.00
51536 | GST Release Note | 2023-04-20 | 18 | 163886 |  | 163886 | 0 | 163886 | 0 | 0 | 0 | 0 | 0 |  |  | 163886 |  | RIUP22/1289 | 198686 | 0 |  |  | 198686 | 18-11-2022 NEFT/AXISP00338955128/RIUP22/1289/RANA BUILDERS 198686.00
51536 | Balwakhedi Village Pipe laying work | 2023-07-14 | 7 | 21245.37 |  | 21245 | 3824 | 25069 | 212 | 1062 | 1062 | 2125 | 3824 |  |  | 16784 |  | RIUP22/2469 | 250000 | 2500 |  |  | 247500 | 06-03-2023 NEFT/AXISP00369001730/RIUP22/2469/RANA BUILDERS 247500.00
51536 | GST Release Note | 2023-09-19 | 7 | 3824 |  | 3824 | 0 | 3824 | 0 | 0 | 0 | 0 | 0 |  |  | 3824 |  | RIUP23/214 |  |  |  |  | 163886 | 29-05-2023 NEFT/AXISP00393029881/RIUP23/214/RANA BUILDERS 163886.00
51536 | [22 empty] | 3824 | 27-09-2023 NEFT/AXISP00427962774/RIUP23/2321/RANA BUILDERS/ICIC0000975 3824.00
51536 | [22 empty] | 297000 | 13-09-2024 NEFT/AXISP00540414565/RIUP24/1784/RANA BUILDERS/ICIC0000975 297000.00