## Sheet1
Subcontractor: | SJ Construction
State: | Uttar Pradesh
District: | Shamli
Block: | GOHARPUR
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold Amount For Quantity excess against DPR | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | Total_Amount | UTR
[9 empty] | 1% | 5% | 10% | 10%
55384
55384 | GOHARPUR VILLAGE Pipeline Work | 2023-02-27 | 5 | 407561 | 18014 | 389547 | 70118.46 | 459667 | 4596.67 | 22983.35 | 45966.7 | 45966.7 | 70118.46 | 13771 | 274495 |  | RIUP22/2499 | 297000 | 297000 | 08-03-2023 NEFT/AXISP00369766201/RIUP22/2499/S J CONSTRUCTIO 297000.00
55384 | GOHARPUR VILLAGE Pipeline Work | 2023-11-23 | 7 | 614361 | 18014 | 596347 | 107342.46 | 703689.46 | 5963.47 | 29817.35 | 59634.7 | 59634.7 | 107342.46 | 31586.5 | 409710.28 |  | RIUP23/2242 | 70118 | 70118 | 06-10-2023 NEFT/AXISP00431402248/RIUP23/2242/S J CONSTRUCTION/PUNB0444200 ₹ 70,118.00
55384 | GOHARPUR VILLAGE Pipeline Work | 2024-10-26 | 17 | 135300 | 3960 | 131340 | 23641.2 | 154981.2 | 1313.4 | 6567 | 13134 | 13134 | 23641.2 | 33000 | 64191.6 |  | RIUP23/3631 |  | 312205 | 06-12-2023 NEFT/AXISP00450230203/RIUP23/3631/S J CONSTRUCTION/PUNB0444200 312205.00
55384 | GST release note |  | 5 | 70118.46 | [10 empty] | 70118.46 |  | RIUP23/3810 |  | 107342 | 27-12-2023 NEFT/AXISP00455698604/RIUP23/3810/S J CONSTRUCTION/PUNB0444200 107342.00
55384 | GST release note |  | 7 | 107342.46 | [10 empty] | 107342.46 |  | RIUP24/2555A |  | 60592 | 08-01-2025 NEFT/AXISP00595630485/RIUP24/2555A/S J CONSTRUCTION/PUNB0444200 60592.00
[10 empty] | 59367.7 | 118735.4 | 118735.4 | 201102.12 | 78357.5 | 925857.8 |  | Total Paid Amount Rs. - |  | 847257
[14 empty] | Total Payable Amount Rs. - |  |  | Balance |  | 78600.8
SJ Construction
Updated On 09-01-2025
[10 empty] | Total Hold |  | 296838.5
[10 empty] | DPR Excess Hold |  | 78357.5
[10 empty] | Advance / Balance Payable |  | 78600.8
Debit
[10 empty] | GST Remaining |  | 23641.2