## Sheet1
Subcontractor: | Shahrukh
State: | Uttar Pradesh
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold the Amount because the Qty. is more then the DPR | Final_Amount | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% | 5% | 10% | 18%
54707 | PALDA Village Pipe laying work. | 2023-06-26 | 4 | 538385.5 | 26973 | 511413 | 92054 | 603467 | 5114 | 25571 | 25571 | 51141 | 92054 | 0 | 404016 | 404016 | 30-06-2023 IFT/IFT23181232621/RIUP235/950/RAO BUILDERS 404016.00
54707 | GST Release Note | 2023-07-15 | 4 | 92054 | [10 empty] | 92054 | 92054 | 24-08-2023 IFT/IFT23236018742/RIUP235/1544/RAO BUILDERS 92054.00
54707 | PALDA Village Pipe laying work. | 2024-11-04 | 9 | 389177 | 17411 | 371766 | 66918 | 438684 | 3718 | 18588 | 37176.6 | 37177 | 66918 | 0 | 275106 | 198000 | 10-11-2023 IFT/IFT23314125334/RIUP235/3263/RAO BUILDERS 198000.00
0
55373 | Jafarpur Village Pipe laying work. | 2023-04-18 | 2 | 474276 | 26973 | 447303 | 80515 | 527818 | 4473 | 22365 | 22365 | 44730 | 80515 | 36933 | 316437 | 80515 | 13-06-2023 IFT/IFT23164043533/RIUP235/577/RAO BUILDERS 80515.00
55373 | GST Release Note | 2023-06-09 | 2 | 80515 | [8 empty] | 0 |  | 80515 | 316437 | 29-04-2023 29-04-2023 IFT/IFT231191700335/SPUP23/0316/RAO BUILDERS 316437.00
55373 | Jafarpur Village Pipe laying work. | 2023-10-08 | 8 | 328748.25 | 154114 | 174634 | 31434 | 206068 | 1746 | 8732 | 8732 | 17463 | 31434 | 36933 | 101028 | 99000 | 16-06-2023 IFT/IFT23167033290/RIUP235/687/RAO BUILDERS 99000.00
55373 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 2028 | 23-10-2023 IFT/IFT23296011166/RIUP235/2779/RAO BUILDERS 2028.00
57874 | Lalukheri Village Pipe laying work. | 2003-08-19 | 7 | 415501.5 | 23823.8 | 391678 | 70502.04 | 462180.04 | 3917 | 19584 | 19584 | 39168 | 70502.04 | 22940 | 286485 | 286485 | 28-08-2023 IFT/IFT23240044116/RIUP235/1722/RAO BUILDERS 286485.00
57874 | GST Release Note | 2023-09-04 | 7 | 70502 | 0 | 70502 |  | 70502 | [6 empty] | 70502 | 70502 | 15-09-2023 IFT/IFT23258027570/RIUP235/2030/RAO BUILDERS 70502.00