## Sheet1
Subcontractor: | Shree Shyam Construction shamli
State: | Uttar Pradesh | [5 empty] | Pipeline Laying work
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | With GST Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold Amount For Quantity excess against DPR | Final_Amount |  | PAYMENT NOTE No. | Amount | TDS Amount @ 1% on BASIC AMOUNT | Total_Amount | UTR | Advance Village Wise
[9 empty] | 1% | 5% | 10% | 10% | [6 empty] | 1%
59129
59129 | Yousufpur Village Pipeline laying work | 2023-08-30 | 5 | 294956 | 0 | 294956 | 53092 | 348048 | 2949.56 | 14748 | 29496 | 29496 | 53092 | 0 | 218266 |  | RIUP22/1935 | 218267 | 0 | 218267 | 12-09-2023 IFT/IFT23255016179/RIUP23/1935/SHRI SHYAM CONSTRU ₹ 2,18,266.00
59129 | Yousufpur Village Pipeline laying work | 2023-09-20 | 6 | 269168 | 0 | 269168 | 48450 | 317618 | 2691.68 | 13458 | 26917 | 26917 | 48450 | 0 | 199184 |  | RIUP22/2220 | 199183 | 0 | 199183 | 22-09-2023 IFT/IFT23265052076/RIUP23/2220/SHRI SHYAM CONSTRU 199183.00
59129 | Yousufpur Village Pipeline laying work | 2023-10-12 | 7 | 231234 | 0 | 231234 | 41622 | 272856 | 2312.34 | 11562 | 23123 | 23123 | 41622 | 59115 | 111999 |  | RIUP23/2640 | 198000 |  | 198000 | 13-10-2023 IFT/IFT23286012047/RIUP23/2640a/SHRI SHYAM CONSTRU 198000.00
59129 | GST release note | 2023-08-30 | 5 | 53092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53092 |  |  |  |  | 53092 | 03-11-2023 IFT/IFT23307022771/RIUP23/2971/SHRI SHYAM CONSTRU ₹ 53,092.00
59129 | GST release note | 2023-09-20 | 6 | 48450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48450 |  |  |  |  | 49500 | 09-11-2023 IFT/IFT23313075544/RIUP23/3199/SHRI SHYAM CONSTRU 49500.00
59129 | Yousufpur Village Pipeline laying work | 2023-11-08 | 9 | 134200 | 0 | 134200 | 24156 | 158356 | 1583.56 | 7917.8 | 15835.6 | 15835.6 | 24156 | 24156 | 99308 |  |  |  |  | 48450 | 24-11-2023 IFT/IFT23328067586/RIUP23/3358/SHRI SHYAM CONSTRU 48450.00
59129 | Yousufpur Village Pipeline laying work | 2023-12-14 | 10 | 57750 | 4504 | 53246 | 9584.28 | 62830.28 | 532.46 | 2662.3 | 5324.6 | 5324.6 | 9584.28 | 0 | 39402 |  |  |  |  | 24156 | 18-12-2023 IFT/IFT23352037913/RIUP23/3815/SHRI SHYAM CONSTRU 24156.00
59129 | GST release note |  | 7 | 41622 | [10 empty] | 41622 |  |  |  |  | 41622 | 18-12-2023 IFT/IFT23352037912/RIUP23/3779/SHRI SHYAM CONSTRU 41622.00
59129 | GST release note |  | 9 | 24156 | [10 empty] | 24156 |  |  |  |  | 3210 | 09-01-2024 IFT/IFT24009037578/RIUP23/4074/SHRI SHYAM CONSTRU 3210.00
59129 | GST release note |  | 10 | 9584.28 | [10 empty] | 9584.28 |  |  |  |  | 9584 | 02-02-2024 IFT/IFT24033021062/RIUP23/4376/SHRI SHYAM CONSTRU 9584.00
[16 empty] | 59965 | [5 empty] | -0.72
59965 | Sahpat Village Pipeline laying work | 2023-10-31 | 8 | 382513 | 9007 | 373506 | 67231 | 440737 | 3735.06 | 18675 | 37351 | 37351 | 67231 | 40445 | 235949 |  |  |  |  | 235948 | 07-11-2023 IFT/IFT23311113725/RIUP23/3100/SHRI SHYAM CONSTRU 235948.00
59965 | Sahpat Village Pipeline laying work | 2023-12-16 | 11 | 79175 | 4503 | 74672 | 13441 | 88113 | 746.72 | 3734 | 7467 | 7467 | 13441 | 14749 | 40508 |  |  |  |  | 67231 | 18-12-2023 IFT/IFT23352037914/RIUP23/3814/SHRI SHYAM CONSTRU 67231.00
59965 | GST release note |  | 8 | 67231 | [10 empty] | 67231 |  |  |  |  | 40507 | 04-01-2024 IFT/IFT24004052742/RIUP23/4103/SHRI SHYAM CONSTRU 40507.00
59965 | GST release note |  | 11 | 13441 | [10 empty] | 13441 |  |  |  |  | 13441 | 01-02-2024 IFT/IFT24032117757/RIUP23/4377/SHRI SHYAM CONSTRU 13441.00
59965 | Sahpat Village Pipeline laying work | 2024-02-27 | 13 | 398706 | 31525 | 367181 | 66093 | 433274 | 3671.81 | 18359 | 36718 | 36718 | 66093 | 20850 | 250864 |  |  |  |  | 250864 | 22-03-2024 IFT/IFT24082070380/RIUP23/5089/SHRI SHYAM CONSTRU 250864.00
59965 | GST release note |  | 13 | 66093 | [10 empty] | 66093 |  |  |  |  | 66093 | 06-04-2024 IFT/IFT24097097244/RIUP23/5311/SHRI SHYAM CONSTRU 66093.00 | 2
59965
59965
[9 empty] | 18223.19 | 91116.1 | 182232.2 | 182232.2 | 323669.28 | 159315 | 1519149.28 |  |  |  |  | 1519148 | Total Paid
[20 empty] | 1.28 | Balance Payable
Shri Shyam Construction
22-08-2024 ( Vikash )
[10 empty] | Total Hold |  | 455580.5
[10 empty] | DPR Excess Hold |  | 159315
[10 empty] | Advance / Surplus |  | 1.28
[10 empty] | Debit |  | 0
[10 empty] | GST Remaining |  | Nil
Qty as per updated Dawing
|  |  | Dia | Length | CUM |  |  | ITEM | DPR | CUM | EXCESS | RATE | AMT
|  |  | 63 | 5175 | 4794.2 | As per updated drawing |  | 90MM | 588 | 625.9 | 37.9 | 95 | 3600.5
|  |  | 75 | 694 | 678.9 |  |  | j HOOK | 0 | 674 | 674 | 8 | 5392
|  |  | 90 | 588 | 625.9 |  | As per old DPR | BOE | 37.13 | 301.7 | 264.57 | 50 | 13228.5
|  |  | 110 | 434 | 421.6 | [6 empty] | hold amt | 22221
|  |  | 160 | 774 | 768 | [6 empty] | prev hold | #REF!
|  |  | 200 | 273 | 189.5 | [6 empty] | to be hold | #REF!
|  |  | Total | 7938