## Sheet1
Subcontractor: | Shri Balaji Construction shamli
State: | Uttar Pradesh | [6 empty] | Pipeline Laying work | [8 empty] | 2024-04-26
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | bill no | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold Amount For Quantity excess against DPR | Final_Amount |  | PAYMENT NOTE No. | Amount | TDS Amount @ 1% on BASIC AMOUNT | Total_Amount | UTR | Advance Village Wise
[10 empty] | 1% | 5% | 10% | 10% | [6 empty] | 1%
55713
55713 | Dulakheri Village Pipeline laying work | 2023-03-15 | 8 | 1 | 139413.72 | 0 | 139414 | 25095 | 164509 | 1394 | 6971 | 13941 | 13941 | 25095 | 0 | 103167 |  | RIUP22/2742 | 80000 | 800 | 79200 | 27-03-2023 IFT/IFT23086029340/RIUP22/2742/SHRI BALAJI CONSTR 79200.00 | -69066.34
55713 | Dulakheri Village Pipeline laying work | 2023-04-01 | 1 | 2 | 389203 | 0 | 389203 | 70057 | 459260 | 3892 | 19460 | 38920 | 38920 | 70057 | 0 | 288011 |  | SPUP23/0067 | 20000 | 200 | 19800 | 11-04-2023 IFT/IFT23101022094/SPUP23/0067/SHRI BALAJI CONSTR 19800.00
55713 | Dulakheri Village Pipeline laying work | 2023-05-11 | 2 | 3 | 386677 | 0 | 386677 | 69602 | 456279 | 3867 | 19334 | 38668 | 38668 | 69602 | 8865 | 277275 |  | RIUP23/049 | 150000 | 1500 | 148500 | 21-04-2023 IFT/IFT23111033830/RIUP23/049/SHRI BALAJI CONSTRU 148500.00
55713 | GST Release Note | 2023-05-18 | 2 |  | 69602 | [10 empty] | 69602 |  | SPUP23/0358 | 143678 | 0 | 143678 | 06-05-2023 IFT/IFT23126013874/SPUP23/0358/SHRI BALAJI CONSTR 143678.00
55713 | GST Release Note | 2023-05-18 | 8 |  | 25095 | [10 empty] | 25095 |  | RIUP23/274 | 25094 | 0 | 25094 | 18-05-2023 IFT/IFT23138055169/RIUP23/274/SHRI BALAJI CONSTRU 25094.00
55713 | GST Release Note | 2023-04-01 | 1 |  | 70057 | 0 | 70057 | 0 | 70057 | 0 | 0 | 0 | 0 | 0 | 0 | 70057 |  | RIUP23/275 | 277276 |  | 277276 | 18-05-2023 IFT/IFT23138055168/RIUP23/275/SHRI BALAJI CONSTRU 277276.00
55713 | Dulakheri Village Pipeline laying work | 2023-06-25 | 3 | 4 | 657719 | 0 | 657719 | 118389 | 776108 | 6577 | 32886 | 65772 | 65772 | 118389 | 13556 | 473156 |  | RIUP23/631 | 100000 | 1000 | 99000 | 13-06-2023 IFT/IFT23164032243/RIUP23/631/SHRI BALAJI CONSTRU 99000.00
55713 | Dulakheri Village Pipeline laying work | 2023-08-26 | 5 | 5 | 331006.5 | 1.5 | 331005 | 59581 | 390586 | 3310 | 16550 | 0 | 0 | 59581 | 0 | 311145 |  | RIUP23/738 | 70057 | 0 | 70057 | 21-06-2023 IFT/IFT23172005911/RIUP23/738/SHRI BALAJI CONSTRU 70057.00
55713 | Dulakheri Village Pipeline laying work | 2023-09-20 | 7 | 7 | 310769 | 38150 | 272619 | 49071 | 321690 | 2726 | 13631 | 27262 | 27262 | 49071 | 0 | 201738 |  | RIUP23/990 | 374156 |  | 374156 | 01-07-2023 IFT/IFT23182088929/RIUP23/990/SHRI BALAJI CONSTRU ₹ 3,74,156.00
55713 | Dulakheri Village Pipeline laying work | 2023-09-27 | 9 | 9 | 403307 | 0 | 403307 | 72595 | 475902 | 4033 | 20165 | 40331 | 40331 | 72595 | 0 | 298447 |  | RIUP23/1379 | 100000 | 1000 | 99000 | 04-08-2023 IFT/IFT23216118401/RIUP23/1379/SHRI BALAJI CONSTR ₹ 99,000.00
55713 | Dulakheri Village Pipeline laying work | 2023-12-08 | 13 | 13 | 299333 | 0 | 299333 | 53879.94 | 353212.94 | 2993.33 | 14966.65 | 29933.3 | 0 | 53879.94 | 0 | 251439.72 |  | RIUP23/1751 | 150000 | 1500 | 148500 | 28-08-2023 IFT/IFT23240055694/RIUP23/1751/SHRI BALAJI CONSTR 148500.00
55713 | GST Release Note |  | 4 |  | 118389 | [10 empty] | 118389 |  | RIUP23/1898 | 63645 |  | 63645 | 07-09-2023 IFT/IFT23250068458/RIUP23/1898/SHRI BALAJI CONSTR 63645.00
55713 | GST Release Note |  | 5 |  | 59581 | [10 empty] | 59581 |  | RIUP23/2217 | 150000 | 1500 | 148500 | 22-09-2023 IFT/IFT23265052077/RIUP23/2217/SHRI BALAJI CONSTR 148500.00
55713 | GST Release Note |  | 7 |  | 49071 | [10 empty] | 49071 |  | RIUP23/2473 | 149947 |  | 149947 | 04-10-2023 IFT/IFT23277053668/RIUP23/2473/SHRI BALAJI CONSTR 149947.00
55713 | GST Release Note |  | 9 |  | 72595 | [10 empty] | 72595 |  | RIUP23/2474 | 201737 |  | 201737 | 04-10-2023 IFT/IFT23277053669/RIUP23/2474/SHRI BALAJI CONSTR 201737.00
55713 | GST Release Note |  | 13 |  | 53879.94 | [10 empty] | 53879.94 |  | RIUP23/2938 | 69602 |  | 69602 | 08-11-2023 IFT/IFT23312068902/RIUP23/2938/SHRI BALAJI CONSTR 69602.00
55713 | [17 empty] | RIUP23/3364 | 177970 |  | 177970 | 23-11-2023 IFT/IFT23327021226/RIUP23/3364/SHRI BALAJI CONSTR ₹ 1,77,970.00
55713 | [17 empty] | RIUP23/3923 | 80000 | 800 | 79200 | 22-12-2023 IFT/IFT23356037807/RIUP23/3923/SHRI BALAJI CONSTR 79200.00
55713 | [17 empty] | RIUP23/3956 | 49071 |  | 49071 | 27-12-2023 IFT/IFT23361009770/RIUP23/3956/SHRI BALAJI CONSTR 49071.00
55713 | [17 empty] | RIUP23/3957 | 142307 |  | 142307 | 27-12-2023 IFT/IFT23361009776/RIUP23/3957/SHRI BALAJI CONSTR 142307.00
55713 | [17 empty] | RIUP23/4037 | 72595 |  | 72595 | 08-01-2024 IFT/IFT24008065306/RIUP23/4037/SHRI BALAJI CONSTR ₹ 72,595.00
55713 | [17 empty] | RIUP23/4367 | 99000 |  | 99000 | 18-01-2024 IFT/IFT24018032119/RIUP23/4367/SHRI BALAJI CONSTR 99000.00
55713 | [17 empty] | RIUP23/5134 |  |  | 53880 | 26-04-2024 IFT/IFT24117006560/RIUP23/5134/SHRI BALAJI CONSTR 53880.00
53640
53640 | Nojal Nojli Village Pipeline laying work | 2022-12-01 | 4 |  | 357732 | 0 | 357732 | 64392 | 422124 | 3577 | 17887 | 35773 | 35773 | 64392 | 18743 | 245979 |  | RIUP22/1475 | 245979 | 0 | 245979 | 10-12-2022 IFT/IFT22344008545/RIUP22/1475/SHRI BALAJI CONSTR 245979.00 | -340357
53640 | Nojal Nojli Village Pipeline laying work | 2023-01-01 | 5 |  | 877768 | 0 | 877768 | 157998 | 1035766 | 8778 | 43888 | 87777 | 87777 | 157998 | 64890 | 584658 |  | RIUP22/1803 | 584658 | 0 | 584658 | 07-01-2023 IFT/IFT23007044361/RIUP22/1803/SHRI BALAJI CONSTR 584658.00
53640 | GST release note | 2023-01-21 | 4 |  | 64392 |  | 64392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64392 |  | RIUP22/1978 | 64392 | 0 | 64392 | 24-01-2023 IFT/IFT23024007687/RIUP22/1978/SHRIBALAJI CONSTR 64392.00
53640 | Nojal Nojli Village Pipeline laying work | 2023-01-30 | 6 |  | 545978 | 0 | 545978 | 98276 | 644254 | 5460 | 27299 | 54598 | 54598 | 98276 | 40097 | 363926 |  | RIUP22/2084 | 363926 | 0 | 363926 | 04-02-2023 IFT/IFT23035022862/RIUP22/2084/SHRI BALAJI CONSTR ₹ 3,63,926.00
53640 | Nojal Nojli Village Pipeline laying work | 2023-03-02 | 7 |  | 555391 | 0 | 555391 | 99970 | 655361 | 5554 | 27770 | 55539 | 55539 | 99970 | 0 | 410989 |  | RIUP22/2214 | 100000 | 1000 | 99000 | 17-02-2023 IFT/IFT23048032050/RIUP22/2214/SHRI BALAJI CONSTR 99000.00
53640 | GST release note | 2023-04-05 | 5 |  | 157998 | [10 empty] | 157998 |  | RIUP22/2641 | 250000 | 2500 | 247500 | 17-03-2023 IFT/IFT23076014164/RIUP22/2641/SHRI BALAJI CONSTR 247500.00
53640 | GST release note | 2023-04-05 | 6 |  | 98276 | [10 empty] | 98276 |  | RIUP22/2748 | 100000 | 1000 | 99000 | 27-03-2023 IFT/IFT23086032017/RIUP22/2748/SHRI BALAJI CONSTR 99000.00
53640 | GST release note | 2023-04-29 | 7 |  | 99970 | [10 empty] | 99970 |  |  | 256274 |  | 256274 | 2023 April 10 --- Shri Balaji Constructions --- Rs. 2,56,274 ----- /IFT23100051022
53640 | Nojal Nojli Village Pipeline laying work | 2023-07-27 | 4 |  | 454626 | 110427.09 | 344198.91 | 61956 | 406154.91 | 3442 | 17210 | 34420 | 34420 | 61956 | 0 | 254707 |  | RIUP23/273 | 99970 |  | 99970 | 19-05-2023 IFT/IFT23139017435/RIUP23/273/SHRI BALAJI CONSTRU ₹ 99,970.00
53640 | Nojal Nojli Village Pipeline laying work | 2023-09-05 | 6 |  | 320402 | 0 | 320402 | 57672 | 378074 | 3204 | 16020 | 32040 | 32040 | 57672 | 0 | 237098 |  | RIUP23/1404 | 220197 |  | 220197 | 08-08-2023 IFT/IFT23220049166/RIUP23/1404/SHRI BALAJI CONSTR 220197.00
53640 | Nojal Nojli Village Pipeline laying work | 2023-09-26 | 8 |  | 175450 | 0 | 175450 | 31581 | 207031 | 1755 | 8773 | 17545 | 17545 | 31581 | 0 | 129832 |  | RIUP23/1717 | 50000 | 500 | 49500 | 25-08-2023 IFT/IFT23237043051/RIUP23/1717/SHRI BALAJI CONSTR 49500.00
53640 | Nojal Nojli Village Pipeline laying work | 2023-10-20 | 11 |  | 671125 | 0 | 671125 | 120803 | 791928 | 6711 | 33556 | 67113 | 67113 | 120803 | 28618 | 468014 |  | RIUP23/2080 | 187599 | 0 | 187599 | 18-09-2023 IFT/IFT23261006068/RIUP23/2080/SHRI BALAJI CONSTR 187599.00
53640 | GST release note |  | 4 |  | 61956 | [10 empty] | 61956 |  | RIUP23/2466 | 129832 |  | 129832 | 04-10-2023 IFT/IFT23277053670/RIUP23/2466/SHRI BALAJI CONSTR 129832.00
53640 | GST release note |  | 8 |  | 89253 | [10 empty] | 89253 |  | RIUP23/2854 | 150000 | 1500 | 148500 | 25-10-2023 IFT/IFT23298013281/RIUP23/2854/SHRI BALAJI CONSTR 148500.00
53640 | GST release note |  | 11 |  | 120803 | [10 empty] | 120803 |  | RIUP23/3011 | 319514 |  | 319514 | 08-11-2023 IFT/IFT23312068903/RIUP23/3011/SHRI BALAJI CONSTR 319514.00
53640 | Nojal Nojli Village Pipeline laying work | 2024-03-09 | 14 |  | 205283 | 19075 | 186208 | 33517 | 219725 | 1862 | 9310 | 18621 | 18621 | 33517 | 103330 | 34464 |  | RIUP23/3365 | 61956 |  | 61956 | 24-11-2023 IFT/IFT23328055355/RIUP23/3365/SHRI BALAJI CONSTR 61956.00
53640 | GST release note |  | 14 |  | 33517 | [10 empty] | 33517 |  | RIUP23/3768 | 150000 | 1500 | 148500 | 15-12-2023 IFT/IFT23349026038/RIUP23/3768/SHRI BALAJI CONSTR 148500.00
53640 | Nojal Nojli Village Pipeline laying work | 2024-10-29 | 12 |  | 907318 | 221270 | 686048 | 123489 | 809537 | 6860 | 34302 | 68605 | 68605 | 123489 |  | 507676 |  | RIUP23/3775 | 89254 |  | 89254 | 27-12-2023 IFT/IFT23361009769/RIUP23/3775/SHRI BALAJI CONSTR 89254.00
53640 | GST release note |  | 12 |  | 123489 | [10 empty] | 123489 |  | RIUP23/5132 | 120803 |  | 120803 | 22-03-2024 IFT/IFT24082070375/RIUP23/5132/SHRI BALAJI CONSTR 120803.00
53640 | [17 empty] | RIUP24/2126 | 250000 | 2500 | 247500 | 05-10-2024 IFT/IFT24279099632/RIUP24/2126/SHRI BALAJI CONSTR 247500.00
53640 | [20 empty] | 247500 | 21-10-2024 IFT/IFT24295027658/RIUP24/2257/SHRI BALAJI CONSTR 247500.00
53640 | [20 empty] | 198000 | 30-10-2024 IFT/IFT24304255883/RIUP24/2364/SHRI BALAJI CONSTR 198000.00
53640 | [20 empty] | 198000 | 04-12-2024 IFT/IFT24339039524/RIUP24/2627/SHRI BALAJI CONSTR 198000.00
51737
51737 | Mantmanti Village Pipeline laying work | 2022-09-20 | 1 |  | 2107070.25 | 54042 | 2053028.25 | 369545 | 2422573.25 | 20530.2825 | 205302.825 |  | 205302.825 | 369545 | 314949 | 1306943.3175 |  | RIUP22/412 | 200000 | 2000 | 198000 | 28-07-2022 IFT/IFT22209020738/RIUP22/412/SHRI BALAJI CONSTRU 198000.00 | -823659.3645
51737 | Mantmanti Village Pipeline laying work | 2022-10-13 | 2 |  | 231800.2 | 0 | 231800.2 | 41724 | 273524.2 | 2318.002 | 23180.02 |  | 23180.02 | 41724 |  | 183122.158 |  | RIUP22/554 | 200000 | 2000 | 198000 | 20-08-2022 IFT/IFT22232005689/RIUP22/554/SHRI BALAJI CONSTRU 198000.00
51737 | GST release note |  | 1 |  | 369545 | 0 | 369545 | 0 | 369545 | 0 | [5 empty] | 369545 |  | RIUP22/586 | 150000 | 1500 | 148500 | 22-08-2022 IFT/IFT22234028107/RIUP22/586/SHRI BALAJI CONSTRU 148500.00
51737 | GST release note |  | 2 |  | 41724 | 0 | 41724 | 0 | 41724 | 0 | 0 |  |  |  | 0 | 41724 |  | RIUP22/884 | 600000 | 6000 | 594000 | 03-10-2022 IFT/IFT22276009534/RIUP22/884/SHRI BALAJI CONSTRU 594000.00
51737 | Mantmanti Village Pipeline laying work | 2023-10-19 | 10 |  | 270086 | 0 | 270086 | 48615.48 | 318701.48 | 2700.86 | 13504.3 | 27008.6 | 27008.6 | 48615.48 | 0 | 199863.64 |  | RIUP22/1078 | 300000 | 3000 | 297000 | 21-10-2022 IFT/IFT22294059834/RIUP22/1078/SHRI BALAJI CONSTR 297000.00
51737 | Mantmanti Village Pipeline laying work | 2023-11-01 | 12 |  | 316012 | 0 | 316012 | 56882.16 | 372894.16 | 3160.12 | 15800.6 | 31601.2 | 31601.2 | 56882.16 | 0 | 233848.88 |  | RIUP22/1181 | 54565 | 0 | 54565 | 05-11-2022 IFT/IFT22309031468/RIUP22/1181/SHRI BALAJI CONSTR 54565.00
51737 | GST release note |  | 10 |  | 48615.48 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | 48615.48 |  | RIUP22/1482 | 200000 | 0 | 200000 | 10-12-2022 IFT/IFT22344008547/RIUP22/1482/SHRI BALAJI CONSTR 200000.00
51737 | GST release note |  | 12 |  | 56882.16 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | 56882.16 |  | RIUP22/1632 | 369545 |  | 369545 | 27-12-2022 IFT/IFT22361012953/RIUP22/1632/SHRI BALAJI CONSTR 369545.00
51737 | [17 empty] | RIUP22/1977 | 41724 |  | 41724 | 24-01-2023 IFT/IFT23024012629/RIUP22/1977/SHRI BALAJI CONSTR ₹ 41,724.00
51737 | [17 empty] | RIUP22/2361 | 50000 | 500 | 49500 | 28-02-2023 IFT/IFT23059053147/RIUP22/2361/SHRI BALAJI CONSTR 49500.00
51737 | [17 empty] | RIUP23/2830 | 150000 | 1500 | 148500 | 23-10-2023 IFT/IFT23296024452/RIUP23/2830/SHRI BALAJI CONSTR 148500.00
51737 | [17 empty] | RIUP23/2016 | 120000 | 1200 | 118800 | 14-09-2023 IFT/IFT23257021729/RIUP23/2016/SHRI BALAJI CONSTR 118800.00
51737 | [17 empty] | RIUP23/3137 | 100000 | 1000 | 99000 | 08-11-2023 IFT/IFT23312076789/RIUP23/3137/SHRI BALAJI CONSTR 99000.00
51737 | [17 empty] | RIUP23/3641 | 17873 |  | 17873 | 07-12-2023 IFT/IFT23341087153/RIUP23/3641/SHRI BALAJI CONSTR 17873.00
51737 | [17 empty] | RIUP23/3955 | 48615 |  | 48615 | 08-01-2024 IFT/IFT24008065305/RIUP23/3955/SHRI BALAJI CONSTR ₹ 48,615.00
51737 | [17 empty] | RIUP23/4815 | 80000 | 800 | 79200 | 22-02-2024 IFT/IFT24053032838/RIUP23/4815/SHRI BALAJI CONSTR 79200.00
51737 | [20 empty] | 56882 | 26-04-2024 IFT/IFT24117006559/RIUP23/5133/SHRI BALAJI CONSTR 56882.00 682517655.06 CBB
51737 | [20 empty] | 99000 | 10-09-2024 IFT/IFT24254007340/RIUP24/1727/SHRI BALAJI CONSTR 99000.00
51737 | [20 empty] | 74250 | 17-09-2024 IFT/IFT24261027201/RIUP24/1806/SHRI BALAJI CONSTR 74250.00
51737 | [20 empty] | 74250 | 21-09-2024 IFT/IFT24265015454/RIUP24/1895/SHRI BALAJI CONSTR 74250.00
51737 | [20 empty] | 99000 | 01-10-2024 IFT/IFT24275137125/RIUP24/2011/SHRI BALAJI CONSTR 99000.00
51737 | [20 empty] | 198000 | 30-10-2024 IFT/IFT24304255885/RIUP24/2365/SHRI BALAJI CONSTR 198000.00
62993 | [16 empty] | 62993
62993 | Bhatu village pipeline work | 2024-03-12 | 15 |  | 260280 |  | 260280 | 46850.4 | 307130.4 | 2602.8 | 13014 | 26028 | 26028 | 46850.4 | 8870 | 183737.2 |  |  |  |  | 183737 | 17-05-2024 IFT/IFT24138018957/RIUP24/0143/SHRI BALAJI CONSTR 183737.00 | 46850.6
62993 | GST release note |  | 15 |  | 46850.4 | [10 empty] | 46850.4
62993
[11 empty] | 650780.395 | 811496.1 | 1010045.645 | 1931540.98 | 601918 | 9480777.8955 |  | Total Paid Amount Rs. - |  |  | 10667010 |  | -1186232.1045
[18 empty] | Balance Payable Amount Rs. - |  |  | -1186232.1045
Shri Balaji Construction
2025-03-20
[9 empty] | Hold Amount |  | 2472322.14
[9 empty] | Advance / Surplus |  | -1186232.1045
[9 empty] | Hold Amount For Quantity excess against DPR |  | 601918
[9 empty] | Debit |  | -123987
[9 empty] | GST Remaining |  | Nil
Qty as per updated Dawing
|  |  | Dia |  | Length | CUM |  |  | ITEM | DPR | CUM | EXCESS | RATE | AMT
|  |  | 63 |  | 5175 | 4794.2 | As per updated drawing |  | 90MM | 588 | 625.9 | 37.9 | 95 | 3600.5
|  |  | 75 |  | 694 | 678.9 |  |  | j HOOK | 0 | 674 | 674 | 8 | 5392
|  |  | 90 |  | 588 | 625.9 |  | As per old DPR | BOE | 37.13 | 301.7 | 264.57 | 50 | 13228.5
|  |  | 110 |  | 434 | 421.6 | [6 empty] | hold amt | 22221
|  |  | 160 |  | 774 | 768 | [6 empty] | prev hold | 8865
|  |  | 200 |  | 273 | 189.5 | [6 empty] | to be hold | 13356
|  |  | Total |  | 7938