## Sheet1
Subcontractor: | Shri Mantai Mahate Construction
State: | Uttar Pradesh | [5 empty] | Pipeline Laying work
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold Amount For Quantity excess against DPR | Final_Amount |  | PAYMENT NOTE No. | Amount | TDS Amount @ 1% on BASIC AMOUNT | Total_Amount | UTR
[9 empty] | 1% | 5% | 10% | 10% | [6 empty] | 1%
55713
58753 | Bibipur Jalabad Village Pipeline laying work | 2023-10-16 | 2 | 344403 | 126098 | 218305 | 39295 | 257600 | 2183 | 10915 | 21831 | 21831 | 39295 | 13195 | 148350 |  | RIUP22/1532 | 100000 | 1000 | 99000 | 14-08-2023 NEFT/AXISP00415803579/RIUP23/1532/SHRI MANTAI MAH ₹ 99,000.00
58753 | GST Release note | 2023-10-16 | 2 | 39295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39295 |  | RIUP23/2863 | 49351 |  | 49351 | 25-10-2023 NEFT/AXISP00436928374/RIUP23/2863/SHRI MANTAI MAHATE/INDB0000042 49351.00
58753 | Bibipur Jalabad Village Pipeline laying work | 2023-12-11 | 3 | 110550 | 98176 | 12374 | 0 | 12374 | 123.74 | 618.7 | 1237.4 | 1237.4 | 0 | 2227 | 9156.76 |  | RIUP23/3776 |  |  | 39295 | 18-12-2023 NEFT/AXISP00453885476/RIUP23/3776/SHRI MANTAIMAHATE/INDB0000042 39295.00
[14 empty] | Total Payable Amount Rs. - | 196801.76 |  | Total Paid Amount Rs. - |  |  | 187646
[5 empty] | 224274 |  | 39295 | 269974 | 2306.74 | 11533.7 | 23068.4 | 23068.4 | 39295 | 15422 |  |  | Balance Payable Amount Rs. - |  |  | 9155.76
Qty as per updated Dawing
|  |  | Dia | Length | CUM |  |  | ITEM | DPR | CUM | EXCESS | RATE | AMT |  |  |  | Updated On 29-01-2024
|  |  | 63 | 5175 | 4794.2 | As per updated drawing |  | 90MM | 588 | 625.9 | 37.9 | 95 | 3600.5 |  |  |  | Hold Amount |  | 59977.24
|  |  | 75 | 694 | 678.9 |  |  | j HOOK | 0 | 674 | 674 | 8 | 5392 |  |  |  | Advance / Surplus |  | 9155.76
|  |  | 90 | 588 | 625.9 |  | As per old DPR | BOE | 37.13 | 301.7 | 264.57 | 50 | 13228.5
|  |  | 110 | 434 | 421.6 | [6 empty] | hold amt | 22221
|  |  | 160 | 774 | 768 | [6 empty] | prev hold | 2227
|  |  | 200 | 273 | 189.5 | [6 empty] | to be hold | 19994
|  |  | Total | 7938