## Sheet1
Subcontractor: | M/s Sharda Constructions
State: | Uttar Pradesh | [5 empty] | Pump house work and chamber work
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | GST | SD_Amount | Final_Amount | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | SD (20%) | Advance paid | Total_Amount | UTR
[7 empty] | 18% |  | 1% |  | 5% |  |  |  | 1% | 20%
52000 | Yarpur village PH Work | 2023-09-30 | 1 | 306000 | 0 | 306000 | 55080 | 361080 | 3060 | 55080 | 15300 | 287640 | RIUP22/900 | 346500 | 0 | 0 | 0 | 346500 | 04-10-2022 NEFT/AXISP00325570958/RIUP22/900/SHARDA CONSTRUCT 346500.00
52013 | Bhadev village Pump house work | 2023-09-30 | 1 | 306000 | 19075 | 286925 | 51646.5 | 338571.5 | 2869 | 51646.5 | 14346 | 269710 | RIUP22/544 | 200000 | 0 | 0 | 0 | 200000 | 20-08-2022 NEFT/AXISP00313032386/RIUP22/544/SHARDA CONSTRUCT 198000.00
52013 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | RIUP22/899 | 150000 | 0 | 0 | 0 | 150000 | 04-10-2022 NEFT/AXISP00325570960/RIUP22/899/SHARDA CONSTRUCT 148500.00
52013
52014 | Khera Gadai village Construction of Pump house and chamber work | 2022-12-07 | 4 | 228600 | 0 | 228600 | 0 | 228600 | 2286 |  | 11430 | 214884 | RIUP22/545 | 200000 | 0 | 0 | 0 | 200000 | 20-08-2022 NEFT/AXISP00313032387/RIUP22/545/SHARDA CONSTRUCT 198000.00
52014 | Khera Gadai village Construction of Pump house and chamber work | 2023-09-30 | 2 | 321000 |  | 321000 | 57780 | 378780 | 3210 | 57780 | 16050 | 301740 | RIUP22/902 | 150000 | 0 | 0 | 0 | 150000 | 04-10-2022 NEFT/AXISP00325570960/RIUP22/902/SHARDA CONSTRUCT 148500.00
52014
52014
52015 | Titarsi village PH Work | 2023-09-30 | 3 | 256000 | 0 | 256000 | 46080 | 302080 | 2560 | 46080 | 12800 | 240640 | RIUP22/546 |  | 0 | 0 | 0 | 99000 | 20-08-2022 NEFT/AXISP00313032388/RIUP22/546/SHARDA CONSTRUCT 99000.00
52015 | [12 empty] | RIUP22/764 |  | 0 | 0 | 0 | 99000 | 16-09-2022 NEFT/AXISP00320727444/RIUP22/764/SHARDA CONSTRUCT 99000.00
52015 | [12 empty] | RIUP22/901 |  |  |  |  | 99000 | 04-10-2022 NEFT/AXISP00325570959/RIUP22/901/SHARDA CONSTRUCT 99000.00
52015 | [12 empty] | RIUP22/1824 |  |  |  |  | 49500 | 10-01-2023 NEFT/AXISP00353729302/RIUP22/1824/SHARDA CONSTRUC 49500.00
52016 | Goharni village Construction of Pump house and chamber work | 2022-12-07 | 6 | 152400 | 0 | 152400 | 0 | 152400 | 1524 |  | 7620 | 143256 | RIUP22/547 | 100000 | 0 | 0 | 0 | 100000 | 20-08-2022 NEFT/AXISP00313032389/RIUP22/547/SHARDA CONSTRUCT 99000.00
52016 | Goharni village Construction of Pump house and chamber work | 2023-09-30 | 6 | 211000 |  | 211000 | 37980 | 248980 | 2110 | 37980 | 10550 | 198340 | RIUP22/765 | 100000 | 0 | 0 | 0 | 100000 | 16-09-2022 NEFT/AXISP00320727445/RIUP22/765/SHARDA CONSTRUCT 99000.0
52016 | [12 empty] | RIUP22/903 | 100000 | 0 | 0 | 0 | 100000 | 04-10-2022 NEFT/AXISP00325570961/RIUP22/903/SHARDA CONSTRUCT 99000.00
52016 | [12 empty] | RIUP22/1825 | 49500 |  |  |  | 49500 | 10-01-2023 NEFT/AXISP00353729303/RIUP22/1825/SHARDA CONSTRUC 49500.00
52493 | mahatpur village PH work | 2023-09-30 | 5 | 325000 | 0 | 325000 | 58500 | 383500 | 3250 | 58500 | 16250 | 305500 | RIUP22/766 | 198000 | 0 | 0 | 0 | 198000 | 16-09-2022 NEFT/AXISP00320727446/RIUP22/766/SHARDA CONSTRUCT 198000.00
52493 | [12 empty] | RIUP22/898 | 148500 |  |  |  | 148500 | 04-10-2022 NEFT/AXISP00325570957/RIUP22/898/SHARDA CONSTRUCT 148500.00
52493
[9 empty] | 20869 | 307066.5 | 104346
[9 empty] | Total Payable Amount Rs. - |  |  | 1961710 |  |  |  | Total Paid Amount Rs. - |  | 2089000
[16 empty] | Balance Payable Amount Rs. - |  | -127290
Updated on 29-01-2023
[8 empty] | Hold | 20869
[8 empty] | Advance/Surplus | -127290