## Sheet1
Subcontractor: | A J Contractor
State: | Uttar Pradesh |  | A J Contractor |  |  |  |  | OHT work
District: | Shamli
Block: | Shamli | [14 empty] | 2024-07-22
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold the Amount because the Qty. is more then the DPR | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | Total_Amount | UTR | Advance Village Wise
[7 empty] | 18% |  | 1% | 5% | 10% | 10% | 18% | [5 empty] | 1%
66071
66071 | BHAMERI SAHPUR VILLAGE PIPE LINE ROAD RESTORATION WORK At- BHAMERI SAHPUR VILLAGE | 2024-10-25 | 11 | 545163 | 209825 | 335338 | 60361 | 395699 | 3353.38 | 16766.9 | 33533.8 | 33533.8 | 60361 |  | 248150 |  | RIUP22/164 | 150000 | 1500 | 99000 | 01-10-2024 IFT/IFT24275137126/RIUP24/2013/A J CONTRACTOR 99000.00 | 10861
66071 | GST RELEASE NOTE |  | 11 | 60361 | [10 empty] | 60361 |  | RIUP22/252 | 150000 | 1500 | 99000 | 30-10-2024 IFT/IFT24304255891/RIUP24/2373/A J CONTRACTOR 99000.00
66071 | [16 empty] | RIUP22/2623 | 150000 | 1500 | 50150 | 23-12-2024 IFT/IFT24358031288/RIUP24/2663/A J CONTRACTOR 50150.00
66071 | [18 empty] | 0 | 49500 | 23-12-2024 IFT/IFT24358031291/RIUP24/2791/A J CONTRACTOR 49500.00
66071 | [18 empty] | 0 | 0
66071
66749
66749 | Rangana Village - Unn - Pipeline work | 2025-03-11 | 18 | 266204 | 0 | 266204 | 47917 | 314121 | 2662.04 | 13310.2 | 26620.4 | 26620.4 | 47917 | 7143 | 189848 |  |  |  |  | 49500 | 14-02-2025 IFT/IFT25045032850/RIUP24/3176/A J CONTRACTOR 49500.00 | 65348
66749 | GST RELEASE NOTE |  | 18 | [11 empty] | 0 |  |  |  |  | 75000 | 09-04-2025 IFT/IFT25099033922/RIUP25/0060/A J CONTRACTOR 75000.00
66749
66749
[10 empty] | 30077.1 | 60154.2 | 60154.2 | 108278 | 7143 | 498359 |  | Total Paid Amount Rs. - |  |  | 422150 | Total Paid | 76209
Balance Payable Amount Rs. -
[20 empty] | 76209 | Balance Payable
A J Contractor
Updated On 16-04-2025
[9 empty] | Total Hold ( SD+OC+HT ) |  | 150385.5
[9 empty] | Advance / Surplus |  | 76209
[9 empty] | DPR excess Hold |  | 7143
Tax Invoice No.
[9 empty] | T.I | 29 | 401850
[9 empty] | T.I | 30 | 782550
[9 empty] | T.I | 31 | 481162
[9 empty] | T.I | 32 | 493500
[9 empty] | T.I | 34 | 296100
[9 empty] | T.I | 35 | 245340
[9 empty] | Total Amount after Deduction |  | 2700502
[9 empty] | GST remainng |  | 47917