## Sheet1
Subcontractor: | A K Contractor
State: | Uttar Pradesh |  | A K Contractor |  |  |  | Pipe Laying work
District: | Shamli
Block: | Shamli | [14 empty] | 2024-07-22
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | Hydro_Testing | On_Commission | GST_SD_Amount | DPR Exceed Qty. / Advance | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | Total_Amount | UTR
[9 empty] | 1% | 5% | 10% | 10% | [6 empty] | 1%
52392
52392 | Mahavatpur Village Pipeline laying work | 2002-11-02 | 51 | 997047 | 58545.5 | 938502 | 168930 | 1107432 | 9385 | 46925 | 46925 | 93850 | 168930 | 91439 | 649978 |  | RIUP22/748 | 200000 | 2000 | 198000 | 15-09-2022 IFT/IFT22258012415/RIUP22/748/A K CONTRACTOR 198000.00 | 695.4852
52392 | GST Release Note | 2022-12-27 | 51 | 168930 | 0 | 168930 | 0 | 168930 | 0 | 0 |  |  | 0 |  | 168930 |  | RIUP22/896 | 150000 | 1500 | 148500 | 04-10-2022 IFT/IFT22277043033/RIUP22/896/A K CONTRACTOR 148500.00
52392 | Mahavatpur Village Pipeline laying work | 2023-08-09 | 6 | 357161.48 | 141155 | 216006.48 | 38881 | 254887.48 | 2160.0648 | 10800 | 21601 | 0 | 38881 |  | 181445.4152 |  | RIUP22/1222 | 300000 | 3000 | 297000 | 09-11-2022 IFT/IFT22313033971/RIUP22/1222/A K CONTRACTOR 297000.00
52392 | Mahavatpur Village Pipeline laying work | 2023-09-07 | 7 | 654093 | 76300 | 577793 | 104003 | 681796 | 5777.93 | 28890 | 0 | 0 | 104003 |  | 543125.07 |  | RIUP22/1267 | 6478 | 0 | 6478 | 22-11-2022 IFT/IFT22326006141/RIUP22/1267/A K CONTRACTOR 6478.00
52392 | GST Release Note | 2022-12-27 | 6 & 7 | 142884 | 0 | 142884 | 0 | 142884 | 0 | 0 |  |  | 0 |  | 142884 |  | RIUP22/1689 | 168930 | 0 | 168930 | 07-01-2023 IFT/IFT23007057532/RIUP22/1689/A K CONTRACTOR 168930.00
52392 |  |  |  | 692 | [10 empty] | 692 |  | RIUP22/2127 | 50000 | 500 | 49500 | 07-02-2023 IFT/IFT23038098507/RIUP22/2127/A K CONTRACTOR ₹ 49,500.00
52392 | [16 empty] | RIUP23/1798/ | 131945 | 0 | 131945 | 31-08-2023 IFT/IFT23243083240/RIUP23/1798/A K CONTRACTOR 131945.00
52392 | [16 empty] | RIUP23/1798/ | 543123 | 0 | 543123 | 18-09-2023 IFT/IFT23261024600/RIUP23/2047/A K CONTRACTOR 543123.00
52392 | [16 empty] | RIUP23/3999/ | 14288300% |  | 142883 | 04-01-2024 IFT/IFT24004052743/RIUP23/3999/A K CONTRACTOR 142883.00
52392
52690
52690 | Kherki Village - Pipe Layiing work | 2023-04-07 | 3 | 343645 | 126098 | 217547 | 39158.46 | 256705.46 | 2175.47 | 10877.35 | 21755 | 21755 | 39158.46 | 0 | 160984.18 |  | SPUP23/0157 | 150000 | 1500 | 148500 | 17-04-2023 IFT/IFT23107022170/SPUP23/0157/A K CONTRACTOR 148500.00 | 19745.32
52690 | Kherki Village - Pipe Layiing work | 2023-08-09 | 5 | 230487 | 126098 | 104389 | 18790.02 | 123179.02 | 1043.89 | 5219.45 | 10439 | 10439 | 18790.02 | 0 | 77247.66 |  | RIUP23/1547 | 50000 | 500 | 49500 | 17-08-2023 IFT/IFT23229007323/RIUP23/1547/A K CONTRACTOR 49500.00
52690 | GST Release Note | 2023-04-07 | 3 | 39158.46 | [10 empty] | 39158.46 |  | RIUP23/2250 | 39158 | 0 | 39158 | 17-10-2023 IFT/IFT23290024866/RIUP23/2250/A K CONTRACTOR 39158.00
52690 | GST Release Note |  | 5 | 18790.02 | [10 empty] | 18790.02 | Wrong filed | RIUP23/1549 | 39277 | 0 | 39277 | 17-10-2023 IFT/IFT23290024867/RIUP23/2251/A K CONTRACTOR 39277.00
52690
53624
53624 | GAGOUR VILLAGE - Pipe line work | 2022-11-30 | 56 | 482318 | 18014 | 464304 | 83574.72 | 547878.72 | 4643.04 | 23215.2 | 23215.2 | 46430.4 | 83574.72 | 46702 | 320098.16 |  | RIUP22/2364 | 320099 |  | 320099 | 14-12-2022 IFT/IFT22348027066/RIUP22/1500/A K CONTRACTOR 320099.00 | -1.12
53624 | GST Release Note |  | 56 | 83574.72 | [10 empty] | 83574.72 |  | RIUP22/2640 | 83575 |  | 83575 | 31-12-2022 IFT/IFT22365031247/RIUP22/1686/A K CONTRACTOR 83575.00
53624
51409
51409 | Dhanena Village - Pipeline work | 2023-10-16 | 64 | 1351255 | 58545 | 1292710 | 232687.8 | 1525397.8 | 12927.1 | 64635.5 | 64635.5 | 129271 | 232687.8 | 186675 | 834565.9 |  | RIUP23/2219 | 79200 |  | 79200 | 24-06-2022 IFT/IFT22175035627/RIUP22254/AK CONTRACTOR 79200.00 | -173499.3
51409 | GST Release Note |  | 64 | 232687.8 | [10 empty] | 232687.8 |  | RIUP23/2903 | 49500 |  | 49500 | 16-07-2022 IFT/IFT22197007096/RIUP22/342/A K CONTRACTOR 49500.00
51409 | [16 empty] | RIUP23/3269 | 396000 |  | 396000 | 20-08-2022 IFT/IFT22232005690/RIUP22/551/A K CONTRACTOR 396000.00
51409 | [14 empty] | 0 |  | RIUP23/3270 | 297000 |  | 297000 | 09-11-2022 IFT/IFT22313033969/RIUP22/1220/A K CONTRACTOR 297000.00
51409 | [16 empty] | RIUP23/3271 | 12865 |  | 12865 | 14-11-2022 IFT/IFT22318014477/RIUP22/1228/A K CONTRACTOR 12865.00
51409 | [16 empty] | RIUP23/3272 | 100000 |  | 100000 | 12-12-2022 IFT/IFT22346021444/RIUP22/1485/A K CONTRACTOR 100000.00
51409 | [16 empty] | RIUP22/1685/ | 232688 |  | 232688 | 18-01-2023 IFT/IFT23018003252/RIUP22/1685/A K CONTRACTOR 232688.00
51409 | [16 empty] | RIUP24/0522/ | 73500 |  | 73500 | 16-05-2024 IFT/IFT24137038653/RIUP24/0522/A K CONTRACTOR 73500.00
51409
51408
51408 | Jalalpur village - Pipeline work | 2022-11-02 | 53 | 1393332 | 18014 | 1375318 | 247557.24 | 1622875.24 | 13753.18 | 68765.9 | 68765.9 | 137531.8 | 247557.24 | 276130 | 810371.22 |  |  |  |  | 247500 | 24-06-2022 IFT/IFT22175031940/RIUP22/253/A K CONTRACTOR 247500.00 | -179628.54
51408 | GST Release Note |  | 53 | 247557.24 | [10 empty] | 247557.24 |  |  |  |  | 247500 | 18-07-2022 IFT/IFT22199033890/RIUP22/341/A K CONTRACTOR 247500.00
51408 | Hold release amount |  |  | 18000 | [10 empty] | 18000 |  |  |  |  | 99000 | 20-08-2022 IFT/IFT22232005691/RIUP22/550/A K CONTRACTOR 99000.00
51408 | [14 empty] | 0 |  |  |  |  | 297000 | 22-08-2022 IFT/IFT22234028106/RIUP22/585/A K CONTRACTOR 297000.00
51408 | [19 empty] | 99000 | 09-12-2022 IFT/IFT22343052683/RIUP22/1473/A K CONTRACTOR 99000.00
51408 | [19 empty] | 247557 | 18-01-2023 IFT/IFT23018003253/RIUP22/1687/A K CONTRACTOR 247557.00
51408 | [19 empty] | 18000 | 2-5-24 and 3-5-24 - Being Paid in cash
51408
55238
55238 | NAI LAGLA NAWEEN VILLAGE - Pipe line work | 2024-04-07 | 2 | 741552 | 94574 | 646978 | 116456.04 | 763434.04 | 6469.78 | 32348.9 | 64697.8 | 64697.8 | 116456.04 | 77299 | 401464.72 |  |  |  |  | 198000 | 28-02-2023 IFT/IFT23059053148/RIUP22/2364/A K CONTRACTOR 198000.00 | 1.52
55238 | GST |  | 2 | 116456.04 | [10 empty] | 116456.04 |  |  |  |  | 198000 | 17-03-2023 IFT/IFT23076014163/RIUP22/2640/A K CONTRACTOR 198000.00
55238 | NAI LAGLA NAWEEN VILLAGE - Pipe line work | 2023-11-09 | 10 | 182338 | 13510 | 168828 | 30389.04 | 199217.04 | 1688.28 | 8441.4 | 16882.8 | 16882.8 | 30389.04 | 8648 | 116284.72 |  |  |  |  | 49500 | 21-04-2023 IFT/IFT23111024136/SPUP23/0221/A K CONTRACTOR 49500.00
55238 | GST |  | 10 | 30389.04 | [10 empty] | 30389.04 |  |  |  |  | 72419 | 17-10-2023 IFT/IFT23290024865/RIUP23/2249/A K CONTRACTOR 72419.00
55238 | [19 empty] | 116285 | 29-11-2023 IFT/IFT23333055011/RIUP23/3433/A K CONTRACTOR 116285.00
55238 | [19 empty] | 30389 | 04-01-2024 IFT/IFT24004052744/RIUP23/4000/A K CONTRACTOR 30389.00
55238
52691
52691 | HARSANA VILLAGE Pipe line work | 2022-11-02 | 52 | 684822 | 40532 | 644290 | 115972.2 | 760262.2 | 6442.9 | 32214.5 | 32214.5 | 64429 | 115972.2 | 45289 | 463700.1 |  |  |  |  | 99000 | 04-10-2022 IFT/IFT22277043032/RIUP22/895/A K CONTRACTOR 99000.00 | -178577.78
52691 | GST |  | 52 | 115972.2 | [10 empty] | 115972.2 |  |  |  |  | 297000 | 09-11-2022 IFT/IFT22313033970/RIUP22/1221/A K CONTRACTOR 297000.00
52691 | Khanpur Village -Pipeline work | 2023-01-31 | 57 | 826554 | 36028 | 790526 | 142294.68 | 932820.68 | 7905.26 | 39526.3 | 79052.6 | 79052.6 | 142294.68 | 244748 | 340241.24 |  |  |  |  | 67700 | 24-11-2022 IFT/IFT22328011600/RIUP22/1340/A K CONTRACTOR 67700.00
52691 | GST |  | 57 | 142294.68 | [10 empty] | 142294.68 |  |  |  |  | 115972 | 09-01-2023 IFT/IFT23009017846/RIUP22/1688/A K CONTRACTOR 115972.00
52691 | Debit amt release note |  |  | 6000 | [10 empty] | 6000 |  |  |  |  | 340241 | 07-02-2023 IFT/IFT23038091087/RIUP22/2109/A K CONTRACTOR ₹ 3,40,241.00
52691 | Multi to Single layer bill |  |  | 19422 | [10 empty] | 19422 |  |  |  |  | 148500 | 23-02-2023 IFT/IFT23054035718/RIUP22/2281/A K CONTRACTOR 148500.00
52691 | [19 empty] | 142295 | 08-03-2023 IFT/IFT23067013960/RIUP22/2494/A K CONTRACTOR 142295.00
52691 | [19 empty] | 49500 | 18-04-2023 18-04-2023 IFT/IFT23108025262/SPUP23/0181/A K CONTRACTOR 49500.00
52691 | [19 empty] | 6000 | Paid in cash - 30.4.24
52691
52691
52691
[10 empty] | 371859.55 | 450184.4 | 664339.5 | 1338694.2 | 976930 | 6282314.5852 |  |  |  |  | 6793579 |  | -511264.4148
-511264.4148
A K Contractor
Updated On 19-08-2024 ( Vikash )
[11 empty] | Total Hold ( SD+OC+HT ) |  | 1486383.45 |  | 2463313.45
[11 empty] | Advance / Surplus |  | -511264.4148
[11 empty] | DPR Excess |  | 976930
[11 empty] | GST Remaining |  | -4.0018e-11