## Sheet1
Subcontractor: | AK Contractor
State: | Uttar Pradesh
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold the Amount because the Qty. is more then the DPR | Final_Amount | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% | 10% | 10% | 18%
51903 | Pipalhera Village Pipe laying Work | 2022-11-30 | 55 | 1141888 | 44955 | 1096933 | 197448 | 1294381 | 10969.33 | 54846.65 | 109693.3 | 109693.3 | 197448 | 85681 | 726049 | 297000 | 26-09-2022 IFT/IFT22269006616/RIUP22/815/A K CONTRACTOR 297000.00
51903 | Pipalhera Village Pipe laying Work | 2023-04-12 | 5 | 474668 | 0 | 474668 | 85440 | 560108 | 4746.68 | 23733.4 | 47466.8 | 47466.8 | 85440 | 26556 | 324698 | 429050 | 14-12-2022 IFT/IFT22348027065/RIUP22/1499/A K CONTRACTOR 429050.00
51903 | GST Release Note | 2022-12-30 | 55 | 197447 | [10 empty] | 197447 | 197448 | 07-01-2023 IFT/IFT23007057533/RIUP22/1737/A K CONTRACTOR 197448.00
51903 | Pipalhera Village Pipe laying Work | 2023-11-09 | 8 | 204520 | 0 | 204520 | 36814 | 241334 | 2045.2 | 10226 | 20452 | 20452 | 36814 | 5855 | 145490 | 324698 | 21-04-2023 IFT/IFT23111024132/SPUP23/0225/A K CONTRACTOR 324698.00
51903 | Pipalhera Village Pipe laying Work | 2023-04-12 | 9 | 852621 | 188000 | 664621 | 119632 | 784253 | 6646.21 | 33231.05 | 66462.1 | 66462.1 | 119632 | 111000 | 380820 | 198000 | 23-11-2023 IFT/IFT23327021225/RIUP23/3393/A K CONTRACTOR ₹ 1,98,000.00
51903 | [15 empty] | 145490 | 22-12-2023 IFT/IFT23356043569/RIUP23/3476/A K CONTRACTOR 145490.00
51903 | [15 empty] | 182820 | 22-12-2023 IFT/IFT23356043571/RIUP23/3477/A K CONTRACTOR 182820.00