## Sheet1
Subcontractor: | JSS CONTRACTOR
State: | Uttar Pradesh
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | Painting and finishing or TD | GST_SD_Amount | Hold Amount | Final_Amount |  | PAYMENT NOTE No. | Amount | TDS Amount @ 1% on BASIC AMOUNT | Total_Amount | UTR | Advance Village Wise
[7 empty] | 18% |  | 1% | 5% |  |  | 10% | 18% | [5 empty] | 1%
52834
52834 | Sanpla village Pump house work | 2022-12-16 | 1 | 381000 | 56461 | 324539 | 58417 | 382956 | 3245 | 16226.95 |  |  |  | 58417 |  | 305067 |  |  |  |  | 148500 | 20-10-2022 NEFT/AXISP00330252339/RIUP22/1056/J S S CONTRACTO 148500.00 | 0 | 1500
52834 | Gst release note |  | 1 | 58417 | [11 empty] | 58417 |  |  |  |  | 156567 | 29-12-2022 NEFT/AXISP00349704441/RIUP22/1677/J S S CONTRACTO 1,56,567.00
52834 | [20 empty] | 58417 | 31-01-2023 NEFT/AXISP00358425191/RIUP22/2009/J S S CONTRACTO 58417.00
54807
54807 | SIKANDARPUR village PH Construction work | 2023-01-31 | 2 | 342900 | 30520 | 312380 | 56228.4 | 368608.4 | 3123.8 | 15619 |  |  |  | 56228.4 |  | 293637.2 |  |  |  |  | 293637 | 04-02-2023 NEFT/AXISP00360451538/RIUP22/2096/J S S CONTRACTO ₹ 2,93,637.00 | 0.2
54807 | Gst release note |  | 2 | 56228 | [11 empty] | 56228 |  |  |  |  | 56228 | 27-02-2023 NEFT/AXISP00365798945/RIUP22/2314/J S S CONTRACTO 56228.00
54807
56799
56799 | Sanpla village BW work | 2023-04-12 | 1 | 327880 | 45780 | 282100 | 50778 | 332878 | 2821 | 14105 |  |  | 14105 | 50778 |  | 251069 |  |  |  |  | 251069 | 25-04-2023 25-04-2023 NEFT/AXISP00384260579/SPUP23/0265/J S S CONTRACTOR 251069.00 | 0
56799 | Gst release note |  | 1 | 50778 | [11 empty] | 50778 |  |  |  |  | 50778 | 07-06-2023 NEFT/AXISP00396261241/RIUP23/531/J S S CONTRACTOR 50778.00
56799 | Sanpla village BW work | 2023-09-08 | 5 | 117635 |  | 117635 | 21174 | 138809 | 1176 | 5881.75 |  |  |  | 21174 | 49700 | 60877 |  |  |  |  | 60877 | 14-09-2023 NEFT/AXISP00424905750/RIUP23/2009/J S S CONTRACTOR/PUNB0182200 60877.00
56799 | Gst release note |  | 5 | 21174 | [11 empty] | 21174 |  |  |  |  | 21174 | 18-11-2023 NEFT/AXISP00445057550/RIUP23/3325/J S S CONTRACTOR/PUNB0182200 21174.00
56799
57389
57389 | Comman village DG Foundation work | 2023-05-16 | 2 | 240000 |  | 240000 | 43200 | 283200 | 2400 | 12000 |  |  |  | 43200 |  | 225600 |  |  |  |  | 225600 | 24-05-2023 NEFT/AXISP00392230439/RIUP23/301/J S S CONTRACTOR 225600.00 | 0
57389 | Gst release note |  | 2 | 43200 | [11 empty] | 43200 |  |  |  |  | 43200 | 27-06-2023 NEFT/AXISP00401014825/RIUP23/805/J S S CONTRACTOR 43200.00
57389 | Comman village DG Foundation work | 2023-07-18 | 4 | 120000 |  | 120000 | 21600 | 141600 | 1200 | 6000 |  |  |  | 21600 |  | 112800 |  |  |  |  | 112800 | 21-07-2023 NEFT/AXISP00404521452/RIUP23/1173/J S S CONTRACTOR 112800.00
57389 | Gst release note |  | 4 | 21600 | [11 empty] | 21600 |  |  |  |  | 21600 | 18-08-2023 NEFT/AXISP00416613500/RIUP23/1582/J S S CONTRACTO 21600.00
57925
57925 | Palekha village OHT 200KL 16M work | 2023-10-27 | 7 | 456000 | 229473 | 226527 | 40774.86 | 267301.86 | 2265.27 | 11326.35 |  |  |  | 40774.86 |  | 212935.38 |  | RIUP23/3005 | 212936 |  | 212936 | 02-11-2023 NEFT/AXISP00439632304/RIUP23/3005/J S S CONTRACTOR/PUNB0182200 212936.00 | -131161.76
57925 | Palekha village OHT 200KL 16M work | 2023-12-29 | 8 | 304000 | 293520 | 10480 | 1886.4 | 12366.4 | 104.8 | 524 |  |  | 1048 | 1886.4 |  | 8803.2 |  | RIUP23/4042 | 200000 | 2000 | 198000 | 30-12-2023 NEFT/AXISP00457527699/RIUP23/4042/J S S CONTRACTOR/PUNB0182200 198000.00
57925 | Palekha village OHT 200KL 16M work | 2024-02-10 | 10 | 456000 | 450761 | 5239 | 943.02 | 6182.02 | 52.39 | 261.95 |  |  |  | 943.02 |  | 4924.66 |  |  |  |  | 99000 | 14-06-2024 NEFT/AXISP00509460932/RIUP24/0862/J S S CONTRACTOR/PUNB0182200 99000.00
57925 | Gst release note |  | 7, 8 & 10 | 43604.28 | [11 empty] | 43604.28
57925 | Palekha village OHT 200KL 16M work | 2024-02-10 | 10 | 152000 | 55119 | 96881 | 17438.58 | 114319.58 | 968.81 | 4844.05 |  |  |  | 17438.58 |  | 91068.14
57925 | Gst release note |  | 10 | 17438.58 | [11 empty] | 17438.58
57926
57926 | SANPLA Village OHT 100KL 14MTR work | [21 empty] | 0
57926
57929
57929 | DABHRI BUZURG Village OHT 175KL 16MTR work | [21 empty] | 0
57929
57930
57930 | Amberidhan village OHT work | [21 empty] | 0
57930
57931
57931 | KHERKI Village OHT 125KL 12MTR work | 2023-12-29 | 9 | 112500 | 110851 | 1649 | 296.82 | 1945.82 | 16.49 | 82.45 |  |  |  | 296.82 |  | 1550.06 |  | RIUP23/4204 | 100000 | 1000 | 99000 | 09-01-2024 NEFT/AXISP00461001718/RIUP23/4204/J S S CONTRACTOR/PUNB0182200 99000.00 | -238443.04
57931 | KHERKI Village OHT 125KL 12MTR work | 2024-02-28 | 12 | 225000 | 174366 | 50634 | 9114.12 | 59748.12 | 506.34 | 2531.7 |  |  |  | 9114.12 |  | 47595.96 |  |  |  |  | 198000 | 17-05-2024 NEFT/AXISP00500883092/RIUP24/0546/J S S CONTRACTOR/PUNB0182200 198000.00
57931 | Gst release note |  | 9 & 12 | 9410.94 | [11 empty] | 9410.94
59927
59927 | Peerkhera village PH work
59927
59928
59928 | Peerkhera village PH work
59928
58366
58366 | Khanpur Jatan Village pump house work | 2023-07-11 | 3 | 381000 | 40902 | 340098 | 61218 | 401316 | 3401 | 17004.9 |  |  | 34009.8 | 61218 |  | 285682 |  | RIUP23/1108 | 285682 | 0 | 285682 | 17-07-2023 NEFT/AXISP00407488695/RIUP23/1108/J S S CONTRACTO 285682.00 | 0
58366 | GST Release note |  | 3 | 61218 | [11 empty] | 61218 |  | RIUP23/2009 | 61218 | 0 | 61218 | 18-08-2023 NEFT/AXISP00416613499/RIUP23/1581/J S S CONTRACTO 61218.00
61819
61819 | Jalalpur Village Compus Development, Repairing & Finishing Work | 2024-12-09 | 6 | 36000 | 0 | 36000 | 6480 | 42480 | 360 | 1800 |  |  |  | 6480 |  | 33840 |  | RIUP23/4373 | 100000 | 1000 | 99000 | 18-01-2024 NEFT/AXISP00463439416/RIUP23/4373/J S S CONTRACTOR/PUNB0182200 99000.00 | 14232
61819 | Jalalpur Village Compus Development, Repairing & Finishing Work | 2024-12-09 | 8 | 65100 | 0 | 65100 | 11718 | 76818 | 651 | 3255 |  |  |  | 11718 |  | 61194
61819 | Gst release note |  | 6 & 8 | 18198 | [11 empty] | 18198
[17 empty] | 62277 | RIUP24/0571 | 100000 | 1000
62277 | KARORI MEHRAMPUR Village OHT 175KL 12MTR work | 2024-02-14 | 11 | 389812 | 256524 | 133288 | 23991.84 | 157279.84 | 1332.88 | 6664.4 |  |  |  | 23991.84 |  | 125290.72 |  | RIUP23/4922 |  |  | 198000 | 29-02-2024 NEFT/AXISP00475421889/RIUP23/4922/J S S CONTRACTOR/PUNB0182200 ₹ 1,98,000.00 | -27700.6
62277 | Gst release note |  | 11 | 23991.84 | [11 empty] | 23991.84 |  |  |  |  | 99000 | 21-05-2024 NEFT/AXISP00501438646/RIUP24/0571/J S S CONTRACTOR/PUNB0182200 99000.00
62277 | KARORI MEHRAMPUR Village OHT 175KL 12MTR work | 2024-10-10 | 2 | 519750 | 417519.75 | 102230.25 | 18401.445 | 120631.695 | 1022.3025 | 5111.5125 |  |  |  | 18401.445 |  | 96096.435 |  |  |  |  | 99000 | 14-06-2024 NEFT/AXISP00509460931/RIUP24/0861/J S S CONTRACTOR/PUNB0182200 99000.00
62277 | KARORI MEHRAMPUR Village OHT 175KL 12MTR work | 2024-11-28 | 5 | 129937.5 | 36617 | 93320.5 | 16797.69 | 110118.19 | 933.205 | 4666.025 |  |  |  | 16797.69 |  | 87721.27
62277 | Gst release note |  | 2 | 18401.445 | [11 empty] | 18401.445
62277 | Gst release note |  | 5 | 16797.69 | [11 empty] | 16797.69
63604
63604 | Jandheri village OHT - 122, 12 work | 2024-05-01 | 1 | 450000 | 103039 | 346961 | 62452.98 | 409413.98 | 3469.61 | 17348.05 |  |  |  | 62452.98 |  | 326143.34 |  |  |  |  | 100000 | 13-03-2025 NEFT/AXISP00633039291/RIUP24/3426/J S S CONTRACTOR/PUNB0182200 100000.00 | 188595.34
63604 | Gst release note | 2024-07-01 | 1 | 62452 | [11 empty] | 62452 |  |  |  |  | 100000 | 30-04-2025 NEFT/AXISP00658414401/RIUP25/0187/J S S CONTRACTOR/PUNB0182200 100000.00
63604
66132
66132 | KARORI MEHRAMPUR village RR work | 2024-11-19 | 3 | 142525 | 0 | 142525 | 25654.5 | 168179.5 | 1425.25 | 7126.25 |  |  |  | 25654.5 |  | 133973.5 |  |  |  |  | 148500 | 03-10-2024 NEFT/AXISP00548224893/RIUP24/2085/J S S CONTRACTOR/PUNB0182200 148500.00 | -3015.2
66132 | KARORI MEHRAMPUR village RR work | 2024-11-19 | 4 | 237600 | 91560 | 146040 | 26287.2 | 172327.2 | 1460.4 | 7302 | 14604 | 14604 |  | 26287.2 |  | 108069.6 |  |  |  |  | 148500 | 30-10-2024 NEFT/AXISP00561828554/RIUPP24/2380/J S S CONTRACTOR/PUNB0182200 148500.00
66132 | Gst release note |  | 3 & 4 | 51941.7 | [11 empty] | 51941.7
66132
67069
67069 | Jalalpur village Pump House & Boundary Wall Repair & Maints. Finishing Work | 2024-12-09 | 7 | 96000 | 0 | 96000 | 17280 | 113280 | 960 | 4800 |  |  |  | 17280 |  | 90240 | Bill Not processed. | [5 empty] | 107520
67069 | Gst release note |  | 7 | 17280 | [11 empty] | 17280
67069
67123
67123 | Jalalpur village Pump Lowering work | 2024-12-19 | 9 | 20000 | 0 | 20000 | 3600 | 23600 | 200 | 1000 |  |  |  | 3600 |  | 18800 | [6 empty] | 22400
67123 | Gst release note |  | 9 | 3600 | [11 empty] | 3600
67123
[9 empty] | 33095.5475 | 165481.3375 | 14604 | 14604 | 49162.8 | 595732.855 | 49700 | 3578709.94 |  | Total Paid Amount Rs. - |  |  | 3646283 |  | -67573.06
[18 empty] | Balance Payable Amount Rs. - |  |  | -67573.06
JSS Contractor
2025-04-22
[8 empty] | Total Hold |  | 243852.1375
[8 empty] | Advance / Surplus |  | -67573.06
[8 empty] | Extra Hold |  | 49700
[8 empty] | GST Remaining |  | Nil