## Sheet1
Subcontractor: | Nitin Contractor
State: | Uttar Pradesh
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | Hold for painting and finishing | GST_SD_Amount | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% | 10% | 10% | 5% | 18% |  |  |  |  | 1%
60569
60569 | PEER KHERA VILLAGE pump house Work | 2023-12-28 | 1 | 222000 | 36242 | 185758 | 33436.44 | 219194.44 | 1857.58 | 9287.9 |  |  |  | 33436.44 | 174612.52 |  | RIUP23/4199 | 174612 | 0 | 174612 | 12-01-2024 NEFT/AXISP00462196367/RIUP23/4199/NITIN/PUNB0041710 174612.00
60569 | PEER KHERA VILLAGE pump house Work | 2024-02-13 | 2 | 101850 | 15260 | 86590 | 15586.2 | 102176.2 | 865.9 | 4329.5 |  |  |  | 15586.2 | 81394.6 |  |  |  |  | 81394 | 17-05-2024 NEFT/AXISP00500883063/RIUP23/4797/NITIN/PUNB0041710 81394.00
60569
60568
60568 | PEER KHERA VILLAGE Boundary Wall Work
60568
60568
60568
49022.64
[10 empty] | 13617.4 | 0 | 0 | 0 | Total Payable Amount Rs. - | 256007.12 |  | Total Paid Amount Rs. - |  |  | 256006
[17 empty] | Balance Payable Amount Rs. - |  |  | 1.12
Nitin Contractor
Updated On 10-08-2024 ( By Nakshatra )
[9 empty] | Total Hold |  | 13617.4
[9 empty] | Total Debit |  | 15260
[9 empty] | Advance/ Surplus |  | 1.12
[9 empty] | GST Remaining |  | 49022.64