## Sheet1
Subcontractor: | Shubham Kumar
State: | Uttar Pradesh
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing |  | PAYMENT NOTE No. | Amount | TDS Amount @ 1% on BASIC AMOUNT | Total_Amount | UTR | Advance Village Wise
[7 empty] | 1% | 5% | 10% | 10% | [5 empty] | 1%
66765
66765 | DAKHORI JAMALPUR village BALANCE PIPE LINE Work | 2024-11-22 | 1 | 117423 | 22517 | 94906 | 949.06 | 4745 | 9491 | 9491 | 0 | 70230 |  | RIUP22/1935 | 218267 | 0
[14 empty] | RIUP22/2220 | 199183 | 0
[14 empty] | RIUP23/2640 | 198000
[7 empty] | 949.06 | 4745 | 9491 | 9491 | 0 | 70230 |  |  |  |  | 0 | Total Paid
[17 empty] | 70230 | Balance Payable
Shubham Kumar
2024-12-07
[8 empty] | Total Hold |  | 23727
[8 empty] | DPR Excess Hold |  | 0
[8 empty] | Advance / Surplus |  | 70230
[8 empty] | Debit |  | 0
[8 empty] | GST Remaining |  | Nil
Qty as per updated Dawing
|  |  | Dia | Length | CUM |  | DPR | CUM | EXCESS | RATE
|  |  | 63 | 5175 | 4794.2 | As per updated drawing | 588 | 625.9 | 37.9 | 95
|  |  | 75 | 694 | 678.9 |  | 0 | 674 | 674 | 8
|  |  | 90 | 588 | 625.9 |  | 37.13 | 301.7 | 264.57 | 50
|  |  | 110 | 434 | 421.6 |  |  |  |  | hold amt
|  |  | 160 | 774 | 768 |  |  |  |  | prev hold
|  |  | 200 | 273 | 189.5 |  |  |  |  | to be hold
|  |  | Total | 7938