## Sheet1
Subcontractor: | V P Enterprises
State: | Uttar Pradesh |  | V P Enterprises |  |  |  |  | Pipe Laying work
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold the Amount because the Qty. is more then the DPR | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | SD (5%) | Advance paid | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% | 10% | 10% | 18% |  |  | 53176 |  |  | 1% | 5%
53176 | Aldi Village Pipe laying work | 2022-12-14 | 1 | 608891 | 0 | 608891 | 109600 | 718491 | 6088.91 | 30444.55 | 60889.1 | 60889.1 | 109600 | 78443 | 372136 |  | RIUP22/1592 | 250000 | 2500 | 0 | 0 | 247500 | 21-12-2022 IFT/IFT22355021697/RIUP22/1592/V P ENTERPRISES 247500.00
53176 | Aldi Village Pipe laying work | 2023-01-20 | 2 | 558364 |  | 558364 | 100506 | 658870 | 5583.64 | 27918.2 | 55836.4 | 55836.4 | 100506 | 40297 | 372892 |  | RIUP22/1719 | 124636 | 0 | 0 | 0 | 124636 | 07-01-2023 IFT/IFT23007057537/RIUP22/1719/V P ENTERPRISES 124636.00
53176 | GST release note |  | 1 | 109600 |  | 109600 | 0 | 109600 | 0 | [5 empty] | 109600 |  | RIUP22/1592 | 50000 | 500 | 0 | 0 | 49500 | 23-01-2023 IFT/IFT23023012476/RIUP22/1944/V P ENTERPRISES ₹ 49,500.00
53176 | GST release note | 2023-02-27 | 2 | 100506 |  | 100506 | 0 | 100506 | 0 | 0 |  |  | 0 |  | 100506 |  | RIUP22/2015 | 323393 |  |  |  | 323393 | 31-01-2023 IFT/IFT23031059986/RIUP22/2015/V P ENTERPRISES 323393.00
53176 | [16 empty] | RIUP22/2217 | 109600 |  |  |  | 109600 | 20-02-2023 IFT/IFT23051015381/RIUP22/2217/V P ENTERPRISES 109600.00
53176 | [16 empty] | RIUP22/2384 | 100506 |  |  |  | 100506 | 01-03-2023 IFT/IFT23060041287/RIUP22/2384/V P ENTERPRISES 100506.00
[10 empty] | 58362.75 | 116725.5 | 116725.5 | 210106 | 118740 | 955134
[14 empty] | Total Payable Amount Rs. - |  |  |  |  | Total Paid Amount Rs. - |  |  | 955135
[19 empty] | Balance Payable Amount Rs. - |  |  | -1
Updated On 23-02-2024
[10 empty] | Hold Amount |  | 291813.75
[10 empty] | Advance / Surplus |  | 0
[10 empty] | Debit |  | 0
[10 empty] | DPR Excess Hold Amount |  | 118740