## Sheet1
Subcontractor: | Welcome Construction & Company
State: | Uttar Pradesh | [5 empty] | Pipeline Laying work
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | Painting Hold | On_Commission | Hydro_Testing | Hold Amount For Quantity excess against DPR | GST_SD_Amount | Final_Amount |  | Total_Amount | UTR
[9 empty] | 1% | 5% | 5% | 10% | 10%
62539
62539 | AHATAGOSHGARH VILLAGE PIPE LINE ROAD RESTORATION WORK | 2024-03-31 | 127 | 644080 | 0 | 644080 | 115934.4 | 760014.4 | 6440.8 | 32204 |  | 64408 | 64408 | 0 | 115934.4 | 476619 |  | 300000 | 08-05-2024 NEFT/AXISP00498179038/RIUP24/0376/WELCOME CONSTRUCTI/UBIN0563498 300000.00
62539 | GST release note |  | 127 | 115934.4 | [11 empty] | 115934.4 |  | 125000 | 28-05-2024 NEFT/AXISP00503313837/RIUP24/0632/WELCOME CONSTRUCTI/UBIN0563498 125000.00
62539 | AHATAGOSHGARH VILLAGE PIPE LINE ROAD RESTORATION WORK | 2024-05-24 | 170 | 365455 | 0 | 365455 | 65781.9 | 431236.9 | 3654.55 | 18272.75 |  | 36545.5 | 36545.5 | 81957 | 65781.9 | 188480 |  | 51619 | 12-06-2024 NEFT/AXISP00508731094/RIUP24/0736/WELCOME CONSTRUCTI/UBIN0563498 51619.00
62539 | GST release note |  | 170 | 65781.9 | [11 empty] | 65781.9 |  | 188478 | 12-06-2024 NEFT/AXISP00508731095/RIUP24/0737/WELCOME CONSTRUCTI/UBIN0563498 188478.00
62539 | [17 empty] | 115934 | 06-07-2024 NEFT/AXISP00516372440/RIUP24/0621/WELCOME CONSTRUCTI/UBIN0563498 ₹ 1,15,934.00
62539 | [17 empty] | 74250 | 03-08-2024 NEFT/AXISP00524511280/RIUP24/1350/WELCOME CONSTRUCTI/UBIN0563498 74250.00
[17 empty] | 0 |  |  | -8465.7
[10 empty] | 50476.75 | 0 | 100953.5 | 100953.5 | 81957 | 181716.3 | 846815.3 |  | 855281 |  | -8465.7
-8465.7
Welcome Construction & Company
Nakshatra - 13.08.24
[8 empty] | Total Hold |  | 252383.75
[8 empty] | DPR Excess Hold |  | 81957
[8 empty] | Advance / Surplus |  | -8465.7
[8 empty] | GST Remaining |  | 65781.9